## 제출현황
2016-12-07 기준
|  | Total Doc. |  | Plan/Issue Doc. | [5 empty] | Delayed Doc. |  |  | Submitted
|  |  |  | FI |  | FA |  | FC
|  | FI | FA | Plan | Issue | Plan | Issue | Plan | Issue | FI | FA | FC
EM3팀 | EM(02) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
배치/운반기술팀 | GA(10) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
성능/프로세스기술팀 | PS(11) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
플랜트기술팀 | PT(12) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
기계기술팀(WT) | WT(13) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
기계기술팀(HVAC) | HVAC(13) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
기계기술팀(FF) | FF(13) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
배관기술팀 | PP(14) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
전력계통기술팀 | EL(15) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
계측제어기술팀 | I&C(16) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
토목기술팀 | CV(17) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
건축기술팀 | S&A(18) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
P/E Center Total |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0

## DDCL(DHI-PP) 2020-10-21
Documents & Drawings Control log For Grati Block 2 Add-on Project | [7 empty] | 380926
No. | Scope | Document No | Serial | Title | Pur | First Plan | Final Plan | Latest Issue to Client |  |  |  | Latest Reply from Client
| DHI/PP |  |  |  | FA/FI | FA | FC | Issue Date (To Owner) | DT No | DT Pur. | DT Rev. | Date | DT No. | Pur. | Rev. | Status
1 | DHI | GRT-DA01-P0ZEN-020001 | 020001 | DOCUMENT IDENTIFICATION | FA | 2017-01-10 | 2017-04-10 | 2017-04-18 | GRT-DS-IP-DT-170048 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A
2 | DHI | GRT-DA01-P0ZEN-020002 | 020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | FA | 2017-01-10 | 2017-04-10 | 2017-04-18 | GRT-DS-IP-DT-170048 | FC | 0 | 2017-06-01 | APPROVED | FC | 0 | A
3 | DHI | GRT-QM01-P0ZEN-040001 | 040001 | Shop Inspection and Test Plan for Manufacturing | FA | 2017-03-10 | 2017-06-10 | 2017-09-20 | GRT-DS-IP-DT-170311 | FC | 0 | 2017-09-26 | 040001-0 | FC | 0 | B
4 | DHI | GRT-QA00-P0H-040002 | 040002 | [HRSG]_NDE Procedure for HRSG HP Drum | FI | 2017-06-20 | 2017-09-20 | 2017-07-31 | GRT-DS-IP-DT-170214 | FC | 0 | 2017-08-11 |  | FC | 0 | A
5 | DHI | GRT-QA00-P0H-040003 | 040003 | [HRSG]_NDE Procedure for HRSG LP Drum | FI | 2017-06-20 | 2017-09-20 | 2017-07-31 | GRT-DS-IP-DT-170214 | FC | 0 | 2017-08-11 |  | FC | 0 | A
6 | DHI | GRT-QA00-P0H-040004 | 040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | FI | 2017-06-20 | 2017-09-20 | 2017-10-26 | GRT-DS-IP-DT-170377 | FC | 1 | 2017-11-02 | 040004-1 | FC | 1 | B
7 | DHI | GRT-QA00-P0H-040005 | 040005 | [HRSG]_NDE Procedure for HRSG Heat Exchanger | FI | 2017-06-20 | 2017-09-20 | 2017-10-26 | GRT-DS-IP-DT-170377 | FC | 1 | 2017-11-02 | 040005-1 | FC | 1 | A
8 | DHI | GRT-QA00-P0H-040006 | 040006 | [HRSG]_Shop Quality Manual for HRSG | FI | 2017-06-23 | 2017-09-23 | 2017-07-31 | GRT-DS-IP-DT-170214 | FC | 0 | 2017-08-11 |  | FC | 0 | A
9 | DHI | GRT-QA00-P0H-040007 | 040007 | [HRSG]_Welders List for HRSG Heat Exchanger | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040007-0 | FC | 0 | A
10 | DHI | GRT-QA00-P0H-040008 | 040008 | [HRSG]_WPS&PQR for HRSG Heat Exchanger | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040008-0 | FC | 0 | A
11 | DHI | GRT-QA00-P0H-040009 | 040009 | [HRSG]_Welders List for HRSG HP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040009-0 | FC | 0 | A
12 | DHI | GRT-QA00-P0H-040010 | 040010 | [HRSG]_WPS&PQR for HRSG HP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040010-0 | FC | 0 | A
13 | DHI | GRT-QA00-P0H-040011 | 040011 | [HRSG]_Welders List for HRSG LP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040011-0 | FC | 0 | A
14 | DHI | GRT-QA00-P0H-040012 | 040012 | [HRSG]_WPS&PQR for HRSG LP Drum | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040012-0 | FC | 0 | A
15 | DHI | GRT-QA00-P0H-040013 | 040013 | NDE Procedure for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040013-0 | FC | 0 | A
16 | DHI | GRT-QA00-P0H-040014 | 040014 | Heat Treatment Procedure for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040014-0 | FC | 0 | A
17 | DHI | GRT-QA00-P0H-040015 | 040015 | Welders List for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040015-0 | FC | 0 | A
18 | DHI | GRT-QA00-P0H-040016 | 040016 | WPS&PQR for HRSG Piping | FI | 2017-08-29 | 2017-11-29 | 2017-10-26 | GRT-DS-IP-DT-170330 | FC | 0 | 2017-11-02 | 040016-0 | FC | 0 | A
19 | DHI | GRT-QA00-P0H-040017 | 040017 | [HRSG]_Welding Consumable Control Procedure for HRSG Pressure Part | FI | 2017-09-06 | 2017-12-06 | 2017-09-29 | GRT-DS-IP-DT-170323 | FC | 0 | 2017-10-02 | 040017-0 | FC | 0 | A
20 | DHI | GRT-QA00-P0H-040018 | 040018 | [HRSG]_Welding Consumable Control Procedure for HRSG Piping | FI | 2017-09-28 | 2017-12-28 | 2018-01-06 | GRT-DS-IP-DT-180002 | FC | 0 | 2018-01-06 | 040018-0 | FC | 0 | A
21 | DHI | GRT-DP00-P0ZEN-070001 | 070001 | Painting specification | FA | 2017-06-21 | 2017-09-21 | 2017-11-29 | GRT-DS-IP-DT-170490 | FC | 0 | 2018-04-26 | 75-5th DRM | FC | 0 | A
22 | DHI | GRT-UC07-P0ZEN-100001 | 100001 | PLOT PLAN | FA | 2017-02-10 | 2017-06-06 | 2018-08-02 | GRT-DS-IP-DT-180194 | FC | 1 | 2018-08-14 | 1000001-1 | FC | 1 | A
23 | DHI | GRT-UC08-P0ZEN-100002 | 100002 | General Arrangement of Power Block | FA | 2017-03-17 | 2018-10-01 | 2018-10-02 | GRT-DS-IP-DT-180230 | FC | 0 | 2018-10-02 | 100002-1 | FC | 0 | A
24 | DHI | GRT-UE00-P0ZEN-100003 | 100003 | General Arrangement of Steam Turbine Building Ground Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100003-0 | FC | 0 | A
25 | DHI | GRT-UE00-P0ZEN-100004 | 100004 | General Arrangement of Steam Turbine Building Mezzanine Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100004-0 | FC | 0 | A
26 | DHI | GRT-UE00-P0ZEN-100005 | 100005 | General Arrangement of Steam Turbine Building Operating Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100005-0 | FC | 0 | A
27 | DHI | GRT-UE00-P0ZEN-100006 | 100006 | General Arrangement of Steam Turbine Building Deaerator Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100006-0 | FC | 0 | A
28 | DHI | GRT-UE00-P0ZEN-100007 | 100007 | General Arrangement of Steam Turbine Building Basement Floor | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100007-0 | FC | 0 | A
29 | DHI | GRT-UE00-P0ZEN-100008 | 100008 | General Arrangement of Steam Turbine Building Section A-A | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100008-0 | FC | 0 | A
30 | DHI | GRT-UE00-P0ZEN-100009 | 100009 | General Arrangement of Steam Turbine Building Section B-B | FA | 2017-03-17 | 2018-10-01 | 2018-07-19 | GRT-DS-IP-DT-180181 | FC | 0 | 2018-07-27 | 100009-0 | FC | 0 | A
31 | DHI | GRT-XG05-P0ZEN-110001 | 110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | FI | 2017-02-10 | 2017-07-14 | 2017-07-04 | GRT-DS-IP-DT-170145 | FC | 0 | 2017-07-19 |  | FC | 0 | B
32 | DHI | GRT-XG05-P0ZEN-110002 | 110002 | [Symbol & Legend]_P&I DIAGRAM | FA | 2017-02-10 | 2017-06-10 | 2017-05-30 | GRT-DS-IP-DT-170082 | FC | 0 | 2017-05-20 | 110002-1 | FC | 0 | A
33 | DHI | GRT-XG02-P0LBA-110003 | 110003 | [HP & LP steam system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2019-01-08 | GRT-DS-IP-DT-190001 | FC | 2 | 2019-01-08 | 110003-1 | FC | 2 | A
34 | DHI | GRT-XG02-P0LBG-110004 | 110004 | [AUX Steam System]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2018-09-12 | GRT-DS-IP-DT-180215 | FC | 2 | 2018-09-20 | 110004-2 | FC | 2 | A
35 | DHI | GRT-XG02-P0LCM-110005 | 110005 | [Steam drain system]_P&ID DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2018-09-12 | GRT-DS-IP-DT-180215 | FC | 2 | 2018-09-20 | 110005-2 | FC | 2 | A
36 | DHI | GRT-XG02-P0LA-110006 | 110006 | [Feedwater system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2020-01-21 | GRT-DS-IP-DT-200012 | FC | 2 | 2018-03-13 | 08.002/E04/PLNE/III/2018 | DCR | 1DCR2 | A
37 | DHI | GRT-XG02-P0LC-110007 | 110007 | [Condensate system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2017-10-26 | GRT-DS-IP-DT-170366 | FC | 1 | 2017-11-02 | 110007-0 | FC | 1 | A
38 | DHI | GRT-XG02-P0PA-110008 | 110008 | [Aux. Cooling Water System]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2020-01-22 | GRT-DS-IP-DT-200014 | FC | 1 | 2020-01-22 | 110008-3 | FC | 1 | A
39 | DHI | GRT-XG02-P0PG-110009 | 110009 | [Closed cooling water system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2020-01-22 | GRT-DS-IP-DT-200015 | FC | 2 | 2020-01-22 | 110009-3 | FC | 2 | A
40 | DHI | GRT-XG02-P0QJA-110010 | 110010 | [N2 Gas system]_P&I DIAGRAM | FA | 2017-02-22 | 2017-07-14 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 2 | 2018-04-26 | 87-5th DRM | FC | 2 | A
41 | DHI | GRT-CN00-P0ZEN-110100 | 110100 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT | FA | 2017-07-14 | 2017-10-12 | 2020-07-10 | GRT-DS-IP-DT-200061 | FC | 1
42 | DHI | GRT-CN00-P0ZEN-110102 | 110102 | [Plant Overall]_PLANT START - UP AND SHUT - DOWN PROCEDURE | FA | 2017-08-18 | 2017-11-16 | 2020-04-06 | GRT-DS-IP-DT-200037 | DCR | 0DCR2 | 2020-04-07 | 110102-2 | DCR | 0DCR2 | C
43 | DHI | GRT-YR01-P0ZEN-110103 | 110103 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE | FA | 2018-02-26 | 2018-05-27 | 2020-02-07 | GRT-DS-IP-DT-200011 | FC | 2 | 2020-02-07 | 110103-2 | FC | 2 | A
44 | DHI | GRT-CN00-P0ZEN-110104 | 110104 | [Plant Overall]_Hazardous Area Classification | FA | 2017-05-30 | 2017-08-28 | 2017-08-30 | GRT-DS-IP-DT-170267 | FC | 0 | 2017-09-08 | 110104-0 | FC | 0 | A
45 | DHI | GRT-YR01-P0ZEN-110105 | 110105 | [HP & LP steam system]_Pressure drop calculation | FA | 2017-03-30 | 2017-07-14 | 2017-07-19 | GRT-DS-IP-DT-170175 | FC | 0 | 2017-07-19 |  | FC | 0 | B
46 | DHI | GRT-CN00-P0ZEN-110106 | 110106 | [Steam drain system]_Flash tank calculation | FA | 2017-03-30 | 2017-07-14 | 2017-07-19 | GRT-DS-IP-DT-170175 | FC | 0 | 2017-07-19 |  | FC | 0 | B
47 | DHI | GRT-YR01-P0ZEN-110107 | 110107 | [Plant Overall]_STEAM FLUSHING - DIAGRAM | FI | 2018-04-06 | 2018-06-15 | 2018-07-19 | GRT-DS-IP-DT-180161 | FC | 0 | 2018-08-02 | 110107-0 | FC | 0 | A
48 | DHI | GRT-XW01-P0LBA-110200 | 110200 | [HP & LP steam system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170159 | FC | 0 | 2017-07-17 |  | FC | 0 | A
49 | DHI | GRT-XW01-P0LBG-110201 | 110201 | [AUX Steam System]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170159 | FC | 0 | 2017-07-17 |  | FC | 0 | A
50 | DHI | GRT-XW01-P0LA-110202 | 110202 | [Feedwater system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-05 | GRT-DS-IP-DT-170135 | FC | 0 | 2017-07-19 |  | FC | 0 | B
51 | DHI | GRT-XW01-P0LC-110203 | 110203 | [Condensate system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-05 | GRT-DS-IP-DT-170135 | FC | 0 | 2017-07-19 |  | FC | 0 | B
52 | DHI | GRT-XW01-P0PA-110204 | 110204 | [Aux. Cooling Water System]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A
53 | DHI | GRT-XW01-P0PG-110205 | 110205 | [Closed cooling water system]_DESIGN CRITERIA | FA | 2017-02-22 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A
54 | DHI | GRT-XW01-P0QJA-110206 | 110206 | [N2 Gas system]_Design Criteria | FA | 2017-02-22 | 2017-07-14 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 1 | 2018-04-26 | 81-5th DRM | FC | 1 | A
55 | DHI | GRT-XG07-P0LBA-110300 | 110300 | [Steam, Feedwater & Condensate system]_PROCESS FLOW DIAGRAM | FA | 2017-03-15 | 2017-07-14 | 2017-07-18 | GRT-DS-IP-DT-170174 | FC | 0 | 2017-07-19 |  | FC | 0 | B
56 | DHI | GRT-XG07-P0PA-110304 | 110304 | [Aux. & Closed Cooling Water System]_PROCESS FLOW DIAGRAM | FA | 2017-03-15 | 2017-07-14 | 2017-08-21 | GRT-DS-IP-DT-170236 | FC | 0 | 2017-08-22 |  | FC | 0 | B
57 | DHI | GRT-XS00-P0LBA-110400 | 110400 | [HP & LP steam system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-06-20 | GRT-DS-IP-DT-170123 | FC | 0 | 2017-06-20 |  | FC | 0 | A
58 | DHI | GRT-XS00-P0LBG-110401 | 110401 | [AUX Steam System]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-06-20 | GRT-DS-IP-DT-170123 | FC | 0 | 2017-06-20 |  | FC | 0 | A
59 | DHI | GRT-XS00-P0LA-110402 | 110402 | [Feedwater system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-07-05 | GRT-DS-IP-DT-170132 | FC | 0 | 2017-07-19 |  | FC | 0 | A
60 | DHI | GRT-XS00-P0LC-110403 | 110403 | [Condensate system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-05-23 | GRT-DS-IP-DT-170078 | FC | 0 | 2017-06-16 | 02.031/E04/PLNE/VI/2017 | FC | 0 | B
61 | DHI | GRT-XS00-P0PA-110404 | 110404 | [Aux. Cooling Water System]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A
62 | DHI | GRT-XS00-P0PG-110405 | 110405 | [Closed cooling water system]_SYSTEM DESCRIPTION | FA | 2017-02-28 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170149 | FC | 0 | 2017-07-19 |  | FC | 0 | A
63 | DHI | GRT-XS00-P0QJA-110406 | 110406 | [N2 Gas system]_system description | FA | 2017-02-28 | 2017-07-14 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 1 | 2018-04-26 | 82-5th DRM | FC | 1 | A
64 | DHI | GRT-XW03-P0LA-110500 | 110500 | [BFP_Design]_sizing Calculation | FA | 2017-03-03 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170157 | FC | 0 | 2017-07-17 |  | FC | 0 | B
65 | DHI | GRT-XW03-P0LC-110501 | 110501 | [CEP_Design]_sizing Calculation | FA | 2017-03-15 | 2017-06-13 | 2017-06-08 | GRT-DS-IP-DT-170101 | FC | 0 | 2017-06-08 | APPROVED | FC | 0 | A
66 | DHI | GRT-YD00-P0QJA-111000 | 111000 | [N2 Gas System]_General Arrangement Drawing | FA | 2017-08-08 | 2017-11-06 | 2017-11-27 | GRT-DS-IP-DT-170483 | FC | 0 | 2018-04-26 | 42-5th DRM | FC | 0 | A
67 | DHI | GRT-XW03-P0QJA-111001 | 111001 | [N2 Gas System_Design]_sizing Calculation | FA | 2017-04-07 | 2017-07-14 | 2017-07-19 | GRT-DS-IP-DT-170175 | FC | 0 | 2017-07-19 |  | FC | 0 | B
68 | DHI | GRT-CT00-P0QJA-111011 | 111011 | [N2 GAS SYSTEM]_OPERATION & MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-07-05 | GRT-DS-IP-DT-180150 | FC | 0 | 2018-07-12 | 111011-1 | FC | 0 | B
69 | DHI | GRT-YT01-P0LB-111100 | 111100 | [Bypass Valve & PRDS]_DATA SHEET FOR BYPASS AND PRDS | FA | 2017-07-14 | 2017-10-12 | 2017-12-15 | GRT-DS-IP-DT-170515 | FC | 1 | 2018-04-26 | 83-5th DRM | FC | 1 | A
70 | DHI | GRT-YK08-P0LB-111101 | 111101 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR BYPASS AND PRDS | FA | 2017-07-14 | 2017-10-12 | 2018-08-24 | GRT-DS-IP-DT-180210 | FC | 1 | 2018-08-30 | 111101-1 | FC | 1 | A
71 | DHI | GRT-YK08-P0LB-111102 | 111102 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR HYDRAULIC POWER UNIT | FI | 2017-07-28 | 2017-10-26 | 2020-01-18 | GRT-DS-IP-DT-200010 | FC | 2 | 2020-01-18 | 1111102-2 | FC | 2 | A
72 | DHI | GRT-YS18-P0LB-111103 | 111103 | [Bypass Valve & PRDS]_CIRCUIT DIAGRAM FOR HYDRAULIC POWER UNIT | FI | 2017-07-28 | 2017-10-26 | 2018-08-24 | GRT-DS-IP-DT-180210 | FC | 1 | 2018-08-30 | 111103-1 | FC | 1 | A
73 | DHI | GRT-XS01-P0LB-111105 | 111105 | [Bypass Valve & PRDS]_Operating Description for HPU system for Bypass System | FI | 2017-07-28 | 2017-10-26 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 44-5th DRM | FC | 0 | A
74 | DHI | GRT-YK09-P0LB-111106 | 111106 | [Bypass Valve & PRDS]_Sectional drawing | FI | 2017-07-14 | 2017-10-12 | 2018-08-24 | GRT-DS-IP-DT-180210 | FC | 1 | 2018-08-30 | 111106-1 | FC | 1 | A
75 | DHI | GRT-YS18-P0LB-111107 | 111107 | [Bypass Valve & PRDS]_P&ID for HPU | FA | 2017-07-28 | 2017-10-26 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 45-5th DRM | FC | 0 | A
76 | DHI | GRT-YL22-P0LB-111108 | 111108 | [Bypass Valve & PRDS]_Name Plate Drawing | FA | 2017-09-14 | 2017-12-13 | 2017-11-01 | GRT-DS-IP-DT-170431 | FC | 0 | 2018-04-26 | 3-5th DRM | FC | 0 | A
77 | DHI | GRT-XL35-P0LB-111109 | 111109 | [Bypass Valve & PRDS]_Instrument List & Database Sheet | FA | 2017-07-14 | 2017-10-12 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 46-5th DRM | FC | 0 | A
78 | DHI | GRT-YT01-P0LB-111110 | 111110 | [Bypass Valve & PRDS]_Data Sheet for HPU | FA | 2017-07-28 | 2017-10-26 | 2017-11-27 | GRT-DS-IP-DT-170472 | FC | 0 | 2018-04-26 | 47-5th DRM | FC | 0 | A
79 | DHI | GRT-YS18-P0LB-111111 | 111111 | [Bypass Valve & PRDS]_Pneumatic Diagram | FI | 2017-07-14 | 2017-10-12 | 2018-07-12 | GRT-DS-IP-DT-180173 | FC | 1 | 2018-07-19 | 111111-1 | FC | 1 | A
80 | DHI | GRT-YS00-P0LB-111112 | 111112 | [Bypass Valve & PRDS]_Wiring Diagram | FI | 2017-07-14 | 2017-10-12 | 2020-01-18 | GRT-DS-IP-DT-200010 | FC | 2 | 2020-01-18 | 1111102-2 | FC | 2 | A
81 | DHI | GRT-YK08-P0ZEN-111200 | 111200 | [Safety Relief Valve(DHI)]_OUTLINE DRAWING FOR SAFEY AND RELIEF VALVE | FI | 2017-09-26 | 2017-12-25 | 2017-10-13 | GRT-DS-IP-DT-170354 | FC | 0 | 2017-10-29 | 20.015/E04/PLNE/IX/2017 | FI | A | I
82 | DHI | GRT-YT01-P0ZEN-111201 | 111201 | [Safety Relief Valve(DHI)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | FA | 2017-09-26 | 2017-12-25 | 2017-10-13 | GRT-DS-IP-DT-170354 | FC | 0 | 2017-10-29 | 20.015/E04/PLNE/IX/2017 | FA | A | B
83 | DHI | GRT-CT00-P0LB-111210 | 111210 | [Bypass]_O&M Manual | FI | 2018-04-20 | 2018-05-31 | 2018-07-05 | GRT-DS-IP-DT-180150 | FC | 0 | 2018-07-12 | 111210-1 | FC | 0 | A
84 | DHI | GRT-YK08-P0LBG-111300 | 111300 | [Silencer]_OUTLINE DRAWING FOR SILENCER | FA | 2017-10-24 | 2018-01-22 | 2017-12-22 | GRT-DS-IP-DT-170432 | FC | 0 | 2018-04-26 | 84-5th DRM | FC | 0 | A
85 | DHI | GRT-YT01-P0LBG-111301 | 111301 | [Silencer]_DATA SHEET FOR SILENCER | FA | 2017-10-24 | 2018-01-22 | 2017-12-22 | GRT-DS-IP-DT-170432 | FC | 0 | 2018-04-26 | 85-5th DRM | FC | 0 | A
86 | DHI | GRT-YD00-P0PCC-113001 | 113001 | [Aux. Cooling Water Pump]_GENERAL ARRANGEMENT DRAWING FOR AUXILIARY COOLING WATER PUMP | FA | 2017-06-05 | 2017-09-03 | 2020-01-22 | GRT-DS-IP-DT-200013 | FC | 1 | 2020-01-22 | 113001-3 | FC | 1 | A
87 | DHI | GRT-YT01-P0PCC-113002 | 113002 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP | FA | 2017-06-05 | 2017-09-03 | 2020-01-22 | GRT-DS-IP-DT-200013 | FC | 1 | 2020-01-22 | 113002-3 | FC | 1 | A
88 | DHI | GRT-YK10-P0PCC-113003 | 113003 | [Aux. Cooling Water Pump]_Pump Sectional Drawing | FA | 2017-06-05 | 2017-09-03 | 2017-08-30 | GRT-DS-IP-DT-170260 | FC | 0 | 2017-09-08 | 113003-0 | FC | 0 | A
89 | DHI | GRT-YT01-P0PCC-113004 | 113004 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-06-05 | 2017-09-03 | 2017-08-30 | GRT-DS-IP-DT-170261 | FC | 0 | 2017-09-08 | 113004-0 | FC | 0 | B
90 | DHI | GRT-YD00-P0PCC-113005 | 113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-06-05 | 2017-09-03 | 2017-11-27 | GRT-DS-IP-DT-170482 | FC | 1 | 2018-04-26 | 48-5th DRM | FC | 1 | A
91 | DHI | GRT-YD00-P0PCC-113007 | 113007 | [Aux. Cooling Water Pump]_MAIN TERMINAL BOX DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-11-01 | GRT-DS-IP-DT-170426 | FC | 0 | 2017-11-02 | 113007-0 | FC | 0 | A
92 | DHI | GRT-YL22-P0PCC-113008 | 113008 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP | FA | 2017-08-12 | 2017-11-10 | 2017-10-13 | GRT-DS-IP-DT-170355 | FC | 0 | 2017-10-13 | 113008-0 | FC | 0 | B
93 | DHI | GRT-YL22-P0PCC-113009 | 113009 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-10-26 | GRT-DS-IP-DT-170358 | FC | 0 | 2017-11-02 | 113009-0 | FC | 0 | A
94 | DHI | GRT-XW03-P0PCC-113010 | 113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | FA | 2017-04-14 | 2017-09-03 | 2017-08-21 | GRT-DS-IP-DT-170236 | FC | 0 | 2017-08-22 |  | FC | 0 | B
95 | DHI | GRT-YL22-P0PCC-113017 | 113017 | [ACWP]_OPERATION & MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-06-28 | GRT-DS-IP-DT-180152 | FC | 0 | 2018-06-29 | 113017-1 | FC | 0 | A
96 | DHI | GRT-YD00-P0PGB-113101 | 113101 | [CCWP ]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2017-06-12 | 2017-09-10 | 2017-09-14 | GRT-DS-IP-DT-170295 | FC | 0 | 2017-09-18 | 13.010/E04/PLNE/IX/2017 | FA | B | B
97 | DHI | GRT-YT01-P0PGB-113102 | 113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | FA | 2017-06-12 | 2017-09-10 | 2017-09-14 | GRT-DS-IP-DT-170295 | FC | 0 | 2017-09-18 | 13.010/E04/PLNE/IX/2017 | FA | C | A
98 | DHI | GRT-YK10-P0PGB-113103 | 113103 | [CCWP ]_Pump Sectional Drawing | FA | 2017-06-12 | 2017-09-10 | 2017-08-30 | GRT-DS-IP-DT-170260 | FC | 0 | 2017-09-08 | 113103-0 | FC | 0 | A
99 | DHI | GRT-YT01-P0PGB-113104 | 113104 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-06-12 | 2017-09-10 | 2017-08-30 | GRT-DS-IP-DT-170261 | FC | 0 | 2017-09-08 | 113104-0 | FC | 0 | B
100 | DHI | GRT-YD00-P0PGB-113105 | 113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-06-12 | 2017-09-10 | 2017-11-27 | GRT-DS-IP-DT-170482 | FC | 1 | 2018-04-26 | 49-5th DRM | FC | 1 | A
101 | DHI | GRT-YD00-P0PGB-113107 | 113107 | [CCWP ]_MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-11-29 | GRT-DS-IP-DT-170494 | FC | 0 | 2018-04-26 | 50-5th DRM | FC | 0 | A
102 | DHI | GRT-YL22-P0PGB-113108 | 113108 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2017-08-12 | 2017-11-10 | 2017-10-13 | GRT-DS-IP-DT-170355 | FC | 0 | 2017-10-13 | 113108-0 | FC | 0 | B
103 | DHI | GRT-YL22-P0PGB-113109 | 113109 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2017-08-12 | 2017-11-10 | 2017-10-26 | GRT-DS-IP-DT-170358 | FC | 0 | 2017-11-02 | 113109-0 | FC | 0 | A
104 | DHI | GRT-XW03-P0PGB-113110 | 113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | FA | 2017-04-14 | 2017-07-14 | 2017-09-06 | GRT-DS-IP-DT-170272 | FC | 0 | 2017-09-08 | 113110-0 | FC | 0 | B
105 | DHI | GRT-YL22-P0PGB-113117 | 113117 | [CCWP]_OPERATION & MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-08-24 | GRT-DS-IP-DT-180211 | FC | 1 | 2018-08-30 | 113117-2 | FC | 1 | A
106 | DHI | GRT-YT01-P0PGB-113200 | 113200 | [Blowdown Cooler]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | FA | 2017-07-24 | 2017-10-22 | 2017-08-21 | GRT-DS-IP-DT-170239 | FC | 0 | 2017-08-22 |  | FC | 0 | B
107 | DHI | GRT-YD00-P0PGB-113201 | 113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | FA | 2017-07-24 | 2017-10-22 | 2017-11-27 | GRT-DS-IP-DT-170481 | FC | 1 | 2018-04-26 | 51-5th DRM | FC | 1 | A
108 | DHI | GRT-YD00-P0PGB-113205 | 113205 | [Blowdown Cooler]_INSTALLATION, OPERATION AND MAINTENANCE MANUAL | FI | 2018-04-20 | 2018-05-31 | 2018-06-28 | GRT-DS-IP-DT-180152 | FC | 0 | 2018-06-29 | 113205-1 | FC | 0 | A
109 | DHI | GRT-YK10-P0ZEN-113300 | 113300 | [MOV (Gate & Globe)(DHI)]_OUTLINE DRAWING FOR MOV (G&G) | FA | 2017-08-15 | 2017-11-13 | 2017-11-29 | GRT-DS-IP-DT-170488 | FC | 0 | 2018-04-26 | 52-5th DRM | FC | 0 | A
110 | DHI | GRT-YT01-P0ZEN-113301 | 113301 | [MOV (Gate & Globe)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (G&G) | FA | 2017-08-15 | 2017-11-13 | 2017-11-29 | GRT-DS-IP-DT-170488 | FC | 0 | 2018-04-26 | 53-5th DRM | FC | 0 | A
111 | DHI | GRT-YK10-P0ZEN-113400 | 113400 | [MOV (Butterfly)(DHI)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | FA | 2017-08-15 | 2017-11-13 | 2017-10-26 | GRT-DS-IP-DT-170383 | FC | 0 | 2017-11-02 | 113400-0 | FC | 0 | B
112 | DHI | GRT-YT01-P0ZEN-113401 | 113401 | [MOV (Butterfly)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | FA | 2017-08-15 | 2017-11-13 | 2017-10-26 | GRT-DS-IP-DT-170383 | FC | 0 | 2017-11-02 | 113401-0 | FC | 0 | B
113 | DHI | GRT-XG02-P0SC-120001 | 120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 1 | 2020-01-31 | 120001-3 | FC | 1 | A
114 | DHI | GRT-XG02-P0SC-120002 | 120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 1 | 2020-01-31 | 120002-3 | FC | 1 | A
115 | DHI | GRT-XG02-P0SC-120003 | 120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 2 | 2020-01-31 | 120003-3 | FC | 2 | A
116 | DHI | GRT-XS00-P0SC-120004 | 120004 | [Compressed air system]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | FA | 2017-02-20 | 2017-06-20 | 2017-06-16 | GRT-DS-IP-DT-170113 | FC | 0 | 2017-06-16 |  | FC | 0 | A
117 | DHI | GRT-XS00-P0SC-120005 | 120005 | [Compressed air system]_DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | FA | 2017-02-06 | 2017-06-06 | 2017-07-20 | GRT-DS-IP-DT-170118 | FC | 1 | 2018-04-26 | 4-5th DRM | FC | 1 | A
118 | DHI | GRT-XW03-P0SC-120006 | 120006 | [Compressed air system]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | FA | 2017-02-06 | 2017-07-14 | 2017-07-24 | GRT-DS-IP-DT-170202 | FC | 0 | 2017-07-24 |  | FC | 0 | B
119 | DHI | GRT-YD00-P0SCA-120007 | 120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | FA | 2017-04-20 | 2017-07-19 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 3 | 2020-01-31 | 120007-3 | FC | 3 | A
120 | DHI | GRT-XG02-P0SCA-120008 | 120008 | [Air Compressor]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | FA | 2017-04-20 | 2017-07-19 | 2017-08-15 | GRT-DS-IP-DT-170232 | FC | 0 | 2017-09-11 | 04.032/E04/PLNE/VIII/2017 | FA | B | A
121 | DHI | GRT-XW01-P0SCA-120009 | 120009 | [Air Compressor]_AIR COMPRESSOR SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | A
122 | DHI | GRT-XW01-P0SCA-120010 | 120010 | [Air Compressor]_AIR DRYER SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | B
123 | DHI | GRT-XW01-P0SCA-120011 | 120011 | [Air Compressor]_AIR RECEIVER SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | A
124 | DHI | GRT-XW01-P0SCA-120012 | 120012 | [Air Compressor]_AIR FILTER SPECIFICATION | FA | 2017-04-20 | 2017-07-19 | 2017-07-27 | GRT-DS-IP-DT-170203 | FC | 0 | 2017-08-03 |  | FC | 0 | A
125 | DHI | GRT-XB00-P0SCA-120013 | 120013 | [Air Compressor]_FOUNDATION DRAWINGS | FI | 2017-04-20 | 2017-07-19 | 2017-09-15 | GRT-DS-IP-DT-170297 | FC | 1 | 2017-09-26 | 120013-0 | FC | 1 | A
126 | DHI | GRT-YU02-P0SCA-120014 | 120014 | [Air Compressor]_SINGLE LINE DIAGRAM | FA | 2017-05-20 | 2017-09-17 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 1 | 2020-01-31 | 120014-3 | FC | 1 | A
127 | DHI | GRT-YV02-P0SCA-120015 | 120015 | [Air Compressor]_ELECTRICAL WIRING DIAGRAMS | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120015-0 | FC | 0 | A
128 | DHI | GRT-YU03-P0SCA-120016 | 120016 | [Air Compressor]_ELECTRICAL SCHEMATIC DIAGRAM | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120016-0 | FC | 0 | A
129 | DHI | GRT-YF02-P0SCA-120017 | 120017 | [Air Compressor]_CONTROL DESCRIPTION (PHILOSOPHY) | FA | 2017-05-20 | 2017-09-17 | 2017-09-29 | GRT-DS-IP-DT-170329 | FC | 0 | 2017-10-02 | 120017-0 | FC | 0 | B
130 | DHI | GRT-YD05-P0SCA-120018 | 120018 | [Air Compressor]_PLC HMI GRAPHICS | FA | 2017-06-20 | 2017-10-18 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120018-0 | FC | 0 | A
131 | DHI | GRT-YL01-P0SCA-120019 | 120019 | [Air Compressor]_PLC HARDWIRED IO LIST | FA | 2017-05-20 | 2017-09-17 | 2017-09-20 | GRT-DS-IP-DT-170300 | FC | 0 | 2017-09-26 | 120019-0 | FC | 0 | B
132 | DHI | GRT-YL01-P0SCA-120020 | 120020 | [Air Compressor]_DATALINK INTERFACE IO LIST | FA | 2017-05-20 | 2017-09-17 | 2017-09-20 | GRT-DS-IP-DT-170300 | FC | 0 | 2017-09-26 | 120020-0 | FC | 0 | B
133 | DHI | GRT-YF00-P0SCA-120021 | 120021 | [Air Compressor]_CONTROL LOGIC & LOOP DIAGRAM | FA | 2017-05-20 | 2017-09-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120021-0 | FC | 0 | A
134 | DHI | GRT-YV02-P0SCA-120022 | 120022 | [Air Compressor]_I&C WIRING DIAGRAMS | FI | 2017-05-20 | 2017-10-17 | 2020-01-24 | GRT-DS-IP-DT-200024 | FC | 2 | 2020-01-31 | 120022-3 | FC | 2 | A
135 | DHI | GRT-YL00-P0SCA-120023 | 120023 | [Air Compressor]_INSTRUMENT LIST | FA | 2017-05-20 | 2017-09-17 | 2017-09-22 | GRT-DS-IP-DT-170301 | FC | 0 | 2017-09-26 | 120023-0 | FC | 0 | A
136 | DHI | GRT-CV03-P0SCA-120024 | 120024 | [Air Compressor]_INSTRUMENT SPECIFICATION | FA | 2017-05-20 | 2017-09-17 | 2017-09-22 | GRT-DS-IP-DT-170301 | FC | 0 | 2017-09-26 | 120024-0 | FC | 0 | A
137 | DHI | GRT-YK00-P0SCA-120025 | 120025 | [Air Compressor]_INSTRUMENTATION HOOK - UP DRAWING | FA | 2017-05-20 | 2017-09-17 | 2017-09-22 | GRT-DS-IP-DT-170301 | FC | 0 | 2017-09-26 | 120025-0 | FC | 0 | A
138 | DHI | GRT-YF02-P0SCA-120026 | 120026 | [Air Compressor]_PLC PANEL DRAWING | FA | 2017-05-20 | 2017-09-17 | 2017-11-27 | GRT-DS-IP-DT-170484 | FC | 0 | 2017-12-18 | 120026-0 | FC | 0 | B
139 | DHI | GRT-XF00-P0SCA-120027 | 120027 | [Air Compressor]_NAME PLATE DRAWING | FA | 2017-06-20 | 2017-10-18 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120027-0 | FC | 0 | A
140 | DHI | GRT-XN00-P0SCA-120028 | 120028 | [Air Compressor]_VALVE LIST | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120028-0 | FC | 0 | A
141 | DHI | GRT-XW01-P0SCA-120029 | 120029 | [Air Compressor]_VALVE SPECIFICATION | FI | 2017-05-20 | 2017-10-17 | 2017-10-26 | GRT-DS-IP-DT-170394 | FC | 0 | 2017-11-02 | 120029-0 | FC | 0 | A
142 | DHI | GRT-CQ02-P0SCA-120030 | 120030 | [Air Compressor]_O & M MANUAL | FA | 2017-07-20 | 2017-11-17 | 2017-11-27 | GRT-DS-IP-DT-170484 | FC | 0 | 2017-12-18 | 120030-0 | FC | 0 | A
143 | DHI | GRT-XW01-P0SCA-120031 | 120031 | [Air Compressor]_MAIN MOTOR SPECIFICATION | FA | 2017-08-30 | 2017-10-30 | 2017-11-01 | GRT-DS-IP-DT-170438 | FC | 0 | 2017-11-02 | 120031-0 | FC | 0 | A
144 | DHI | GRT-YD00-P0LCB-121001 | 121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | FA | 2017-04-20 | 2017-07-20 | 2017-10-26 | GRT-DS-IP-DT-170376 | FC | 0 | 2018-04-26 | 5-5th DRM | FC | 0 | A
145 | DHI | GRT-XG02-P0LCB-121002 | 121002 | [Condensate Extraction Pump]_P&I DIAGRAM | FA | 2017-04-20 | 2017-07-20 | 2017-11-27 | GRT-DS-IP-DT-170469 | FC | 1 | 2017-12-18 | 121002-1 | FC | 1 | A
146 | DHI | GRT-YT01-P0LCB-121003 | 121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | FI | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170443 | FC | 1 | 2018-04-26 | 6-5th DRM | FC | 1 | A
147 | DHI | GRT-YK09-P0LCB-121004 | 121004 | [Condensate Extraction Pump]_PUMP SECTIONAL DRAWING | FA | 2017-05-20 | 2017-08-20 | 2017-08-21 | GRT-DS-IP-DT-170234 | FC | 0 | 2017-08-22 |  | FC | 0 | A
148 | DHI | GRT-YT01-P0LCB-121005 | 121005 | [Condensate Extraction Pump]_MECHANICAL SEAL SPECIFICATION | FA | 2017-06-20 | 2017-09-20 | 2017-11-01 | GRT-DS-IP-DT-170443 | FC | 1 | 2018-04-26 | 7-5th DRM | FC | 1 | A
149 | DHI | GRT-YT01-P0LCB-121006 | 121006 | [Condensate Extraction Pump]_COUPLING SPECIFICATION | FI | 2017-05-20 | 2017-08-20 | 2017-08-21 | GRT-DS-IP-DT-170234 | FC | 0 | 2017-08-22 |  | FC | 0 | A
150 | DHI | GRT-YT01-P0LCB-121007 | 121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | FI | 2017-06-20 | 2017-09-20 | 2017-11-27 | GRT-DS-IP-DT-170469 | FC | 0 | 2017-12-18 | 121007-0 | FC | 0 | A
151 | DHI | GRT-YD00-P0LCB-121008 | 121008 | [Condensate Extraction Pump]_FOUNDATION DRAWINGS | FA | 2017-04-20 | 2017-07-20 | 2017-08-15 | GRT-DS-IP-DT-170233 | FC | 0 | 2017-08-25 |  | FC | 0 | A
152 | DHI | GRT-YM01-P0LCB-121009 | 121009 | [Condensate Extraction Pump]_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2017-05-20 | 2017-09-20 | 2017-11-01 | GRT-DS-IP-DT-170443 | FC | 0 | 2018-04-26 | 8-5th DRM | FC | 0 | A
153 | DHI | GRT-YL00-P0LCB-121010 | 121010 | [Condensate Extraction Pump]_INSTRUMENT LIST | FI | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170411 | FC | 0 | 2017-11-02 | 121010-0 | FC | 0 | A
154 | DHI | GRT-YK00-P0LCB-121011 | 121011 | [Condensate Extraction Pump]_INSTRUMENTATION HOOK - UP DRAWING | FI | 2017-06-20 | 2017-10-20 | 2017-11-27 | GRT-DS-IP-DT-170469 | FC | 0 | 2017-12-18 | 121011-0 | FC | 0 | A
155 | DHI | GRT-YL22-P0LCB-121012 | 121012 | [Condensate Extraction Pump]_NAME PLATE DRAWING | FI | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170411 | FC | 0 | 2017-11-02 | 121012-0 | FC | 0 | A
156 | DHI | GRT-CQ02-P0LCB-121013 | 121013 | [Condensate Extraction Pump]_O&M MANUAL | FA | 2018-01-22 | 2018-04-22 | 2018-10-02 | GRT-DS-IP-DT-180231 | FC | 1 | 2018-10-02 | 121013-2 | FC | 1 | A
157 | DHI | GRT-YD00-P0LCB-121014 | 121014 | [Condensate Extraction Pump]_VFD OUTLINE AND DATA SHEET | FI | 2017-08-25 | 2017-10-25 | 2017-12-15 | GRT-DS-IP-DT-170514 | FC | 1 | 2018-04-26 | 76-5th DRM | FC | 1 | A
158 | DHI | GRT-XG02-P0LAC-122001 | 122001 | [HP Feed Water Pump]_P&I DIAGRAM | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 33-5th DRM | FC | 0 | A
159 | DHI | GRT-YD00-P0LAC-122002 | 122002 | [HP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | FA | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 9-5th DRM | FC | 0 | A
160 | DHI | GRT-YT01-P0LAC-122003 | 122003 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2017-04-20 | 2017-07-20 | 2017-11-13 | GRT-DS-IP-DT-170452 | FC | 0 | 2017-11-13 | 122003-0 | FC | 0 | B
161 | DHI | GRT-YK10-P0LAC-122004 | 122004 | [HP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | FA | 2017-05-20 | 2017-08-20 | 2017-09-25 | GRT-DS-IP-DT-170315 | FC | 0 | 2017-09-26 | 122004-0 | FC | 0 | A
162 | DHI | GRT-YT01-P0LAC-122005 | 122005 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 10-5th DRM | FC | 0 | A
163 | DHI | GRT-YT02-P0LAC-122006 | 122006 | [HP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | FA | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170405 | FC | 0 | 2017-11-02 | 122006-0 | FC | 0 | A
164 | DHI | GRT-YL22-P0LAC-122007 | 122007 | [HP Feed Water Pump]_NAME PLATE DRAWING | FA | 2017-06-20 | 2017-09-20 | 2017-09-25 | GRT-DS-IP-DT-170318 | FC | 0 | 2017-09-26 | 122007-0 | FC | 0 | A
165 | DHI | GRT-YL22-P0LAC-122008 | 122008 | [HP Feed Water Pump]_Hydraulic Coupling Data Sheet | FA | 2017-10-31 | 2017-11-30 | 2018-07-19 | GRT-DS-IP-DT-180174 | FC | 1 | 2018-08-02 | 122008-1 | FC | 1 | A
166 | DHI | GRT-CQ02-P0LAC-122022 | 122022 | [HP Feed Water Pump]_Operational & Maintenance Manual | FI | 2018-04-20 | 2018-05-31 | 2018-08-16 | GRT-DS-IP-DT-180202 | FC | 0 | 2018-08-30 | 122022-1 | FC | 0 | A
167 | DHI | GRT-XG02-P0LAC-122501 | 122501 | [LP Feed Water Pump]_P&I DIAGRAM | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 40-5th DRM | FC | 0 | A
168 | DHI | GRT-YD00-P0LAC-122502 | 122502 | [LP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | FA | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 11-5th DRM | FC | 0 | A
169 | DHI | GRT-YT01-P0LAC-122503 | 122503 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2017-04-20 | 2017-07-20 | 2017-11-13 | GRT-DS-IP-DT-170452 | FC | 0 | 2017-11-13 | 122503-0 | FC | 0 | B
170 | DHI | GRT-YK10-P0LAC-122504 | 122504 | [LP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | FA | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 12-5th DRM | FC | 0 | A
171 | DHI | GRT-YT01-P0LAC-122505 | 122505 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2017-04-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170417 | FC | 0 | 2018-04-26 | 13-5th DRM | FC | 0 | A
172 | DHI | GRT-YT02-P0LAC-122506 | 122506 | [LP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | FA | 2017-06-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170405 | FC | 0 | 2017-11-02 | 122506-0 | FC | 0 | A
173 | DHI | GRT-YL22-P0LAC-122507 | 122507 | [LP Feed Water Pump]_NAME PLATE DRAWING | FA | 2017-06-20 | 2017-09-20 | 2017-09-25 | GRT-DS-IP-DT-170318 | FC | 0 | 2017-09-26 | 122507-0 | FC | 0 | A
174 | DHI | GRT-YD00-P0LAC-122508 | 122508 | [LP Feed Water Pump]_VFD OUTLINE AND DATA SHEET | FI | 2017-08-25 | 2017-10-25 | 2018-07-26 | GRT-DS-IP-DT-180187 | FC | 1 | 2018-08-02 | 122508-1 | FC | 1 | A
175 | DHI | GRT-CQ02-P0LAC-122522 | 122522 | [LP Feed Water Pump]_Operational & Maintenance Manual | FI | 2018-04-20 | 2018-05-31 | 2018-08-16 | GRT-DS-IP-DT-180202 | FC | 0 | 2018-08-30 | 122522-1 | FC | 0 | A
176 | DHI | GRT-YD00-P0SM-123001 | 123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | FA | 2017-05-19 | 2017-08-18 | 2017-10-26 | GRT-DS-IP-DT-170379 | FC | 0 | 2017-11-02 | 123001-0 | FC | 0 | B
177 | DHI | GRT-YT01-P0SM-123002 | 123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | FA | 2017-05-19 | 2017-08-18 | 2017-10-26 | GRT-DS-IP-DT-170379 | FC | 0 | 2017-11-02 | 123002-0 | FC | 0 | B
178 | DHI | GRT-CQ02-P0SM-123003 | 123003 | [Crane & Hoist(DHI)]_HOIST_O&M MANUAL FOR HOIST | FI | 2018-04-20 | 2018-05-31 | 2018-06-05 | GRT-DS-IP-DT-180144 | FC | 0 | 2018-06-08 | 123003-1 | FC | 0 | A
179 | DHI | GRT-XG02-P0QC-130001 | 130001 | [Chemical Dosing System]_P&ID | FA | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130001-1 | FC | 1 | A
180 | DHI | GRT-XA00-P0QC-130002 | 130002 | [Chemical Dosing System]_GENERAL ARRANGEMENT DRAWING | FA | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130002-1 | FC | 1 | A
181 | DHI | GRT-XS00-P0QC-130003 | 130003 | [Chemical Dosing System]_SYSTEM DESCRIPTION | FA | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130003-1 | FC | 1 | A
182 | DHI | GRT-CC07-P0QC-130004 | 130004 | [Chemical Dosing System]_CALCULATION SHEET | FA | 2017-07-11 | 2017-10-23 | 2017-11-01 | GRT-DS-IP-DT-170421 | FC | 0 | 2017-11-03 | 130004-0 | FC | 0 | B
183 | DHI | GRT-YD00-P0QC-130005 | 130005 | [Chemical Dosing System]_CONTROL PANEL ARRANGEMENT DRAWING | FA | 2017-07-11 | 2017-10-23 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-06 | 130005-1 | FC | 1 | A
184 | DHI | GRT-YF02-P0QC-130006 | 130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | FA | 2017-07-11 | 2017-10-23 | 2017-12-22 | GRT-DS-IP-DT-170540 | FC | 1 | 2018-04-26 | 88-5th DRM | FC | 1 | A
185 | DHI | GRT-YL00-P0QC-130007 | 130007 | [Chemical Dosing System]_INSTRUMENT LIST | FI | 2017-07-11 | 2017-10-23 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-04-26 | 122-5th DRM | FC | 1 | A
186 | DHI | GRT-XN00-P0QC-130008 | 130008 | [Chemical Dosing System]_VALVE LIST | FI | 2017-07-11 | 2017-10-23 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130008-1 | FC | 1 | A
187 | DHI | GRT-XB02-P0QC-130009 | 130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | FI | 2017-08-10 | 2017-11-22 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-29 | 130009-1 | FC | 1 | B
188 | DHI | GRT-YK10-P0QC-130010 | 130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | FI | 2017-08-10 | 2017-11-22 | 2018-03-21 | GRT-DS-IP-DT-180071 | FC | 2 | 2018-03-27 | 130010-2 | FC | 2 | A
189 | DHI | GRT-XH01-P0QC-130011 | 130011 | [Chemical Dosing System]_PIPING ARRANGEMENT DRAWING | FI | 2017-08-10 | 2017-11-22 | 2018-01-19 | GRT-DS-IP-DT-180016 | FC | 1 | 2018-01-24 | 130011-1 | FC | 1 | A
190 | DHI | GRT-YT01-P0QC-130012 | 130012 | [Chemical Dosing System]_TECHNICAL DATASHEET | FA | 2017-08-10 | 2017-11-22 | 2017-11-13 | GRT-DS-IP-DT-170458 | FC | 0 | 2017-11-13 | 130012-0 | FC | 0 | A
191 | DHI | GRT-YT01-P0QC-130013 | 130013 | [Chemical Dosing System]_MOTOR DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2017-11-13 | GRT-DS-IP-DT-170458 | FC | 0 | 2017-11-13 | 130013-0 | FC | 0 | A
192 | DHI | GRT-YT01-P0QC-130014 | 130014 | [Chemical Dosing System]_PUMP DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2017-11-30 | GRT-DS-IP-DT-170498 | FC | 0 | 2017-12-18 | 130014-0 | FC | 0 | B
193 | DHI | GRT-YT01-P0QC-130015 | 130015 | [Chemical Dosing System]_VALVE DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130015-1 | FC | 1 | A
194 | DHI | GRT-YT01-P0QC-130016 | 130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | FA | 2017-08-10 | 2017-11-22 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130016-1 | FC | 1 | A
195 | DHI | GRT-YV02-P0QC-130017 | 130017 | [Chemical Dosing System]_INTERCONNECTION WIRING DIAGRAM | FI | 2017-09-09 | 2017-12-22 | 2019-04-01 | GRT-DS-IP-DT-190055 | FC | 1 | 2019-04-01 | 130017-2 | FC | 1 | A
196 | DHI | GRT-YL22-P0QC-130018 | 130018 | [Chemical Dosing System]_NAME PLATE DRAWING | FI | 2017-09-09 | 2017-12-22 | 2018-03-21 | GRT-DS-IP-DT-180074 | FC | 1 | 2018-03-27 | 130018-1 | FC | 1 | A
197 | DHI | GRT-YF00-P0QC-130019 | 130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2017-09-09 | 2017-12-22 | 2018-02-27 | GRT-DS-IP-DT-180046 | FC | 1 | 2018-03-01 | 130019-1 | FC | 1 | A
198 | DHI | GRT-YS01-P0QC-130020 | 130020 | [Chemical Dosing System]_SCHEMATIC DIAGRAM | FI | 2017-09-09 | 2017-12-22 | 2019-02-13 | GRT-DS-IP-DT-190024 | FC | 2 | 2019-02-13 | 130020-3 | FC | 2 | A
199 | DHI | GRT-YE00-P0QC-130021 | 130021 | [Chemical Dosing System]_CABLE TRAY LAYOUT DRAWING | FI | 2017-09-09 | 2017-12-22 | 2017-12-22 | GRT-DS-IP-DT-170538 | FC | 0 | 2018-04-26 | 90-5th DRM | FC | 0 | A
200 | DHI | GRT-YK00-P0QC-130022 | 130022 | [Chemical Dosing System]_HOOK UP DRAWING | FI | 2017-09-09 | 2017-12-22 | 2018-03-21 | GRT-DS-IP-DT-180071 | FC | 2 | 2018-03-27 | 130022-2 | FC | 2 | A
201 | DHI | GRT-CQ02-P0QC-130023 | 130023 | [Chemical Dosing System]_O&M MANUAL | FI | 2018-01-17 | 2018-05-01 | 2018-04-27 | GRT-DS-IP-DT-180118 | FC | 0 | 2018-05-04 | 130023-2 | FC | 0 | B
202 | DHI | GRT-XG02-P0QU-130024 | 130024 | [Sampling System]_P&ID | FA | 2017-06-20 | 2017-10-02 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 54-5th DRM | FC | 0 | A
203 | DHI | GRT-XA00-P0QU-130025 | 130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | FA | 2017-06-20 | 2017-10-02 | 2018-04-02 | GRT-DS-IP-DT-180079 | FC | 1 | 2018-04-13 | 130025-1 | FC | 1 | A
204 | DHI | GRT-XS00-P0QU-130026 | 130026 | [Sampling System]_SYSTEM DESCRIPTION | FA | 2017-06-20 | 2017-10-02 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 14-5th DRM | FC | 0 | A
205 | DHI | GRT-YF02-P0QU-130027 | 130027 | [Sampling System]_CONTROL CONFIGURATION DIAGRAM | FA | 2017-07-20 | 2017-11-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 15-5th DRM | FC | 0 | A
206 | DHI | GRT-YL00-P0QU-130028 | 130028 | [Sampling System]_INSTRUMENT LIST | FI | 2017-07-20 | 2017-11-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 16-5th DRM | FC | 0 | A
207 | DHI | GRT-XN00-P0QU-130029 | 130029 | [Sampling System]_VALVE LIST | FI | 2017-07-20 | 2017-11-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 55-5th DRM | FC | 0 | A
208 | DHI | GRT-YT01-P0QU-130030 | 130030 | [Sampling System]_TECHNICAL DATASHEET | FA | 2017-08-19 | 2017-12-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 17-5th DRM | FC | 0 | A
209 | DHI | GRT-YT01-P0QU-130031 | 130031 | [Sampling System]_INSTRUMENT DATA SHEET | FA | 2017-08-19 | 2017-12-01 | 2017-11-27 | GRT-DS-IP-DT-170470 | FC | 0 | 2018-04-26 | 18-5th DRM | FC | 0 | A
210 | DHI | GRT-YV02-P0QU-130032 | 130032 | [Sampling System]_INTERCONNECTION WIRING DIAGRAM | FI | 2017-09-18 | 2017-12-31 | 2018-04-13 | GRT-DS-IP-DT-180097 | FC | 1 | 2018-04-25 | 130032-1 | FC | 1 | A
211 | DHI | GRT-YF00-P0QU-130033 | 130033 | [Sampling System]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2017-09-18 | 2017-12-31 | 2017-11-13 | GRT-DS-IP-DT-170446 | FC | 0 | 2017-11-13 | 130033-0 | FC | 0 | A
212 | DHI | GRT-YS01-P0QU-130034 | 130034 | [Sampling System]_SCHEMATIC DIAGRAM | FI | 2017-09-18 | 2017-12-31 | 2018-04-13 | GRT-DS-IP-DT-180097 | FC | 1 | 2018-04-25 | 130034-1 | FC | 1 | A
213 | DHI | GRT-CQ02-P0QU-130035 | 130035 | [Sampling System]_O&M MANUAL | FI | 2017-12-17 | 2018-03-31 | 2018-04-02 | GRT-DS-IP-DT-180079 | FC | 0 | 2018-04-13 | 130035-1 | FC | 0 | A
214 | DHI | GRT-XG02-P0LDB-130036 | 130036 | [Condensate Filter System]_P&ID | FA | 2017-05-26 | 2017-09-08 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130036-1 | FC | 1 | A
215 | DHI | GRT-XA00-P0LDB-130037 | 130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | FA | 2017-05-26 | 2017-09-08 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130037-1 | FC | 1 | A
216 | DHI | GRT-XS00-P0LDB-130038 | 130038 | [Condensate Filter System]_SYSTEM DESCRIPTION | FA | 2017-05-26 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170434 | FC | 0 | 2018-04-26 | 19-5th DRM | FC | 0 | A
217 | DHI | GRT-CC07-P0LDB-130039 | 130039 | [Condensate Filter System]_CALCULATION SHEET | FA | 2017-05-26 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170434 | FC | 0 | 2018-04-26 | 20-5th DRM | FC | 0 | A
218 | DHI | GRT-YD00-P0LDB-130040 | 130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | FA | 2017-06-26 | 2017-10-08 | 2018-04-25 | GRT-DS-IP-DT-180110 | FC | 2 | 2018-04-27 | 130040-2 | FC | 2 | A
219 | DHI | GRT-YF02-P0LDB-130041 | 130041 | [Condensate Filter System]_CONTROL CONFIGURATION DIAGRAM | FA | 2017-06-26 | 2017-10-08 | 2017-11-29 | GRT-DS-IP-DT-170489 | FC | 0 | 2018-04-26 | 56-5th DRM | FC | 0 | A
220 | DHI | GRT-YL00-P0LDB-130042 | 130042 | [Condensate Filter System]_INSTRUMENT LIST | FI | 2017-06-26 | 2017-10-08 | 2017-11-01 | GRT-DS-IP-DT-170434 | FC | 0 | 2018-04-26 | 21-5th DRM | FC | 0 | A
221 | DHI | GRT-XN00-P0LDB-130043 | 130043 | [Condensate Filter System]_VALVE LIST | FI | 2017-06-26 | 2017-10-08 | 2017-11-27 | GRT-DS-IP-DT-170474 | FC | 0 | 2018-04-26 | 57-5th DRM | FC | 0 | A
222 | DHI | GRT-XB02-P0LDB-130044 | 130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | FI | 2017-06-26 | 2017-10-08 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130044-1 | FC | 1 | A
223 | DHI | GRT-YK10-P0LDB-130045 | 130045 | [Condensate Filter System]_EQUIPMENT ASSEMBLY DRAWING | FI | 2017-06-26 | 2017-10-08 | 2017-12-08 | GRT-DS-IP-DT-170500 | FC | 0 | 2017-12-08 | 130045-0 | FC | 0 | A
224 | DHI | GRT-XH01-P0LDB-130046 | 130046 | [Condensate Filter System]_PIPING ARRANGEMENT DRAWING | FI | 2017-06-26 | 2017-10-08 | 2017-11-30 | GRT-DS-IP-DT-170497 | FC | 0 | 2018-04-26 | 58-5th DRM | FC | 0 | A
225 | DHI | GRT-YT01-P0LDB-130047 | 130047 | [Condensate Filter System]_TECHNICAL DATASHEET | FA | 2017-07-25 | 2017-11-07 | 2017-11-27 | GRT-DS-IP-DT-170474 | FC | 0 | 2018-04-26 | 59-5th DRM | FC | 0 | A
226 | DHI | GRT-YT01-P0LDB-130050 | 130050 | [Condensate Filter System]_VALVE DATA SHEET | FA | 2017-07-25 | 2017-11-07 | 2017-11-27 | GRT-DS-IP-DT-170474 | FC | 0 | 2018-04-26 | 60-5th DRM | FC | 0 | A
227 | DHI | GRT-YT01-P0LDB-130051 | 130051 | [Condensate Filter System]_INSTRUMENT DATA SHEET | FA | 2017-07-25 | 2017-11-07 | 2017-11-13 | GRT-DS-IP-DT-170444 | FC | 0 | 2017-11-13 | 130051-0 | FC | 0 | A
228 | DHI | GRT-YV02-P0LDB-130052 | 130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130052-1 | FC | 1 | A
229 | DHI | GRT-YL22-P0LDB-130053 | 130053 | [Condensate Filter System]_NAME PLATE DRAWING | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130053-1 | FC | 1 | A
230 | DHI | GRT-YF00-P0LDB-130054 | 130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130054-1 | FC | 1 | A
231 | DHI | GRT-YS01-P0LDB-130055 | 130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | FI | 2017-08-24 | 2017-12-07 | 2020-01-15 | GRT-DS-IP-DT-200003 | FC | 3 | 2020-01-15 | 130055-3 | FC | 3 | A
232 | DHI | GRT-YE00-P0LDB-130056 | 130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | FI | 2017-08-24 | 2017-12-07 | 2018-03-12 | GRT-DS-IP-DT-180065 | FC | 1 | 2018-03-22 | 130056-1 | FC | 1 | A
233 | DHI | GRT-YK00-P0LDB-130057 | 130057 | [Condensate Filter System]_HOOK UP DRAWING | FI | 2017-08-24 | 2017-12-07 | 2017-11-13 | GRT-DS-IP-DT-170444 | FC | 0 | 2017-11-13 | 130057-0 | FC | 0 | A
234 | DHI | GRT-CQ02-P0LDB-130058 | 130058 | [Condensate Filter System]_O&M MANUAL | FI | 2017-11-23 | 2018-03-07 | 2018-03-28 | GRT-DS-IP-DT-180078 | FC | 0 | 2018-04-26 | 123-5th DRM | FC | 0 | A
235 | DHI | GRT-FF03-P0SGA-133001 | 133001 | [Fire Fighting System] Water Spray System P&ID for STG Enclosure Inside | FA | 2018-06-05 | 2018-09-07 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133001-0 | FC | 0 | A
236 | DHI | GRT-FF01-P0SGA-133002 | 133002 | [Fire Fighting System] Water Spray System Plan for STG Enclosure Inside | FA | 2018-06-15 | 2018-09-14 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133002-0 | FC | 0 | A
237 | DHI | GRT-XG11-P0SGA-133003 | 133003 | [Fire Fighting System] Single Line Diagram for STG Enclosure Inside | FA | 2018-06-15 | 2018-09-14 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133003-0 | FC | 0 | A
238 | DHI | GRT-FF02-P0SGA-133004 | 133004 | [Fire Fighting System] Detection and Alarm System Equipment Location Plan for STG Enclosure Inside | FA | 2018-06-15 | 2018-09-14 | 2018-08-16 | GRT-DS-IP-DT-180204 | FC | 0 | 2018-08-30 | 133004-0 | FC | 0 | A
239 | DHI | GRT-FF05-P0SGA-133005 | 133005 | [Fire Fighting System] Water Spray System Hydraulic Calculation | FA | 2018-06-15 | 2018-09-14 | 2018-08-02 | GRT-DS-IP-DT-180197 | FC | 0 | 2018-08-10 | 133005-0 | FC | 0 | A
240 | DHI | GRT-XJ00-P0LBA-140001 | 140001 | Piping ISO (Large Bore) - HP Steam | FI | 2017-06-09 | 2017-08-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140001-7 | FC | 3 | A
241 | DHI | GRT-XJ00-P0LBA-140002 | 140002 | Piping ISO (Large Bore) - LP Steam | FI | 2017-06-09 | 2017-08-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140002-7 | FC | 3 | A
242 | DHI | GRT-XJ00-P0LBG-140003 | 140003 | Piping ISO (Large Bore) - Aux. Steam | FI | 2017-06-16 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140003-7 | FC | 3 | A
243 | DHI | GRT-XJ00-P0LCM-140004 | 140004 | Piping ISO (Large Bore) - Steam drain | FI | 2017-06-09 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 2 | 2020-01-22 | 140004-7 | FC | 2 | A
244 | DHI | GRT-XJ00-P0LAB-140005 | 140005 | Piping ISO (Large Bore) - Feedwater | FI | 2017-06-16 | 2017-08-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 3 | 2020-01-22 | 140005-7 | FC | 3 | A
245 | DHI | GRT-XJ00-P0LCA-140006 | 140006 | Piping ISO (Large Bore) - Condensate | FI | 2017-06-16 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 2 | 2020-01-22 | 140006-7 | FC | 2 | A
246 | DHI | GRT-XJ00-P0PAB-140007 | 140007 | Piping ISO (Large Bore) - Aux. cooling water | FI | 2017-06-23 | 2018-01-31 | 2020-01-22 | GRT-DS-IP-DT-200006 | FC | 1 | 2020-01-22 | 140007-7 | FC | 1 | A
247 | DHI | GRT-XJ00-P0PGB-140008 | 140008 | Piping ISO (Large Bore) - CCW | FI | 2017-06-23 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 2 | 2020-02-07 | 140008-7 | FC | 2 | A
248 | DHI | GRT-XJ00-P0SCA-140009 | 140009 | Piping ISO (Large Bore) - Compressed air | FI | 2017-06-30 | 2018-01-31 | 2018-02-19 | GRT-DS-IP-DT-180039 | FC | 0 | 2018-03-01 | 140009-0 | FC | 0 | A
249 | DHI | GRT-XJ00-P0MAA-140010 | 140010 | Piping ISO (Large Bore) - ST Misc. | FI | 2017-06-30 | 2018-01-31 | 2018-02-19 | GRT-DS-IP-DT-180039 | FC | 0 | 2018-03-01 | 140010-0 | FC | 0 | A
250 | DHI | GRT-XJ00-P0TEM-140011 | 140011 | Piping ISO (Large Bore) - Steam blowing & flushing | FI | 2018-03-30 | 2018-06-01 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 1 | 2020-02-07 | 140011-5 | FC | 1 | A
251 | DHI | GRT-XJ00-P0PAB-140012 | 140012 | Piping ISO (Large Bore) - Cooling water | FI | 2017-08-11 | 2018-01-31 | 2018-02-19 | GRT-DS-IP-DT-180039 | FC | 0 | 2018-03-01 | 140012-0 | FC | 0 | A
252 | DHI | GRT-DP00-P0ZEN-141001 | 141001 | WPS&PQR for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 114-5th DRM | FC | 0 | A
253 | DHI | GRT-DP00-P0ZEN-141002 | 141002 | Heat treatment procedure for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 115-5th DRM | FC | 0 | A
254 | DHI | GRT-QA00-P0ZEN-141003 | 141003 | Welder qualificatoin list for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 116-5th DRM | FC | 0 | A
255 | DHI | GRT-DP00-P0ZEN-141004 | 141004 | Repair welding procedure for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 117-5th DRM | FC | 0 | A
256 | DHI | GRT-QA00-P0ZEN-141005 | 141005 | Welder consumable control procedure for BOP Piping | FI | 2017-09-15 | 2017-12-15 | 2017-12-22 | GRT-DS-IP-DT-170528 | FC | 0 | 2018-04-26 | 118-5th DRM | FC | 0 | A
257 | DHI | GRT-QM03-P0ZEN-141006 | 141006 | RADIOGRAPHIC EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 77-5th DRM | FC | 0 | A
258 | DHI | GRT-QM03-P0ZEN-141007 | 141007 | ULTRASONIC EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 78-5th DRM | FC | 0 | A
259 | DHI | GRT-QM03-P0ZEN-141008 | 141008 | MAGNETIC PARTICLE EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 79-5th DRM | FC | 0 | A
260 | DHI | GRT-QM03-P0ZEN-141009 | 141009 | LIQUID PENETRANT EXAMINATION PROCEDURE | FA | 2017-10-11 | 2017-11-13 | 2017-11-27 | GRT-DS-IP-DT-170461 | FC | 0 | 2018-04-26 | 80-5th DRM | FC | 0 | A
261 | DHI | GRT-XJ00-P0LBA-143001 | 143001 | Piping ISO (Small Bore) - HP Steam | FI | 2017-07-07 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143001-5 | FC | 2 | A
262 | DHI | GRT-XJ00-P0LBA-143002 | 143002 | Piping ISO (Small Bore) - LP Steam | FI | 2017-07-07 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143002-5 | FC | 2 | A
263 | DHI | GRT-XJ00-P0LBG-143003 | 143003 | Piping ISO (Small Bore) - Aux. Steam | FI | 2017-07-14 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143003-5 | FC | 2 | A
264 | DHI | GRT-XJ00-P0LCM-143004 | 143004 | Piping ISO (Small Bore) - Steam drain | FI | 2017-07-07 | 2018-01-31 | 2017-12-29 | GRT-DS-IP-DT-170543 | FC | 0 | 2018-04-26 | 127-5th DRM | FC | 0 | A
265 | DHI | GRT-XJ00-P0LAB-143005 | 143005 | Piping ISO (Small Bore) - Feedwater | FI | 2017-07-14 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 2 | 2020-02-07 | 143005-5 | FC | 2 | A
266 | DHI | GRT-XJ00-P0LCA-143006 | 143006 | Piping ISO (Small Bore) - Condensate | FI | 2017-07-14 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 3 | 2020-02-07 | 143006-5 | FC | 3 | A
267 | DHI | GRT-XJ00-P0PAB-143007 | 143007 | Piping ISO (Small Bore) - Aux. cooling water | FI | 2017-07-21 | 2018-01-31 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 3 | 2020-02-07 | 143007-5 | FC | 3 | A
268 | DHI | GRT-XJ00-P0PGB-143008 | 143008 | Piping ISO (Small Bore) - CCW | FI | 2017-07-21 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143008-3 | FC | 2 | A
269 | DHI | GRT-XJ00-P0QJA-143009 | 143009 | Piping ISO (Small Bore) - N2 | FI | 2017-07-21 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 3 | 2020-01-31 | 143009-3 | FC | 3 | A
270 | DHI | GRT-XJ00-P0SCA-143010 | 143010 | Piping ISO (Small Bore) - Compressed air | FI | 2017-07-28 | 2018-01-31 | 2018-04-02 | GRT-DS-IP-DT-180082 | FC | 1 | 2018-04-10 | 143010-1 | FC | 1 | A
271 | DHI | GRT-XJ00-P0SCB-143011 | 143011 | Piping ISO (Small Bore) - Service air | FI | 2017-07-28 | 2018-01-31 | 2018-04-02 | GRT-DS-IP-DT-180086 | FC | 1 | 2018-04-06 | 143011-1 | FC | 1 | A
272 | DHI | GRT-XJ00-P0QFB-143012 | 143012 | Piping ISO (Small Bore) - Instrument air | FI | 2017-07-28 | 2018-01-31 | 2018-07-26 | GRT-DS-IP-DT-180190 | FC | 2 | 2018-08-02 | 143012-2 | FC | 2 | A
273 | DHI | GRT-XJ00-P0MAA-143013 | 143013 | Piping ISO (Small Bore) - ST Misc. | FI | 2017-07-28 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143013-3 | FC | 2 | A
274 | DHI | GRT-XJ00-P0LCW-143014 | 143014 | Piping ISO (Small Bore) - Seal Water | FI | 2017-07-21 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 1 | 2020-01-31 | 143014-3 | FC | 1 | A
275 | DHI | GRT-XJ00-P0PAB-143015 | 143015 | Piping ISO (Small Bore) - Cooling water | FI | 2017-07-07 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143015-3 | FC | 2 | A
276 | DHI | GRT-XJ00-P0QC-143016 | 143016 | Piping ISO (Small Bore) - Chemical dosing | FI | 2017-07-14 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 2 | 2020-01-31 | 143016-2 | FC | 2 | A
277 | DHI | GRT-XJ00-P0QUA-143017 | 143017 | Piping ISO (Small Bore) - Sampling | FI | 2017-07-28 | 2018-01-31 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 3 | 2020-01-31 | 143017-3 | FC | 3 | A
278 | DHI | GRT-XK00-P0LBA-144001 | 144001 | Support DWG (Large Bore) - HP Steam | FI | 2017-08-15 | 2017-11-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 2 | 2020-02-07 | 144001-7 | FC | 2 | A
279 | DHI | GRT-XK00-P0LBA-144002 | 144002 | Support DWG (Large Bore) - LP Steam | FI | 2017-08-15 | 2017-11-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 3 | 2020-02-07 | 144002-7 | FC | 3 | A
280 | DHI | GRT-XK00-P0LBG-144003 | 144003 | Support DWG (Large Bore) - Aux. Steam | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 4 | 2020-02-07 | 144003-7 | FC | 4 | A
281 | DHI | GRT-XK00-P0LCM-144004 | 144004 | Support DWG (Large Bore) - Steam drain | FI | 2017-12-31 | 2018-01-30 | 2018-03-22 | GRT-DS-IP-DT-180040 | FC | 0 | 2018-04-06 | 144004-1 | FC | 0 | B
282 | DHI | GRT-XK00-P0LAB-144005 | 144005 | Support DWG (Large Bore) - Feedwater | FI | 2017-08-15 | 2017-11-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 3 | 2020-02-07 | 144005-7 | FC | 3 | A
283 | DHI | GRT-XK00-P0LCA-144006 | 144006 | Support DWG (Large Bore) - Condensate | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 2 | 2020-02-07 | 144006-7 | FC | 2 | A
284 | DHI | GRT-XK00-P0PAB-144007 | 144007 | Support DWG (Large Bore) - Aux. cooling water | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144007-7 | FC | 1 | A
285 | DHI | GRT-XK00-P0PGB-144008 | 144008 | Support DWG (Large Bore) - CCW | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144008-7 | FC | 1 | A
286 | DHI | GRT-XK00-P0SCA-144009 | 144009 | Support DWG (Large Bore) - Compressed air | FI | 2017-12-31 | 2018-01-30 | 2018-03-22 | GRT-DS-IP-DT-180040 | FC | 0 | 2018-04-06 | 144009-1 | FC | 0 | B
287 | DHI | GRT-XK00-P0MAA-144010 | 144010 | Support DWG (Large Bore) - ST Misc. | FI | 2017-12-31 | 2018-01-30 | 2018-09-12 | GRT-DS-IP-DT-180214 | FC | 1 | 2018-09-20 | 144010-2 | FC | 1 | A
288 | DHI | GRT-XK00-P0TEM-144011 | 144011 | Support DWG (Large Bore) - Steam blowing | FI | 2018-04-30 | 2018-06-01 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144011-7 | FC | 1 | A
289 | DHI | GRT-XK00-P0PAB-144012 | 144012 | Support DWG (Large Bore) - Cooling Water | FI | 2017-12-31 | 2018-01-30 | 2020-02-07 | GRT-DS-IP-DT-200025 | FC | 1 | 2020-02-07 | 144012-7 | FC | 1 | A
290 | DHI | GRT-DE00-P0ZEN-144500 | 144500 | [Piping General]_Piping material specification (BOP) | FA | 2017-03-03 | 2017-06-09 | 2017-11-27 | GRT-DS-IP-DT-170475 | FC | 1 | 2018-04-26 | 61-5th DRM | FC | 1 | A
291 | DHI | GRT-DE00-P0ZEN-144501 | 144501 | [Piping General]_Piping Insulation Specification (BOP) | FA | 2017-04-07 | 2017-07-07 | 2020-02-07 | GRT-DS-IP-DT-200009 | FC | 1 | 2020-02-07 | 144501-5 | FC | 1 | A
292 | DHI | GRT-YT10-P0ZEN-144502 | 144502 | [Piping General]_Pipe Thickness Calculation (BOP) | FA | 2017-03-17 | 2017-06-16 | 2017-11-27 | GRT-DS-IP-DT-170475 | FC | 1 | 2018-04-26 | 62-5th DRM | FC | 1 | A
293 | DHI | GRT-XL00-P0ZEN-144503 | 144503 | [Piping General]_Piping Line List (BOP) | FA | 2017-03-31 | 2017-06-30 | 2017-07-31 | GRT-DS-IP-DT-170213 | FC | 0 | 2017-08-25 |  | FC | 0 | A
294 | DHI | GRT-XL00-P0ZEN-144504 | 144504 | [Piping General]_Piping Specialty List (BOP) | FA | 2017-03-31 | 2017-06-30 | 2017-07-31 | GRT-DS-IP-DT-170213 | FC | 0 | 2017-08-25 |  | FC | 0 | A
295 | DHI | GRT-XN00-P0ZEN-144505 | 144505 | [Piping General]_Manual Valve List (BOP) | FA | 2017-03-31 | 2017-06-30 | 2017-07-31 | GRT-DS-IP-DT-170213 | FC | 0 | 2017-08-25 |  | FC | 0 | A
296 | DHI | GRT-XK00-P0ZEN-144511 | 144511 | [Piping General]_Typical Installation Drawing for Pipe Support | FA | 2017-06-15 | 2017-08-18 | 2020-01-31 | GRT-DS-IP-DT-200023 | FC | 1 | 2020-01-31 | 144511-3 | FC | 1 | A
297 | DHI | GRT-DF04-P0ZEN-144512 | 144512 | [Piping General]_Stress Analysis Report for HP steam system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180125 | FC | 1 | 2018-05-16 | 144512-1 | FC | 1 | A
298 | DHI | GRT-DF04-P0ZEN-144513 | 144513 | [Piping General]_Stress Analysis Report for LP steam system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180126 | FC | 1 | 2018-05-16 | 144513-1 | FC | 1 | A
299 | DHI | GRT-DF04-P0ZEN-144514 | 144514 | [Piping General]_Stress Analysis Report for Aux.steam system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180127 | FC | 1 | 2018-05-16 | 144514-1 | FC | 1 | A
300 | DHI | GRT-DF04-P0ZEN-144515 | 144515 | [Piping General]_Stress Analysis Report for Feedwater system | FA | 2017-06-23 | 2017-09-15 | 2018-05-16 | GRT-DS-IP-DT-180128 | FC | 1 | 2018-05-16 | 144515-1 | FC | 1 | A
301 | DHI | GRT-XH01-P0UMA-144521 | 144521 | [Steam Turbine Building_Piping]_Piping Arrangement | FA | 2017-06-02 | 2017-09-29 | 2018-02-21 | GRT-DS-IP-DT-180045 | FC | 1 | 2018-03-01 | 144521-1 | FC | 1 | A
302 | DHI | GRT-XH01-P0UZT-144522 | 144522 | [Pipe Rack_Piping]_Piping Arrangement | FA | 2017-06-02 | 2017-09-29 | 2018-02-21 | GRT-DS-IP-DT-180045 | FC | 1 | 2018-03-01 | 144522-1 | FC | 1 | A
303 | DHI | GRT-XH01-P0UTG-144523 | 144523 | [N2 Gas Shelter_Piping]_Piping Arrangement | FA | 2017-06-02 | 2017-09-29 | 2018-02-21 | GRT-DS-IP-DT-180045 | FC | 1 | 2018-03-01 | 144523-1 | FC | 1 | A
304 | DHI | GRT-XK00-P0ZEN-144900 | 144900 | Outline Drawing for Piping Manual Ball Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144900-1 | FC | 1 | B
305 | DHI | GRT-XK00-P0ZEN-144901 | 144901 | Outline Drawing for Piping Manual Butterfly Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144901-1 | FC | 1 | B
306 | DHI | GRT-XK00-P0ZEN-144902 | 144902 | Outline Drawing for Piping HP Manual Casting Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144902-1 | FC | 1 | A
307 | DHI | GRT-XK00-P0ZEN-144903 | 144903 | Outline Drawing for Piping LP Manual Casting Valve | FI | 2017-11-15 | 2017-12-01 | 2018-03-21 | GRT-DS-IP-DT-180042 | FC | 1 | 2018-03-27 | 144903-1 | FC | 1 | A
308 | DHI | GRT-XK00-P0ZEN-144904 | 144904 | Outline Drawing for Piping HP Manual Forging Valve | FI | 2017-11-15 | 2017-12-01 | 2018-04-13 | GRT-DS-IP-DT-180090 | FC | 2 | 2018-04-27 | 144904-2 | FC | 2 | A
309 | DHI | GRT-XK00-P0ZEN-144905 | 144905 | Outline Drawing for Piping LP Manual Forging Valve | FI | 2017-11-15 | 2017-12-01 | 2018-04-13 | GRT-DS-IP-DT-180090 | FC | 2 | 2018-04-27 | 144905-2 | FC | 2 | A
310 | DHI | GRT-XW01-P0ZEN-161001 | 161001 | [INC_Plant_Overall_Design]_I&C General Design Criteria | FA | 2017-03-03 | 2017-07-14 | 2020-01-18 | GRT-DS-IP-DT-200016 | FC | 1 | 2020-01-18 | 161001-1 | FC | 1 | A
311 | DHI | GRT-MA01-P0ZEN-161002 | 161002 | [INC_Plant_Overall_Design]_Plant Control System Configuration Diagram | FA | 2017-03-31 | 2017-07-14 | 2020-01-18 | GRT-DS-IP-DT-200016 | FC | 1 | 2020-01-18 | 161002-1 | FC | 1 | A
312 | DHI | GRT-YU04-P0ZEN-161003 | 161003 | [INC_Plant_Overall_Design]_Plant Control Block Diagram | FA | 2017-03-31 | 2017-07-14 | 2017-07-24 | GRT-DS-IP-DT-170188 | FC | 0 | 2017-07-27 |  | FC | 0 | A
313 | DHI | GRT-YF01-P0ZEN-161004 | 161004 | [INC_Plant_Overall_Design]_Plant Protection & Interlock Diagram | FA | 2017-04-07 | 2017-06-30 | 2017-08-23 | GRT-DS-IP-DT-170247 | FC | 0 | 2017-08-23 |  | FC | 0 | A
314 | DHI | GRT-MA02-P0ZEN-161006 | 161006 | [INC_Interface]_3rd Party Data-link Interface Concept Diagram | FA | 2017-03-31 | 2017-07-14 | 2020-01-18 | GRT-DS-IP-DT-200008 | FC | 1 | 2020-01-18 | 161006-3 | FC | 1 | A
315 | DHI | GRT-YL01-P0ZEN-161101 | 161101 | [INC_DCS_IO]_DCS I/O Database | FA | 2017-04-07 | 2017-06-30 | 2019-10-03 | GRT-DS-IP-DT-190144 | FC | 2 | 2019-10-03 | 161101-3 | FC | 2 | A
316 | DHI | GRT-YL01-P0ZEN-161102 | 161102 | [INC_DCS_IO]_3rd Party Data-link Interface Signal Database | FA | 2017-09-15 | 2017-11-03 | 2019-10-25 | GRT-DS-IP-DT-190151 | FC | 2 | 2019-10-25 | 161102-2 | FC | 2 | A
317 | DHI | GRT-CV03-P0ZEN-161110 | 161110 | [DCS]_Functional Design Specification for Hardware | FA | 2017-03-31 | 2017-06-30 | 2017-07-27 | GRT-DS-IP-DT-170210 | FC | 0 | 2017-08-03 |  | FC | 0 | A
318 | DHI | GRT-CV03-P0ZEN-161111 | 161111 | [DCS]_Functional Design Specification for Software | FA | 2017-03-31 | 2017-06-30 | 2017-09-06 | GRT-DS-IP-DT-170275 | FC | 0 | 2017-09-08 | 161111-0 | FC | 0 | A
319 | DHI | GRT-CV03-P0ZEN-161112 | 161112 | [DCS]_Functional Design Specification for Graphic | FA | 2017-04-07 | 2017-07-07 | 2017-11-27 | GRT-DS-IP-DT-170454 | FC | 0 | 2018-04-26 | 24-5th DRM | FC | 0 | A
320 | DHI | GRT-YD06-P0ZEN-161113 | 161113 | [INC_Plant_Overall_Design]_DCS Power Distribution Concept Diagram | FA | 2017-03-31 | 2017-06-30 | 2017-09-14 | GRT-DS-IP-DT-170287 | FC | 0 | 2017-09-18 | 161113-0 | FC | 0 | A
321 | DHI | GRT-YE03-P0ZEN-161114 | 161114 | [DCS]_Grounding Concept & Drawing | FA | 2017-03-31 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170182 | FC | 0 | 2017-07-24 |  | FC | 0 | A
322 | DHI | GRT-YD06-P0ZEN-161115 | 161115 | [DCS]_Equipment Power Distribution Diagram | FA | 2017-03-31 | 2017-06-30 | 2017-10-30 | GRT-DS-IP-DT-170409 | FC | 0 | 2017-11-02 | 161115-0 | FC | 0 | A
323 | DHI | GRT-CV03-P0ZEN-161116 | 161116 | [DCS]_Functional Design Specification for Safety Related System | FA | 2017-04-21 | 2017-06-30 | 2017-10-26 | GRT-DS-IP-DT-170398 | FC | 0 | 2017-11-02 | 161116-0 | FC | 0 | A
324 | DHI | GRT-CV03-P0ZEN-161117 | 161117 | [DCS]_Functional Design Specification for Performance Monitoring System | FA | 2017-04-21 | 2017-06-30 | 2017-10-26 | GRT-DS-IP-DT-170402 | FC | 0 | 2017-11-02 | 161117-0 | FC | 0 | A
325 | DHI | GRT-MA02-P0ZEN-161121 | 161121 | [DCS]_LAN Configuration Diagram | FA | 2017-03-31 | 2017-06-30 | 2020-01-22 | GRT-DS-IP-DT-200021 | FC | 1 | 2020-01-22 | 161121-3 | FC | 1 | A
326 | DHI | GRT-YD07-P0ZEN-161122 | 161122 | [DCS]_IO & Module Allocation | FA | 2017-04-21 | 2017-07-07 | 2019-02-11 | GRT-DS-IP-DT-190021 | FC | 2 | 2019-02-11 | 161122-2 | FC | 2 | A
327 | DHI | GRT-YD05-P0ZEN-161123 | 161123 | [DCS]_HMI Graphic Drawing | FA | 2017-09-15 | 2017-11-03 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161123-1 | FC | 1 | A
328 | DHI | GRT-YR05-P0ZEN-161131 | 161131 | [DCS]_Outline & Detail Drawing for Console desk & Computer desk & Printer desk | FA | 2017-04-07 | 2017-07-07 | 2020-01-22 | GRT-DS-IP-DT-200021 | FC | 1 | 2020-01-22 | 161131-3 | FC | 1 | A
329 | DHI | GRT-YR05-P0ZEN-161132 | 161132 | [DCS]_Outline & Detail Drawing for LAN Cabinet | FA | 2017-04-07 | 2017-07-07 | 2017-11-27 | GRT-DS-IP-DT-170454 | FC | 0 | 2018-04-26 | 27-5th DRM | FC | 0 | A
330 | DHI | GRT-YR05-P0ZEN-161133 | 161133 | [DCS]_Outline & Detail Drawing for Power Distribution Cabinet | FA | 2017-04-07 | 2017-07-07 | 2020-01-22 | GRT-DS-IP-DT-200021 | FC | 1 | 2020-01-22 | 161133-3 | FC | 1 | A
331 | DHI | GRT-YR05-P0ZEN-161134 | 161134 | [DCS]_Outline & Detail Drawing for System & Marshalling Cabinet | FA | 2017-04-07 | 2017-07-07 | 2019-02-04 | GRT-DS-IP-DT-190017 | FC | 2 | 2019-02-04 | 161134-2 | FC | 2 | A
332 | DHI | GRT-YR05-P0ZEN-161135 | 161135 | [DCS]_Outline & Detail Drawing for Relay Cabinet | FA | 2017-04-07 | 2017-07-07 | 2017-10-30 | GRT-DS-IP-DT-170409 | FC | 0 | 2017-11-02 | 161135-0 | FC | 0 | A
333 | DHI | GRT-YR05-P0ZEN-161136 | 161136 | [DCS]_Outline & Detail Drawing for Safety Related System Panel | FA | 2017-04-07 | 2017-07-07 | 2017-11-27 | GRT-DS-IP-DT-170454 | FC | 0 | 2018-04-26 | 29-5th DRM | FC | 0 | A
334 | DHI | GRT-YF00-P0ZEN-161201 | 161201 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Symbol & Legend | FA | 2017-04-14 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170166 | FC | 0 | 2017-07-17 |  | FC | 0 | A
335 | DHI | GRT-YF00-P0ZEN-161202 | 161202 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Typical Function | FA | 2017-04-14 | 2017-07-31 | 2018-08-02 | GRT-DS-IP-DT-180175 | FC | 1 | 2018-08-10 | 161202-1 | FC | 1 | A
336 | DHI | GRT-YF00-P1LBA-161203 | 161203 | [HP & LP steam system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161203-1 | FC | 1 | A
337 | DHI | GRT-YF00-P0LBG-161204 | 161204 | [AUX Steam System_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161204-1 | FC | 1 | A
338 | DHI | GRT-YF00-P0LA-161205 | 161205 | [Feedwater system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161205-1 | FC | 1 | A
339 | DHI | GRT-YF00-P0LC-161206 | 161206 | [Condensate system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-09-20 | GRT-DS-IP-DT-180226 | FC | 2 | 2018-09-26 | 161206-2 | FC | 2 | A
340 | DHI | GRT-YF00-P0PA-161207 | 161207 | [Aux. Cooling Water System_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2019-10-03 | GRT-DS-IP-DT-190144 | FC | 3 | 2019-10-03 | 161207-4 | FC | 3 | A
341 | DHI | GRT-YF00-P0PG-161208 | 161208 | [Closed cooling water system_I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2019-10-03 | GRT-DS-IP-DT-190144 | FC | 3 | 2019-10-03 | 161208-4 | FC | 3 | A
342 | DHI | GRT-YF00-P0ZEN-161210 | 161210 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Sampling & Chemical Dosing System | FA | 2017-04-28 | 2017-07-31 | 2017-09-06 | GRT-DS-IP-DT-170283 | FC | 0 | 2017-09-11 | 161210-0 | FC | 0 | B
343 | DHI | GRT-YF00-P0ZEN-161211 | 161211 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Interface with other Control System | FA | 2017-04-28 | 2017-07-31 | 2019-09-10 | GRT-DS-IP-DT-190131 | FC | 1 | 2019-09-10 | 161211-1 | FC | 1 | A
344 | DHI | GRT-YF00-P0ZEN-161212 | 161212 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Miscellaneous System | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161212-1 | FC | 1 | A
345 | DHI | GRT-YF00-P0MAJ-161213 | 161213 | [Condenser Vacuum Pump System _I&C_Logic]_Control Logic Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161213-1 | FC | 1 | A
346 | DHI | GRT-YF00-P0ZEN-161301 | 161301 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Symbol & Legend | FA | 2017-04-14 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170166 | FC | 0 | 2017-07-17 |  | FC | 0 | A
347 | DHI | GRT-YF00-P0ZEN-161302 | 161302 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Typical Function | FA | 2017-04-14 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170166 | FC | 0 | 2017-07-17 |  | FC | 0 | A
348 | DHI | GRT-YF00-P1LBA-161303 | 161303 | [HP & LP steam system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161303-1 | FC | 1 | A
349 | DHI | GRT-YF00-P0LBG-161304 | 161304 | [AUX Steam System_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-14 | 2017-07-31 | 2018-08-30 | GRT-DS-IP-DT-180212 | FC | 1 | 2018-09-06 | 161304-1 | FC | 1 | A
350 | DHI | GRT-YF00-P0LA-161305 | 161305 | [Feedwater system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161305-1 | FC | 1 | A
351 | DHI | GRT-YF00-P0LC-161306 | 161306 | [Condensate system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161306-1 | FC | 1 | A
352 | DHI | GRT-YF00-P0PA-161307 | 161307 | [Aux. Cooling Water System_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161307-1 | FC | 1 | A
353 | DHI | GRT-YF00-P0PG-161308 | 161308 | [Closed cooling water system_I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-21 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161308-1 | FC | 1 | A
354 | DHI | GRT-YF00-P0ZEN-161310 | 161310 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Sampling & Chemical Dosing System | FA | 2017-04-28 | 2017-07-31 | 2017-07-31 | GRT-DS-IP-DT-170218 | FC | 0 | 2017-08-22 |  | FC | 0 | B
355 | DHI | GRT-YF00-P0ZEN-161311 | 161311 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Interface with other Control System | FA | 2017-04-28 | 2017-07-31 | 2019-09-10 | GRT-DS-IP-DT-190131 | FC | 1 | 2019-09-10 | 161311-1 | FC | 1 | A
356 | DHI | GRT-YF00-P0ZEN-161312 | 161312 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Miscellaneous System | FA | 2017-04-28 | 2017-07-31 | 2018-08-16 | GRT-DS-IP-DT-180198 | FC | 1 | 2018-09-06 | 161312-1 | FC | 1 | A
357 | DHI | GRT-YF00-P0MAJ-161313 | 161313 | [Condenser Vacuum Pump System _I&C_Loop]_Control Loop Diagram for BOP | FA | 2017-04-28 | 2017-07-31 | 2018-08-24 | GRT-DS-IP-DT-180203 | FC | 1 | 2018-09-06 | 161313-1 | FC | 1 | A
358 | DHI | GRT-YF00-P0ZEN-161401 | 161401 | [INC_PMC]_Plant Master Control Diagram | FA | 2017-07-14 | 2017-10-12 | 2018-07-26 | GRT-DS-IP-DT-180189 | FC | 1 | 2018-08-02 | 161401-1 | FC | 1 | A
359 | DHI | GRT-YF00-P0ZEN-161402 | 161402 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170368 | FC | 0 | 2017-11-02 | 161402-0 | FC | 0 | A
360 | DHI | GRT-YF00-P0ZEN-161403 | 161403 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Cold Start-up | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170369 | FC | 0 | 2017-11-02 | 161403-0 | FC | 0 | A
361 | DHI | GRT-YF00-P0ZEN-161404 | 161404 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Warm Start-up | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170369 | FC | 0 | 2017-11-02 | 161404-0 | FC | 0 | A
362 | DHI | GRT-YF00-P0ZEN-161405 | 161405 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Hot Start-up | FA | 2017-08-18 | 2017-11-16 | 2017-10-26 | GRT-DS-IP-DT-170369 | FC | 0 | 2017-11-02 | 161405-0 | FC | 0 | A
363 | DHI | GRT-YF00-P0ZEN-161406 | 161406 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Shutdown | FA | 2017-08-18 | 2017-11-16 | 2017-11-27 | GRT-DS-IP-DT-170463 | FC | 0 | 2018-04-26 | 30-5th DRM | FC | 0 | A
364 | DHI | GRT-CV03-P0ZEN-162301 | 162301 | [VMS]_Technical Specification & Datasheet for Vibration Monitoring System | FA | 2017-06-09 | 2017-09-15 | 2019-01-21 | GRT-DS-IP-DT-180269 | FC | 1 | 2019-01-21 | 162301-2 | FC | 1 | A
365 | DHI | GRT-YS05-P0ZEN-162701 | 162701 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Field Instrument | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A
366 | DHI | GRT-YS05-P0ZEN-162702 | 162702 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Control Valve | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A
367 | DHI | GRT-YS05-P0ZEN-162703 | 162703 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for MOV | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A
368 | DHI | GRT-YS05-P0ZEN-162704 | 162704 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Instrument Rack and Junction Box | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A
369 | DHI | GRT-YS05-P0ZEN-162705 | 162705 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Conduit Support | FI | 2017-03-17 | 2017-07-31 | 2017-07-17 | GRT-DS-IP-DT-170152 | FC | 0 | 2017-07-17 |  | FC | 0 | A
370 | DHI | GRT-YS00-P0ZEN-163301 | 163301 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram - Index | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163301-0 | FC | 0 | A
371 | DHI | GRT-YS00-P0ZEN-163302 | 163302 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163302-0 | FC | 0 | A
372 | DHI | GRT-YS00-P0ZEN-163303 | 163303 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163303-0 | FC | 0 | A
373 | DHI | GRT-YS00-P0ZEN-163304 | 163304 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163304-0 | FC | 0 | A
374 | DHI | GRT-YS00-P0ZEN-163305 | 163305 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Modulating Control Actuator | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163305-0 | FC | 0 | A
375 | DHI | GRT-YS00-P0ZEN-163306 | 163306 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Input | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163306-0 | FC | 0 | A
376 | DHI | GRT-YS00-P0ZEN-163307 | 163307 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Output | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163307-0 | FC | 0 | A
377 | DHI | GRT-YS00-P0ZEN-163308 | 163308 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Input | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163308-0 | FC | 0 | A
378 | DHI | GRT-YS00-P0ZEN-163309 | 163309 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Output | FA | 2017-03-03 | 2017-05-31 | 2017-06-05 | GRT-DS-IP-DT-170091 | FC | 0 | 2017-06-05 | 163309-0 | FC | 0 | A
379 | DHI | GRT-YS00-P0ZEN-163310 | 163310 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Electrical System | FA | 2017-07-21 | 2017-09-30 | 2017-09-06 | GRT-DS-IP-DT-170284 | FC | 0 | 2017-09-12 | 163310-0 | FC | 0 | A
380 | DHI | GRT-YL00-P0ZEN-163700 | 163700 | [Field Instruments(DHI)]_Field Instrument List for BOP | FA | 2017-07-19 | 2017-10-31 | 2020-01-21 | GRT-DS-IP-DT-200017 | FC | 2 | 2020-01-21 | 163700-3 | FC | 2 | A
381 | DHI | GRT-CV03-P0ZEN-163701 | 163701 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Process Transmitter - BOP | FA | 2017-07-31 | 2017-10-31 | 2020-01-21 | GRT-DS-IP-DT-200017 | FC | 1 | 2020-01-21 | 163701-3 | FC | 1 | A
382 | DHI | GRT-CV03-P0ZEN-163702 | 163702 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Local Instrument - BOP | FA | 2017-07-31 | 2017-10-31 | 2018-04-20 | GRT-DS-IP-DT-180107 | FC | 1 | 2018-04-27 | 163702-1 | FC | 1 | A
383 | DHI | GRT-CV03-P0ZEN-163703 | 163703 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Flow Element - BOP | FA | 2017-07-31 | 2017-10-31 | 2018-04-02 | GRT-DS-IP-DT-180084 | FC | 1 | 2018-04-06 | 163703-1 | FC | 1 | A
384 | DHI | GRT-CV03-P0ZEN-163704 | 163704 | [Control Valves(DHI)]_Technical Specification & Datasheet for Control Valve - BOP | FA | 2017-07-21 | 2017-10-31 | 2018-03-21 | GRT-DS-IP-DT-180072 | FC | 1 | 2018-03-27 | 163704-1 | FC | 1 | A
385 | DHI | GRT-CV03-P0ZEN-163705 | 163705 | [Instrument Installation materials(DHI)]_Technical Specification for Instrument Installation Materials | FA | 2017-07-19 | 2017-10-31 | 2017-09-14 | GRT-DS-IP-DT-170291 | FC | 0 | 2017-09-18 | 163705-0 | FC | 0 | A
386 | DHI | GRT-CV03-P0ZEN-163706 | 163706 | [Local Boxes(DHI)]_Technical Specification for Junction Box & Racks | FA | 2017-07-25 | 2017-11-05 | 2017-11-29 | GRT-DS-IP-DT-170492 | FC | 1 | 2017-12-18 | 163706-1 | FC | 1 | A
387 | DHI | GRT-YK00-P0ZEN-164301 | 164301 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - General Notes | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164301-2 | FC | 1 | A
388 | DHI | GRT-YK00-P0ZEN-164302 | 164302 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Symbol & Legend | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164302-2 | FC | 1 | A
389 | DHI | GRT-YK00-P0ZEN-164303 | 164303 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Material List | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164303-2 | FC | 1 | A
390 | DHI | GRT-YK00-P0ZEN-164304 | 164304 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164304-2 | FC | 1 | A
391 | DHI | GRT-YK00-P0ZEN-164305 | 164305 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Diff. Press. Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164305-2 | FC | 1 | A
392 | DHI | GRT-YK00-P0ZEN-164306 | 164306 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Flow Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164306-2 | FC | 1 | A
393 | DHI | GRT-YK00-P0ZEN-164307 | 164307 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Level Transmitter / Switch | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164307-2 | FC | 1 | A
394 | DHI | GRT-YK00-P0ZEN-164308 | 164308 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Gauge | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164308-2 | FC | 1 | A
395 | DHI | GRT-YK00-P0ZEN-164309 | 164309 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Control Valve | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164309-2 | FC | 1 | A
396 | DHI | GRT-YK00-P0ZEN-164310 | 164310 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Stanchion & Rack | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164310-2 | FC | 1 | A
397 | DHI | GRT-YD08-P0UMA-164311 | 164311 | [Steam Turbine Building_INC_ILD]_BOP_Instrument Location Drawing | FI | 2017-07-25 | 2017-11-05 | 2018-07-26 | GRT-DS-IP-DT-180184 | FC | 1 | 2018-08-02 | 164311-1 | FC | 1 | B
398 | DHI | GRT-YK00-P0ZEN-164312 | 164312 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Temp.Transmitter/ Guage/ Test Well | FI | 2017-04-21 | 2017-08-31 | 2020-01-18 | GRT-DS-IP-DT-200007 | FC | 1 | 2020-01-18 | 164312-2 | FC | 1 | A
399 | DHI | GRT-XB00-P0MA-200001 | 200001 | [STG]_Foundation - Shape & Anchoring | FI | 2017-02-28 | 2017-07-14 | 2017-06-21 | GRT-DS-IP-DT-170126 | FC | 0 | 2017-06-22 |  | FC | 0 | A
400 | DHI | GRT-XB00-P0MA-200002 | 200002 | [STG]_Foundation - Embedded Elements | FI | 2017-02-28 | 2017-07-14 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A
401 | DHI | GRT-XB00-P0MA-200003 | 200003 | [STG]_Foundation - Static & Dynamic Calculation | FI | 2017-02-28 | 2017-08-08 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A
402 | DHI | GRT-CA03-P0MA-200004 | 200004 | [STG]_Steel structures | FA | 2017-10-25 | 2018-02-24 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-03-01 | 200004-0 | FC | 0 | A
403 | DHI | GRT-XG08-P0MA-200005 | 200005 | [STG]_P&I Diagrams | FA | 2017-03-10 | 2017-07-09 | 2019-10-24 | GRT-DS-IP-DT-190149 | FC | 3 | 2019-10-24 | 200005-3 | FC | 3 | A
404 | DHI | GRT-YD00-P0MA-200006 | 200006 | [STG]_General Arrangement Drawing | FA | 2017-03-10 | 2017-09-25 | 2019-01-15 | GRT-DS-IP-DT-190004 | FC | 1 | 2019-01-15 | 200006-1 | FC | 1 | A
405 | DHI | GRT-XB00-P0MA-200007 | 200007 | [STG]_Foundation load plan | FI | 2017-03-10 | 2017-07-14 | 2017-06-20 | GRT-DS-IP-DT-170122 | FC | 0 | 2017-06-20 |  | FC | 0 | A
406 | DHI | GRT-XB00-P0MA-200008 | 200008 | [STG]_Loads plan - Levels | FI | 2017-06-19 | 2017-11-24 | 2019-01-15 | GRT-DS-IP-DT-190004 | FC | 1 | 2019-01-15 | 200008-1 | FC | 1 | A
407 | DHI | GRT-XB00-P0MA-200009 | 200009 | [STG]_Lay down plan | FI | 2017-05-21 | 2017-09-20 | 2017-09-29 | GRT-DS-IP-DT-170321 | FC | 0 | 2017-10-02 | 200009-0 | FC | 0 | A
408 | DHI | GRT-XV00-P0MA-200010 | 200010 | [STG]_List of pipelines | FI | 2017-05-21 | 2017-08-08 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A
409 | DHI | GRT-XN00-P0MA-200011 | 200011 | [STG]_List of valves | FI | 2017-05-21 | 2017-08-08 | 2017-10-26 | GRT-DS-IP-DT-170375 | FC | 0 | 2017-11-02 | 200011-1 | FC | 0 | A
410 | DHI | GRT-XV00-P0MA-200012 | 200012 | [STG]_List of equipments | FI | 2017-05-21 | 2017-10-25 | 2017-11-01 | GRT-DS-IP-DT-170419 | FC | 0 | 2017-11-02 | 200012-0 | FC | 0 | A
411 | DHI | GRT-XB00-P0MA-200013 | 200013 | [STG]_Allowable loadings and displacements | FI | 2017-03-10 | 2017-10-25 | 2017-10-26 | GRT-DS-IP-DT-170400 | FC | 0 | 2017-11-02 | 200013-0 | FC | 0 | A
412 | DHI | GRT-US02-P0MA-200014 | 200014 | [STG]_Detail drawings - piping, components and BOM | FI | 2018-01-22 | 2018-05-22 | 2019-10-24 | GRT-DS-IP-DT-190149 | FC | 2 | 2019-03-03 | 200014-3 | FC | 1 | A
413 | DHI | GRT-YD00-P0MA-200017 | 200017 | [STG]_Layout - piping routing - | FI | 2017-05-21 | 2017-10-25 | 2017-11-01 | GRT-DS-IP-DT-170419 | FC | 0 | 2017-11-02 | 200017-0 | FC | 0 | A
414 | DHI | GRT-DF04-P0MA-200018 | 200018 | [STG]_Stress analysis of piping | FI | 2017-10-25 | 2018-03-24 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-03-01 | 200018-0 | FC | 0 | A
415 | DHI | GRT-YK09-P0MA-200020 | 200020 | [STG]_Functional description | FI | 2017-05-21 | 2017-08-28 | 2017-09-06 | GRT-DS-IP-DT-170277 | FC | 0 | 2017-09-08 | 200020-0 | FC | 0 | A
416 | DHI | GRT-YD00-P0MA-200022 | 200022 | [STG]_Steam Turbine Auxiliaries outline drawing | FI | 2017-11-03 | 2018-02-02 | 2018-07-19 | GRT-DS-IP-DT-180178 | FC | 1 | 2018-08-02 | 200022-1 | FC | 1 | A
417 | DHI | GRT-YD00-P0MA-200024 | 200024 | [STG]_Generator Specification | FI | 2017-05-14 | 2017-09-13 | 2017-10-26 | GRT-DS-IP-DT-170371 | FC | 0 | 2017-11-02 | 200024-0 | FC | 0 | A
418 | DHI | GRT-YK09-P0MA-200025 | 200025 | [STG]_Excitation system | FI | 2017-11-11 | 2018-03-10 | 2019-12-19 | GRT-DS-IP-DT-190182 | FC | 1 | 2019-12-19 | 200025-1 | FC | 1 | A
419 | DHI | GRT-YK09-P0MA-200026 | 200026 | [STG]_Line and Neutral Cubicles | FI | 2017-11-11 | 2018-03-10 | 2019-03-29 | GRT-DS-IP-DT-190048 | FC | 2 | 2019-03-29 | 200026-3 | FC | 2 | A
420 | DHI | GRT-YK09-P0MA-200027 | 200027 | [STG]_Electrical Protections | FI | 2017-11-11 | 2018-03-10 | 2019-03-29 | GRT-DS-IP-DT-190050 | FC | 2 | 2019-03-29 | 200027-3 | FC | 2 | A
421 | DHI | GRT-YK09-P0MA-200028 | 200028 | [STG]_Measuring and Synchronization | FI | 2017-11-11 | 2018-03-10 | 2019-10-23 | GRT-DS-IP-DT-190150 | FC | 1 | 2019-10-23 | 200028-1 | FC | 1 | A
422 | DHI | GRT-YK09-P0MA-200029 | 200029 | [STG]_Frequency converter for turning gear | FI | 2017-11-11 | 2018-03-10 | 2019-10-23 | GRT-DS-IP-DT-190150 | FC | 2 | 2019-10-23 | 200029-2 | FC | 2 | A
423 | DHI | GRT-YK09-P0MA-200030 | 200030 | [STG]_DC motor starter | FI | 2017-11-11 | 2018-03-10 | 2018-04-17 | GRT-DS-IP-DT-180104 | FC | 1 | 2018-04-27 | 200030-1 | FC | 1 | A
424 | DHI | GRT-YK09-P0MA-200032 | 200032 | [STG]_Cabling system | FI | 2017-11-11 | 2018-03-10 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-02-20 | 200032-0 | FC | 0 | A
425 | DHI | GRT-YK09-P0MA-200033 | 200033 | [STG]_Electrical system description | FI | 2017-05-14 | 2017-08-13 | 2017-11-01 | GRT-DS-IP-DT-170414 | FC | 0 | 2017-11-02 | 200033-0 | FC | 0 | B
426 | DHI | GRT-YK00-P0MA-200034 | 200034 | [STG]_Hook ups | FA | 2017-05-14 | 2017-08-14 | 2019-03-05 | GRT-DS-IP-DT-190037 | FC | 1 | 2019-03-05 | 200034-2 | FC | 1 | A
427 | DHI | GRT-YK09-P0MA-200035 | 200035 | [STG]_Instrumentation data sheets | FI | 2017-11-22 | 2018-03-24 | 2018-11-16 | GRT-DS-IP-DT-180242 | FC | 1 | 2018-11-16 | 200035-2 | FC | 1 | A
428 | DHI | GRT-YF00-P0MA-200036 | 200036 | [STG]_Consumer schemes | FI | 2017-05-14 | 2017-09-13 | 2017-09-29 | GRT-DS-IP-DT-170327 | FC | 0 | 2017-10-02 | 200036-0 | FC | 0 | A
429 | DHI | GRT-YL00-P0MA-200037 | 200037 | [STG]_Measurement list | FI | 2017-05-14 | 2017-09-13 | 2017-09-29 | GRT-DS-IP-DT-170327 | FC | 0 | 2017-10-02 | 200037-0 | FC | 0 | A
430 | DHI | GRT-YL19-P0MA-200038 | 200038 | [STG]_Electrical load list | FI | 2017-03-28 | 2017-07-28 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A
431 | DHI | GRT-YU03-P0MA-200039 | 200039 | [STG]_Control system architecture | FA | 2017-03-28 | 2017-07-21 | 2017-11-27 | GRT-DS-IP-DT-170467 | FC | 0 | 2018-04-26 | 31-5th DRM | FC | 0 | A
432 | DHI | GRT-YK00-P0MA-200040 | 200040 | [STG]_I&C Lay-outs | FI | 2017-05-22 | 2017-09-21 | 2019-01-15 | GRT-DS-IP-DT-190004 | FC | 1 | 2019-01-15 | 200040-1 | FC | 1 | A
433 | DHI | GRT-YU03-P0MA-200041 | 200041 | [STG]_Control system function philosophy | FI | 2017-05-22 | 2017-09-21 | 2017-09-29 | GRT-DS-IP-DT-170333 | FC | 0 | 2017-10-02 | 200041-0 | FC | 0 | B
434 | DHI | GRT-YU03-P0MA-200043 | 200043 | [STG]_Control system. Hardware specification | FI | 2017-07-22 | 2017-11-21 | 2019-02-11 | GRT-DS-IP-DT-190022 | FC | 2 | 2019-02-11 | 200043-2 | FC | 2 | A
435 | DHI | GRT-YF00-P0MA-200044 | 200044 | [STG]_Logic diagrams for control of functional groups | FA | 2017-09-16 | 2017-12-22 | 2017-10-26 | GRT-DS-IP-DT-170406 | FC | 0 | 2017-11-02 | 200044-0 | FC | 0 | B
436 | DHI | GRT-YL00-P0MA-200045 | 200045 | [STG]_List of signals | FI | 2017-03-22 | 2017-07-22 | 2017-08-15 | GRT-DS-IP-DT-170226 | FC | 0 | 2017-08-25 |  | FC | 0 | A
437 | DHI | GRT-YL21-P0MA-200046 | 200046 | [STG]_Trips & Alarms settings | FI | 2017-09-16 | 2018-01-21 | 2017-10-26 | GRT-DS-IP-DT-170406 | FC | 0 | 2017-11-02 | 200046-0 | FC | 0 | B
438 | DHI | GRT-YK08-P0MA-200047 | 200047 | [STG]_HMI design | FI | 2017-09-16 | 2018-01-21 | 2019-01-16 | GRT-DS-IP-DT-190008 | FC | 0 | 2019-01-16 | 200047-1 | FC | 0 | A
439 | DHI | GRT-YL00-P0MA-200048 | 200048 | [STG]_I/O list | FI | 2017-11-22 | 2018-03-10 | 2018-03-19 | GRT-DS-IP-DT-180070 | FC | 0 | 2018-03-22 | 200048-1 | FC | 0 | A
440 | DHI | GRT-YU03-P0MA-200049 | 200049 | [STG]_Wiring diagrams, Loop diagrams | FI | 2017-11-22 | 2018-03-10 | 2019-12-19 | GRT-DS-IP-DT-190182 | FC | 1 | 2019-12-19 | 200049-1 | FC | 1 | A
441 | DHI | GRT-YL15-P0MA-200050 | 200050 | [STG]_Cable list | FI | 2017-11-20 | 2018-02-19 | 2018-02-08 | GRT-DS-IP-DT-180035 | FC | 0 | 2018-02-20 | 200050-0 | FC | 0 | A
442 | DHI | GRT-YK09-P0MA-200051 | 200051 | [STG]_Operating instructions for the steam turbine and accessories | FI | 2018-02-28 | 2018-05-22 | 2018-04-25 | GRT-DS-IP-DT-180112 | FC | 0 | 2018-05-04 | 200051-2 | FC | 0 | B
443 | DHI | GRT-YK09-P0MA-200052 | 200052 | [STG]_Maintenance instructions for the steam turbine and accessories | FI | 2018-02-28 | 2018-05-22 | 2018-08-10 | GRT-DS-IP-DT-180201 | FC | 2 | 2018-08-30 | 200052-4 | FC | 2 | A
444 | DHI | GRT-YK09-P0MA-200053 | 200053 | [STG]_Summary Operation and Maintenance instructions | FI | 2018-02-28 | 2018-05-22 | 2018-05-02 | GRT-DS-IP-DT-180108 | FC | 0 | 2018-05-04 | 200053-0 | FC | 0 | B
445 | DHI | GRT-YK10-P0MA-200056 | 200056 | [STG]_Initial specification for TG installation | FI | 2018-02-28 | 2018-05-22 | 2018-04-17 | GRT-DS-IP-DT-180105 | FC | 0 | 2018-04-27 | 200056-0 | FC | 0 | B
446 | DHI | GRT-YK10-P0MA-200057 | 200057 | [STG]_Instructions for steam turbine assembly | FI | 2018-02-28 | 2018-05-22 | 2018-04-17 | GRT-DS-IP-DT-180104 | FC | 0 | 2018-04-27 | 200057-0 | FC | 0 | B
447 | DHI | GRT-YK10-P0MA-200058 | 200058 | [STG]_Main assembly manual | FI | 2018-02-28 | 2018-05-22 | 2018-05-02 | GRT-DS-IP-DT-180108 | FC | 0 | 2018-05-04 | 200058-0 | FC | 0 | B
448 | DHI | GRT-YK09-P0MA-200059 | 200059 | [STG]_First commissioning and start-up TG | FI | 2018-02-28 | 2018-05-22 | 2018-08-10 | GRT-DS-IP-DT-180201 | FC | 2 | 2018-08-30 | 200059-4 | FC | 2 | A
449 | DHI | GRT-YK10-P0MA-200061 | 200061 | [STG]_Assembly manual for auxiliary equipment | FI | 2018-05-18 | 2018-07-17 | 2018-07-12 | GRT-DS-IP-DT-180167 | FC | 0 | 2018-07-27 | 200061-0 | FC | 0 | A
450 | DHI | GRT-YK09-P0MA-200062 | 200062 | [STG]_Commissioning manual for auxiliary equipment | FI | 2018-06-20 | 2018-08-20 | 2018-08-24 | GRT-DS-IP-DT-180208 | FC | 0 | 2018-08-30 | 200062-1 | FC | 0 | A
451 | DHI | GRT-YK09-P0MA-200063 | 200063 | [STG]_ Elec. Heater panel | FI | 2018-12-10 | 2019-03-11 | 2019-01-21 | GRT-DS-IP-DT-190009 | FC | 0 | 2019-01-21 | 200063-0 | FC | 0 | A
452 | DHI | GRT-CQ02-P1H-300001 | 300001 | [HRSG]_INSTALLATION, OPERATION AND MAINTENANCE INSTRUCTION MANUAL | FA | 2018-02-28 | 2018-05-28 | 2018-08-10 | GRT-DS-IP-DT-180200 | FC | 0 | 2018-08-24 | 300001-0 | FC | 0 | A
453 | DHI | GRT-DF04-P1H-300002 | 300002 | [HRSG]_STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | FA | 2017-04-20 | 2017-07-20 | 2017-07-17 | GRT-DS-IP-DT-170164 | FC | 0 | 2017-09-18 | 300002-1 | FC | 0 | B
454 | DHI | GRT-DM02-P1H-300005 | 300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2018-01-09 | GRT-DS-IP-DT-180003 | FC | 1 | 2018-01-24 | 300005-1 | FC | 1 | B
455 | DHI | GRT-UE00-P1H-300006 | 300006 | [HRSG]_GENERAL ARRANGEMENT | FA | 2017-03-30 | 2017-06-30 | 2019-09-24 | GRT-DS-IP-DT-190139 | FC | 2 | 2019-09-24 | 300006-2 | FC | 2 | A
456 | DHI | GRT-UE00-P1H-300007 | 300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | FI | 2017-04-20 | 2017-07-20 | 2019-04-11 | GRT-DS-IP-DT-190064 | FC | 3 | 2019-04-11 | 300007-3 | FC | 3 | A
457 | DHI | GRT-UE00-P1H-300008 | 300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | FI | 2017-04-20 | 2017-07-20 | 2019-08-08 | GRT-DS-IP-DT-190103 | FC | 2 | 2019-08-08 | 300008-3 | FC | 2 | A
458 | DHI | GRT-UE00-P1H-300009 | 300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | FI | 2017-05-20 | 2017-08-20 | 2017-11-01 | GRT-DS-IP-DT-170420 | FC | 0 | 2018-04-26 | 32-5th DRM | FC | 0 | A
459 | DHI | GRT-VN03-P1H-300010 | 300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2018-01-09 | GRT-DS-IP-DT-180003 | FC | 1 | 2018-01-24 | 300010-1 | FC | 1 | B
460 | DHI | GRT-VN03-P1H-300011 | 300011 | [HRSG]_TYPICAL HANDRAIL DETAIL FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2017-07-05 | GRT-DS-IP-DT-170143 | FC | 0 | 2017-07-19 |  | FC | 0 | A
461 | DHI | GRT-VN03-P1H-300012 | 300012 | [HRSG]_TYPICAL LADDER DETAIL FOR STEEL STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2017-08-24 | GRT-DS-IP-DT-170254 | FC | 0 | 2017-08-25 |  | FC | 0 | A
462 | DHI | GRT-VN03-P1H-300013 | 300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | FI | 2017-05-20 | 2017-08-20 | 2018-01-09 | GRT-DS-IP-DT-180003 | FC | 1 | 2018-01-24 | 300013-1 | FC | 1 | B
463 | DHI | GRT-XB02-P1H-300014 | 300014 | [HRSG]_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | FA | 2017-03-30 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | B
464 | DHI | GRT-XB02-P1H-300015 | 300015 | [HRSG]_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FA | 2017-03-30 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | B
465 | DHI | GRT-XB02-P1H-300016 | 300016 | [HRSG]_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | FA | 2017-03-30 | 2017-06-30 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | B
466 | DHI | GRT-XB02-P1H-300018 | 300018 | [HRSG]_FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | FA | 2017-03-23 | 2017-07-14 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-01 |  | FC | 0 | A
467 | DHI | GRT-XG02-P1H-300020 | 300020 | [HRSG]_P&I DIAGRAM | FA | 2017-03-23 | 2017-07-14 | 2019-01-08 | GRT-DS-IP-DT-190002 | FC | 2 | 2019-01-08 | 300020-2 | FC | 2 | A
468 | DHI | GRT-XH01-P1H-300021 | 300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | FI | 2017-09-20 | 2017-12-20 | 2018-02-14 | GRT-DS-IP-DT-180044 | FC | 1 | 2018-03-01 | 300021-1 | FC | 1 | A
469 | DHI | GRT-XH01-P1H-300023 | 300023 | [HRSG]_PIPE SUPPORT DRAWINGS | FI | 2017-08-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-04-26 | 92-5th DRM | FC | 0 | A
470 | DHI | GRT-XJ00-P1H-300024 | 300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | FI | 2017-09-20 | 2017-12-20 | 2018-05-24 | GRT-DS-IP-DT-180137 | FC | 1 | 2018-05-25 | 300024-1 | FC | 1 | A
471 | DHI | GRT-XL00-P1H-300028 | 300028 | [HRSG]_LINE LIST | FA | 2017-05-20 | 2017-08-20 | 2018-09-12 | GRT-DS-IP-DT-180216 | FC | 1 | 2018-09-20 | 300028-1 | FC | 1 | A
472 | DHI | GRT-XN00-P1H-300029 | 300029 | [HRSG]_VALVE LIST | FI | 2017-04-20 | 2017-07-20 | 2018-07-05 | GRT-DS-IP-DT-180160 | FC | 1 | 2018-07-12 | 30029-1 | FC | 1 | A
473 | DHI | GRT-XS00-P1H-300031 | 300031 | [HRSG]_SYSTEM DESCRIPTION | FA | 2017-04-20 | 2017-05-20 | 2017-07-05 | GRT-DS-IP-DT-170143 | FC | 0 | 2017-07-19 |  | FC | 0 | B
474 | DHI | GRT-XS00-P1H-300032 | 300032 | [HRSG]_BLOWDOWN SYSTEM SUMMARY | FA | 2017-03-23 | 2017-07-14 | 2017-07-17 | GRT-DS-IP-DT-170164 | FC | 0 | 2017-09-18 | 300032-1 | FC | 0 | A
475 | DHI | GRT-YB03-P1H-300033 | 300033 | [HRSG]_CABLE CONNECTION DIAGRAM | FA | 2017-08-20 | 2017-11-21 | 2019-05-21 | GRT-DS-IP-DT-190076 | FC | 1 | 2019-05-21 | 300033-1 | FC | 1 | A
476 | DHI | GRT-YD00-P1H-300034 | 300034 | [HRSG]_PRESSURE PART ARRANGEMENT | FI | 2017-03-20 | 2017-07-20 | 2017-11-01 | GRT-DS-IP-DT-170420 | FC | 0 | 2018-04-26 | 34-5th DRM | FC | 0 | A
477 | DHI | GRT-YD00-P1H-300035 | 300035 | [HRSG]_SPEC. & DRAWING FOR STEAM DRUM | FI | 2017-08-20 | 2017-10-20 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300035-0 | FC | 0 | A
478 | DHI | GRT-YD00-P1H-300036 | 300036 | [HRSG]_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | FI | 2017-06-20 | 2017-09-20 | 2017-08-24 | GRT-DS-IP-DT-170256 | FC | 0 | 2017-08-25 |  | FC | 0 | A
479 | DHI | GRT-YD00-P1H-300037 | 300037 | [HRSG]_POWER DISTRIBUTION PANEL DRAWINGS | FA | 2017-09-20 | 2017-12-20 | 2019-04-05 | GRT-DS-IP-DT-190061 | FC | 1 | 2019-04-05 | 3000037-1 | FC | 1 | A
480 | DHI | GRT-YD00-P1H-300039 | 300039 | [HRSG]_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FA | 2017-07-20 | 2017-10-20 | 2017-10-26 | GRT-DS-IP-DT-170387 | FC | 0 | 2017-11-02 | 300039-0 | FC | 0 | A
481 | DHI | GRT-YD00-P1H-300040 | 300040 | [HRSG]_SPEC. & DRAWING FOR STACK DAMPER | FA | 2017-07-20 | 2017-10-20 | 2019-04-29 | GRT-DS-IP-DT-190065 | FC | 1 | 2019-04-29 | 300040-1 | FC | 1 | A
482 | DHI | GRT-YD00-P1H-300041 | 300041 | [HRSG]_SPEC. & DRAWING FOR SILENCER | FA | 2017-07-20 | 2017-10-20 | 2017-11-01 | GRT-DS-IP-DT-170420 | FC | 0 | 2018-04-26 | 36-5th DRM | FC | 0 | A
483 | DHI | GRT-YD04-P1H-300042 | 300042 | [HRSG]_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | FI | 2017-07-20 | 2017-10-20 | 2019-01-15 | GRT-DS-IP-DT-190005 | FC | 2 | 2019-01-15 | 300042-2 | FC | 2 | A
484 | DHI | GRT-YF00-P1H-300044 | 300044 | [HRSG]_SEQUENCES & CONTROLS | FA | 2017-06-20 | 2017-09-20 | 2019-01-21 | GRT-DS-IP-DT-180276 | FC | 2 | 2019-01-21 | 300044-2 | FC | 2 | A
485 | DHI | GRT-YK01-P1H-300048 | 300048 | [HRSG]_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-11-14 | GRT-DS-IP-DT-180263 | FC | 2 | 2018-11-14 | 300048-2 | FC | 2 | A
486 | DHI | GRT-YK09-P1H-300049 | 300049 | [HRSG]_SPECIALTY DRAWING FOR EXTERNAL PIPING | FI | 2017-09-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-06-29 | 300049-0 | FC | 0 | A
487 | DHI | GRT-YK10-P1H-300050 | 300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | FI | 2017-09-20 | 2017-12-20 | 2018-05-24 | GRT-DS-IP-DT-180137 | FC | 1 | 2018-05-25 | 300050-1 | FC | 1 | A
488 | DHI | GRT-YL00-P1H-300051 | 300051 | [HRSG]_INSTRUMENT LIST | FI | 2017-03-20 | 2017-07-20 | 2020-06-30 | GRT-DS-IP-DT-200056 | FC | 2
489 | DHI | GRT-YL16-P1H-300052 | 300052 | [HRSG]_CABLE SCHEDULE | FA | 2017-08-20 | 2017-11-20 | 2019-08-08 | GRT-DS-IP-DT-190104 | FC | 2 | 2019-08-08 | 300052-2 | FC | 2 | A
490 | DHI | GRT-YR01-P1H-300054 | 300054 | [HRSG]_CHEMICAL CLEANING PROCEDURE | FI | 2017-09-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-04-26 | 98-5th DRM | FC | 0 | A
491 | DHI | GRT-YR01-P1H-300055 | 300055 | [HRSG]_CONSERVATION PROCEDURE | FI | 2017-09-20 | 2017-12-20 | 2017-12-22 | GRT-DS-IP-DT-170530 | FC | 0 | 2018-04-26 | 99-5th DRM | FC | 0 | A
492 | DHI | GRT-YT01-P1H-300056 | 300056 | [HRSG]_DATA & BOM OF INSULATION FOR DRUM AND BLOWDOWN TANK | FI | 2017-06-20 | 2017-09-20 | 2017-09-14 | GRT-DS-IP-DT-170279 | FC | 0 | 2017-09-18 | 300056-0 | FC | 0 | A
493 | DHI | GRT-YT01-P1H-300057 | 300057 | [HRSG]_DATA & BOM OF INSULATION FOR INTERNAL PIPING | FI | 2017-08-20 | 2017-11-20 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300057-0 | FC | 0 | A
494 | DHI | GRT-YT01-P1H-300058 | 300058 | [HRSG]_PERFORMANCE AND OPERATIONAL DATA | FA | 2017-03-23 | 2017-06-20 | 2017-07-24 | GRT-DS-IP-DT-170185 | FC | 0 | 2017-08-25 |  | FC | 0 | A
495 | DHI | GRT-YT01-P1H-300059 | 300059 | [HRSG]_MOV DATASHEET & DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-04-27 | GRT-DS-IP-DT-180117 | FC | 1 | 2018-05-04 | 300059-1 | FC | 1 | B
496 | DHI | GRT-YT01-P1H-300060 | 300060 | [HRSG]_CV DATASHEET & DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-05-11 | GRT-DS-IP-DT-180124 | FC | 1 | 2018-05-16 | 300060-1 | FC | 1 | A
497 | DHI | GRT-YT01-P1H-300061 | 300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | FA | 2017-07-20 | 2017-10-20 | 2018-04-27 | GRT-DS-IP-DT-180117 | FC | 1 | 2018-05-04 | 300061-1 | FC | 1 | A
498 | DHI | GRT-YT01-P1H-300062 | 300062 | [HRSG]_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | FI | 2017-10-20 | 2017-12-20 | 2018-10-26 | GRT-DS-IP-DT-180239 | FC | 2 | 2018-10-26 | 300062-2 | FC | 2 | A
499 | DHI | GRT-YT01-P1H-300063 | 300063 | [HRSG]_CEMS DATASHEET & DRAWINGS | FA | 2017-09-20 | 2017-11-20 | 2020-06-30 | GRT-DS-IP-DT-200056 | FC | 3
500 | DHI | GRT-YT02-P1H-300065 | 300065 | [HRSG]_REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | FA | 2017-09-20 | 2017-11-20 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300065-0 | FC | 0 | A
501 | DHI | GRT-YU02-P1H-300066 | 300066 | [HRSG]_ELECTRICAL SINGLE LINE DIAGRAMS | FI | 2017-05-20 | 2017-08-20 | 2018-04-25 | GRT-DS-IP-DT-180113 | FC | 1 | 2018-05-04 | 300066-1 | FC | 1 | A
502 | DHI | GRT-DE00-P1H-300067 | 300067 | [HRSG]_PIPING MATERIAL CLASSIFICATION | FA | 2017-06-20 | 2017-09-20 | 2017-09-27 | GRT-DS-IP-DT-170308 | FC | 0 | 2017-10-29 | 300067-0 | FC | 0 | B
503 | DHI | GRT-YT01-P1H-300068 | 300068 | [HRSG]_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | FA | 2017-08-29 | 2017-09-12 | 2020-06-30 | GRT-DS-IP-DT-200057 | FC | 2
504 | DHI | GRT-YT01-P1H-300069 | 300069 | [HRSG]_ SPEC. & DRAWING FOR PREHEATER RECIRCULATION PUMP | FA | 2017-08-29 | 2017-11-29 | 2017-11-27 | GRT-DS-IP-DT-170486 | FC | 0 | 2017-12-18 | 300069-0 | FC | 0 | A
505 | DHI | GRT-YD00-P1H-300070 | 300070 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR SMALL BORE PIPING | FI | 2018-06-29 | 2018-07-27 | 2019-01-28 | GRT-DS-IP-DT-190012 | FC | 1 | 2019-01-28 | 300070-2 | FC | 1 | A
506 | DHI | GRT-YD00-P0PGB-400040 | 400040 | Outline Drawing for CCW Heat Exchanger | FA | 2017-03-08 | 2017-08-05 | 2018-04-02 | GRT-DS-IP-DT-180085 | FC | 3 | 2018-04-06 | 400040-3 | FC | 3 | A
507 | DHI | GRT-YT10-P0PGB-400050 | 400050 | Thermal Calculation for CCW Heat Exchanger | FA | 2017-10-16 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170545 | FC | 0 | 2018-04-26 | 134-5th DRM | FC | 0 | A
508 | DHI | GRT-YT10-P0PGB-400060 | 400060 | Strength Calculation for CCW Heat Exchanger | FA | 2017-10-16 | 2017-12-22 | 2017-12-22 | GRT-DS-IP-DT-170539 | FC | 0 | 2018-04-26 | 120-5th DRM | FC | 0 | A
509 | DHI | GRT-CQ02-P0PGB-400070 | 400070 | Operation and Maintenance Manual for CCW Heat Exchanger | FI | 2018-04-20 | 2018-06-30 | 2018-05-16 | GRT-DS-IP-DT-180129 | FC | 0 | 2018-05-16 | 400070-2 | FC | 0 | A
510 | DHI | GRT-YK08-P0MAG-410001 | 410001 | Condenser_General Layout | FA | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 102-5th DRM | FC | 1 | A
511 | DHI | GRT-YK08-P0MAG-410002 | 410002 | Condenser_General Arrangement | FA | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 65-5th DRM | FC | 1 | A
512 | DHI | GRT-XL00-P0MAG-410003 | 410003 | Condenser_Connection List | FI | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 103-5th DRM | FC | 1 | A
513 | DHI | GRT-XL00-P0MAG-410004 | 410004 | Condenser_Connection Detail | FI | 2017-02-10 | 2017-05-10 | 2017-12-15 | GRT-DS-IP-DT-170506 | FC | 1 | 2018-04-26 | 104-5th DRM | FC | 1 | A
514 | DHI | GRT-VL00-P0MAG-410005 | 410005 | Condenser_Foundation Assembly | FA | 2017-02-10 | 2017-05-10 | 2017-09-20 | GRT-DS-IP-DT-170298 | FC | 1 | 2017-09-26 | 410005-0 | FC | 1 | A
515 | DHI | GRT-VL00-P0MAG-410006 | 410006 | Condenser_Foundation Detail | FA | 2017-02-10 | 2017-05-10 | 2017-05-31 | GRT-DS-IP-DT-170061 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A
516 | DHI | GRT-YT01-P0MAG-410007 | 410007 | Condenser_Data Sheet | FA | 2017-02-10 | 2017-05-10 | 2017-09-20 | GRT-DS-IP-DT-170298 | FC | 0 | 2017-09-26 | 410007-0 | FC | 0 | A
517 | DHI | GRT-YT01-P0MAG-410008 | 410008 | Condenser_Nozzle Force and Moment | FI | 2017-02-10 | 2017-05-10 | 2017-05-31 | GRT-DS-IP-DT-170061 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A
518 | DHI | GRT-YT01-P0MAG-410009 | 410009 | Condenser_Performance Curves | FI | 2017-02-10 | 2017-05-10 | 2017-05-31 | GRT-DS-IP-DT-170061 | FC | 0 | 2017-05-31 | APPROVED | FC | 0 | A
519 | DHI | GRT-YL00-P0MAG-410010 | 410010 | Condenser_Instrument list and Datasheet for Condenser | FA | 2017-07-30 | 2017-08-30 | 2018-01-19 | GRT-DS-IP-DT-180015 | FC | 1 | 2018-04-26 | 124-5th DRM | FC | 1 | A
520 | DHI | GRT-CQ02-P0MAG-410011 | 410011 | Condenser_Instruction Manuals for Erection, Installation, Operation and Maintenance | FI | 2017-09-30 | 2017-11-30 | 2020-04-06 | GRT-DS-IP-DT-200035 | DCR | 0DCR2 | 2020-04-09 | 410011-3 | DCR | 0DCR2 | C
521 | DHI | GRT-YK08-P0MAG-410012 | 410012 | Transition Piece Assembly between LP TBN and Condenser | FA | 2017-10-13 | 2017-12-30 | 2020-04-06 | GRT-DS-IP-DT-200035 | DCR | 1DCR2 | 2020-03-19 | 410012-2 | DCR | 1DCR1 | C
522 | DHI | GRT-YK08-P0LAA-420001 | 420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | FA | 2017-04-28 | 2017-06-29 | 2018-02-08 | GRT-DS-IP-DT-180037 | FC | 2 | 2018-04-26 | 125-5th DRM | FC | 2 | A
523 | DHI | GRT-CV03-P0LAA-420002 | 420002 | Datasheet for Deaerator & Feedwater Storage Tank | FA | 2017-04-28 | 2017-06-29 | 2018-02-08 | GRT-DS-IP-DT-180037 | FC | 1 | 2018-04-26 | 126-5th DRM | FC | 1 | A
524 | DHI | GRT-CQ02-P0LAA-420003 | 420003 | OPERATING AND MAINTENANCE MANUAL FOR DEAERATOR & FEEDWATER STORAGE TANK | FI | 2018-04-20 | 2018-06-30 | 2018-07-05 | GRT-DS-IP-DT-180164 | FC | 0 | 2018-07-12 | 420003-2 | FC | 0 | A
525 | DHI | GRT-YD00-P0LCM-430010 | 430010 | Outline Drawing for Atmospheric Flash Tank | FA | 2017-03-08 | 2017-08-05 | 2017-12-18 | GRT-DS-IP-DT-170524 | FC | 1 | 2018-04-26 | 106-5th DRM | FC | 1 | A
526 | DHI | GRT-YD00-P0PGB-430020 | 430020 | Outline Drawing for CCW Chemical Additive Tank | FA | 2017-03-08 | 2017-08-05 | 2017-12-18 | GRT-DS-IP-DT-170523 | FC | 1 | 2018-04-26 | 107-5th DRM | FC | 1 | A
527 | DHI | GRT-YD00-P0PGB-430030 | 430030 | Outline Drawing for CCW Expansion Head Tank | FA | 2017-03-08 | 2017-08-05 | 2017-10-26 | GRT-DS-IP-DT-170392 | FC | 0 | 2017-11-02 | 430030-0 | FC | 0 | B
528 | DHI | GRT-YT10-P0LCM-430110 | 430110 | Strength Calculation for Atmospheric Flash Tank | FA | 2017-10-20 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170542 | FC | 0 | 2018-04-26 | 131-5th DRM | FC | 0 | A
529 | DHI | GRT-YT10-P0PGB-430120 | 430120 | Strength Calculation for CCW Chemical Additive Tank | FA | 2017-10-20 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170542 | FC | 0 | 2018-04-26 | 132-5th DRM | FC | 0 | A
530 | DHI | GRT-YT10-P0PGB-430130 | 430130 | Strength Calculation for CCW Expansion Head Tank | FA | 2017-10-20 | 2017-12-22 | 2017-12-29 | GRT-DS-IP-DT-170542 | FC | 0 | 2018-04-26 | 133-5th DRM | FC | 0 | A
531 | DHI | GRT-XG02-P0PAH-440001 | 440001 | Condenser Tube Cleaning System_P & I Diagram | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440001-0 | FC | 0 | A
532 | DHI | GRT-YK08-P0PAH-440002 | 440002 | Condenser Tube Cleaning System_Outline Drawing | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440002-0 | FC | 0 | A
533 | DHI | GRT-YK08-P0PAH-440003 | 440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-04-01 | 2017-10-31 | 2020-01-22 | GRT-DS-IP-DT-200018 | FC | 1 | 2020-01-22 | 440003-3 | FC | 1 | A
534 | DHI | GRT-YF00-P0PAH-440004 | 440004 | Control Logic for CTCS & Debris Filter | FI | 2017-06-01 | 2017-10-31 | 2017-11-13 | GRT-DS-IP-DT-170449 | FC | 0 | 2017-11-13 | 440004-0 | FC | 0 | A
535 | DHI | GRT-YV02-P0PAH-440005 | 440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | FA | 2017-06-01 | 2017-10-31 | 2020-01-22 | GRT-DS-IP-DT-200018 | FC | 2 | 2020-01-22 | 440005-3 | FC | 2 | A
536 | DHI | GRT-YB03-P0PAH-440006 | 440006 | Configuration Diagram of Package System for CTCS & Debris Filter | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180009 | FC | 1 | 2018-01-23 | 440006-1 | FC | 1 | A
537 | DHI | GRT-YK08-P0PAH-440007 | 440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180009 | FC | 1 | 2018-01-23 | 440007-1 | FC | 1 | A
538 | DHI | GRT-YT01-P0PAH-440008 | 440008 | Condenser Tube Cleaning System_Technical Data Sheet | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440008-0 | FC | 0 | B
539 | DHI | GRT-CQ02-P0PAH-440009 | 440009 | Condenser Tube Cleaning system_Operation & Maintenance Manual | FI | 2018-05-04 | 2018-06-29 | 2018-09-20 | GRT-DS-IP-DT-180219 | FC | 0 | 2018-09-26 | 44009-1 | FC | 0 | A
540 | DHI | GRT-XG02-P0PAH-440051 | 440051 | CCW HEX Tube Cleaning System_P & I Diagram | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 67-5th DRM | FC | 0 | A
541 | DHI | GRT-YK08-P0PAH-440052 | 440052 | CCW HEX Tube Cleaning System_Outline Drawing | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 68-5th DRM | FC | 0 | A
542 | DHI | GRT-YK08-P0PAH-440053 | 440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 69-5th DRM | FC | 0 | A
543 | DHI | GRT-YF00-P0PAH-440054 | 440054 | CCW HEX Tube Cleaning System_Control Logic | FI | 2017-06-01 | 2017-10-31 | 2017-11-13 | GRT-DS-IP-DT-170451 | FC | 0 | 2017-11-13 | 440054-0 | FC | 0 | A
544 | DHI | GRT-YV02-P0PAH-440055 | 440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | FA | 2017-06-01 | 2017-10-31 | 2020-01-22 | GRT-DS-IP-DT-200018 | FC | 2 | 2020-01-22 | 440055-3 | FC | 2 | A
545 | DHI | GRT-YB03-P0PAH-440056 | 440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180010 | FC | 1 | 2018-01-23 | 440056-1 | FC | 1 | A
546 | DHI | GRT-YK08-P0PAH-440057 | 440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | FA | 2017-06-01 | 2017-10-31 | 2018-01-17 | GRT-DS-IP-DT-180010 | FC | 1 | 2018-01-23 | 440057-1 | FC | 1 | A
547 | DHI | GRT-YT01-P0PAH-440058 | 440058 | CCW HEX Tube Cleaning System_Technical Data Sheet | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440058-0 | FC | 0 | B
548 | DHI | GRT-CQ02-P0PAH-440059 | 440059 | CCW HEX Tube Cleaning system_Operation & Maintenance Manual | FI | 2018-06-30 | 2018-07-31 | 2019-01-24 | GRT-DS-IP-DT-190013 | FC | 0 | 2019-01-24 | 440059-1 | FC | 0 | A
549 | DHI | GRT-XG02-P0PBB-440101 | 440101 | Debris Filter_P & I Diagram | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440101-0 | FC | 0 | A
550 | DHI | GRT-YK08-P0PBB-440102 | 440102 | Debris Filter_Outline Drawing | FA | 2017-04-01 | 2017-10-31 | 2017-12-15 | GRT-DS-IP-DT-170508 | FC | 0 | 2018-04-26 | 70-5th DRM | FC | 0 | A
551 | DHI | GRT-YT01-P0PBB-440103 | 440103 | Debris Filter_Technical Data Sheet | FA | 2017-04-01 | 2017-10-31 | 2017-10-13 | GRT-DS-IP-DT-170361 | FC | 0 | 2017-10-13 | 440103-0 | FC | 0 | B
552 | DHI | GRT-CQ02-P0PAH-440104 | 440104 | Debris Filter_Operation & Maintenance Manual | FI | 2018-05-04 | 2018-06-29 | 2018-09-20 | GRT-DS-IP-DT-180219 | FC | 0 | 2018-09-26 | 44104-1 | FC | 0 | A
553 | DHI | GRT-YK08-P0MAJ-460100 | 460100 | General Arrangement Drawing For Condenser Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-12-22 | GRT-DS-IP-DT-170535 | FC | 2 | 2018-04-26 | 109-5th DRM | FC | 2 | A
554 | DHI | GRT-XG02-P0MAJ-460101 | 460101 | P & ID For Condenser Vacuum Pump | FA | 2017-06-16 | 2017-09-08 | 2018-01-17 | GRT-DS-IP-DT-180011 | FC | 1 | 2018-04-26 | 128-5th DRM | FC | 1 | A
555 | DHI | GRT-YV02-P0MAJ-460102 | 460102 | Wiring Diargam For Condenser Vacuum Pump | FI | 2017-06-30 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460102-0 | FC | 0 | A
556 | DHI | GRT-YB10-P0MAJ-460103 | 460103 | Terminal Box For Condenser Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460103-0 | FC | 0 | A
557 | DHI | GRT-YT01-P0MAJ-460104 | 460104 | Technical Data Sheet for Condenser Vacuum Pump | FA | 2017-07-21 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460104-0 | FC | 0 | A
558 | DHI | GRT-YT01-P0MAJ-460105 | 460105 | Motor Data sheet and Characteristic Curves and Drawing For CVP | FI | 2017-07-07 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170396 | FC | 0 | 2017-11-02 | 17.007/E04/PLNE/X/2017 | FI | B | I
559 | DHI | GRT-YT01-P0MAJ-460106 | 460106 | Heat Exchanger Drawing and Data Sheet For Condenser Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460106-0 | FC | 0 | A
560 | DHI | GRT-YL00-P0MAJ-460107 | 460107 | Instrument list For Condenser Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170395 | FC | 0 | 2017-11-02 | 460107-0 | FC | 0 | A
561 | DHI | GRT-CQ02-P0MAJ-460108 | 460108 | Operation and Maintenance Manuals for Condenser & Water box vacuum pump | FI | 2017-11-10 | 2018-01-20 | 2018-01-17 | GRT-DS-IP-DT-180011 | FC | 0 | 2018-04-26 | 129-5th DRM | FC | 0 | A
562 | DHI | GRT-XS00-P0MAJ-460109 | 460109 | Vacuum Pump System Description & Control Philosophy | FA | 2017-07-21 | 2017-09-08 | 2018-04-11 | GRT-DS-IP-DT-180102 | FC | 2 | 2018-04-25 | 460109-2 | FC | 2 | A
563 | DHI | GRT-XB02-P0MAJ-460111 | 460111 | Foundation Drawing For Condenser Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170331 | FC | 0 | 2017-10-02 | 460111-0 | FC | 0 | A
564 | DHI | GRT-XK00-P0MAJ-460112 | 460112 | Outline & Sectional Drawing For Condenser Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460112-0 | FC | 0 | A
565 | DHI | GRT-XK00-P0MAJ-460113 | 460113 | Tank Drawing For Condenser Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-12-20 | GRT-DS-IP-DT-170526 | FC | 1 | 2018-04-26 | 110-5th DRM | FC | 1 | A
566 | DHI | GRT-XK00-P0MAJ-460114 | 460114 | Baseframe Drawing For Condenser Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-03 | 460114-0 | FC | 0 | A
567 | DHI | GRT-YT01-P0MAJ-460115 | 460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | FI | 2017-07-07 | 2017-09-08 | 2017-12-20 | GRT-DS-IP-DT-170526 | FC | 1 | 2018-04-26 | 111-5th DRM | FC | 1 | A
568 | DHI | GRT-XK00-P0MAJ-460116 | 460116 | Name Plate Drawing For Condenser Vacuum Pump | FA | 2017-08-11 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FA | A | A
569 | DHI | GRT-XK00-P0MAJ-460117 | 460117 | Coupling Drawing For Condenser Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FI | A | I
570 | DHI | GRT-DB00-P0MAJ-460118 | 460118 | Performance Curves For Condenser Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170331 | FC | 0 | 2017-10-02 | 460118-0 | FC | 0 | B
571 | DHI | GRT-XN00-P0MAJ-460119 | 460119 | Valve and Specialty List For Condenser Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460119-0 | FC | 0 | A
572 | DHI | GRT-PL03-P0MAJ-460120 | 460120 | Terminal Point List For Condenser Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460120-0 | FC | 0 | B
573 | DHI | GRT-YL10-P0MAJ-460121 | 460121 | Spare Part List For Condenser Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460121-0 | FC | 0 | A
574 | DHI | GRT-DA06-P0MAJ-460122 | 460122 | Utility Consumption List For Condenser Vacuum Pump | FA | 2017-08-08 | 2017-11-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460122-0 | FC | 0 | A
575 | DHI | GRT-DA06-P0MAJ-460123 | 460123 | Lubricant List For Condenser Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460123-0 | FC | 0 | A
576 | DHI | GRT-YL00-P0MAJ-460127 | 460127 | Instrument Data sheet For Condenser Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-20 | GRT-DS-IP-DT-170304 | FC | 0 | 2017-09-26 | 460127-0 | FC | 0 | A
577 | DHI | GRT-YK08-P0MAJ-460200 | 460200 | General Arrangement Drawing For Water Box Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2020-01-18 | GRT-DS-IP-DT-200005 | FC | 2 | 2020-01-18 | 460200-2 | FC | 2 | A
578 | DHI | GRT-XG02-P0MAJ-460201 | 460201 | P & ID For Water Box Vacuum Pump | FA | 2017-06-16 | 2017-09-08 | 2018-01-17 | GRT-DS-IP-DT-180011 | FC | 1 | 2018-04-26 | 130-5th DRM | FC | 1 | A
579 | DHI | GRT-YV02-P0MAJ-460202 | 460202 | Wiring Diargam For Water Box Vacuum Pump | FI | 2017-06-30 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460202-0 | FC | 0 | A
580 | DHI | GRT-YB10-P0MAJ-460203 | 460203 | Terminal Box For Water Box Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170365 | FC | 0 | 2017-11-02 | 460203-0 | FC | 0 | A
581 | DHI | GRT-YT01-P0MAJ-460205 | 460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | FI | 2017-07-07 | 2017-09-08 | 2017-12-15 | GRT-DS-IP-DT-170507 | FC | 1 | 2018-04-26 | 72-5th DRM | FC | 1 | A
582 | DHI | GRT-YT01-P0MAJ-460206 | 460206 | Heat Exchanger Drawing and Data Sheet For Water Box Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460206-0 | FC | 0 | A
583 | DHI | GRT-YL00-P0MAJ-460207 | 460207 | Instrument list For Water Box Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-10-26 | GRT-DS-IP-DT-170395 | FC | 0 | 2017-11-02 | 460207-0 | FC | 0 | A
584 | DHI | GRT-XB02-P0MAJ-460211 | 460211 | Foundation Drawing For Water Box Vacuum Pump | FI | 2017-07-07 | 2017-09-08 | 2017-11-27 | GRT-DS-IP-DT-170455 | FC | 1 | 2018-04-26 | 73-5th DRM | FC | 1 | A
585 | DHI | GRT-XK00-P0MAJ-460212 | 460212 | Outline & Sectional Drawing For Water Box Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460212-0 | FC | 0 | A
586 | DHI | GRT-XK00-P0MAJ-460213 | 460213 | Tank Drawing For Water Box Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-12-20 | GRT-DS-IP-DT-170526 | FC | 1 | 2018-04-26 | 112-5th DRM | FC | 1 | A
587 | DHI | GRT-XK00-P0MAJ-460214 | 460214 | Baseframe Drawing For Water Box Vacuum Pump | FI | 2017-08-04 | 2017-09-08 | 2017-11-27 | GRT-DS-IP-DT-170455 | FC | 1 | 2018-04-26 | 74-5th DRM | FC | 1 | A
588 | DHI | GRT-YT01-P0MAJ-460215 | 460215 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For WBVP | FI | 2017-07-07 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170396 | FC | 0 | 2017-11-23 | 23.001/E04/PLNE/X/2017 | FI | B | I
589 | DHI | GRT-XK00-P0MAJ-460216 | 460216 | Name Plate Drawing For Water Box Vacuum Pump | FA | 2017-08-11 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FA | A | A
590 | DHI | GRT-XK00-P0MAJ-460217 | 460217 | Coupling Drawing For Water Box Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-11-01 | GRT-DS-IP-DT-170393 | FC | 0 | 2017-11-02 | 20.011/E04/PLNE/X/2017 | FI | A | I
591 | DHI | GRT-DB00-P0MAJ-460218 | 460218 | Performance Curves For Water Box Vacuum Pump | FA | 2017-06-30 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170331 | FC | 0 | 2017-10-02 | 460218-0 | FC | 0 | B
592 | DHI | GRT-XN00-P0MAJ-460219 | 460219 | Valve and Specialty List For Water Box Vacuum Pump | FI | 2017-07-21 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460219-0 | FC | 0 | A
593 | DHI | GRT-PL03-P0MAJ-460220 | 460220 | Terminal Point List For Water Box Vacuum Pump | FA | 2017-07-07 | 2017-09-08 | 2017-09-29 | GRT-DS-IP-DT-170322 | FC | 0 | 2017-10-02 | 460220-0 | FC | 0 | B
594 | DHI | GRT-YL10-P0MAJ-460221 | 460221 | Spare Part List For Water Box Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460221-0 | FC | 0 | A
595 | DHI | GRT-DA06-P0MAJ-460222 | 460222 | Utility Consumption List For Water Box Vacuum Pump | FA | 2017-08-08 | 2017-11-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460222-0 | FC | 0 | A
596 | DHI | GRT-DA06-P0MAJ-460223 | 460223 | Lubricant List For Water Box Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-06 | GRT-DS-IP-DT-170271 | FC | 0 | 2017-09-08 | 460223-0 | FC | 0 | A
597 | DHI | GRT-YL00-P0MAJ-460227 | 460227 | Instrument Data sheet For Water Box Vacuum Pump | FI | 2017-07-14 | 2017-09-08 | 2017-09-20 | GRT-DS-IP-DT-170304 | FC | 0 | 2017-09-26 | 460227-0 | FC | 0 | A
598 | DHI | GRT-DN02-P0ZEN-820001 | 820001 | [Commissioning Program]_Steam Blowing-Out Emergency Response Plan | FI | 2019-12-03 | 2020-03-20 | 2019-12-04 | GRT-DS-IP-DT-190174 | FI | A | 2019-12-28 | 820001-0 | FI | A | I
599 | DHI | GRT-DN02-P0ZEN-830000 | 830000 | General Commissioning Procedure | FI | 2018-07-23 | 2018-09-25 | 2019-09-25 | GRT-DS-IP-DT-190141 | FC | 0 | 2019-09-25 | 830000-1 | FC | 0 | A
600 | DHI | GRT-DN02-P0LBA-830001 | 830001 | [Commissioning Procedure] HP & LP Steam System | FA | 2018-02-28 | 2018-04-30 | 2019-12-03 | GRT-DS-IP-DT-190173 | FC | 1 | 2019-12-03 | 830001-2 | FC | 1 | A
601 | DHI | GRT-DN02-P0LBG-830002 | 830002 | [Commissioning Procedure] Auxiliary Steam System | FA | 2018-01-30 | 2018-03-30 | 2019-11-20 | GRT-DS-IP-DT-190155 | FC | 1 | 2019-11-20 | 830002-2 | FC | 1 | A
602 | DHI | GRT-DN02-P0PC-830003 | 830003 | [Commissioning Procedure] Auxiliary Cooling Water System | FA | 2018-01-30 | 2018-03-30 | 2019-11-20 | GRT-DS-IP-DT-190154 | FC | 1 | 2019-11-20 | 830003-2 | FC | 1 | A
603 | DHI | GRT-DN02-P0PG-830004 | 830004 | [Commissioning Procedure] Closed Cooling Water system | FA | 2018-01-30 | 2018-03-30 | 2019-11-20 | GRT-DS-IP-DT-190156 | FC | 1 | 2019-11-20 | 840004-2 | FC | 1 | A
604 | DHI | GRT-DN02-P0LC-830005 | 830005 | [Commissioning Procedure] Condensate System | FA | 2018-01-30 | 2018-03-30 | 2019-12-03 | GRT-DS-IP-DT-190172 | FC | 1 | 2019-12-03 | 830005-2 | FC | 1 | A
605 | DHI | GRT-DN02-P0LA-830006 | 830006 | [Commissioning Procedure] Feedwater System | FA | 2018-01-30 | 2018-03-30 | 2019-11-25 | GRT-DS-IP-DT-190168 | FC | 1 | 2019-11-25 | 830006-2 | FC | 1 | A
606 | DHI | GRT-DN02-P0SCA-830007 | 830007 | [Commissioning Procedure] Compressed Air System | FA | 2018-02-28 | 2018-04-30 | 2019-11-21 | GRT-DS-IP-DT-190157 | FC | 1 | 2019-11-21 | 830007-2 | FC | 1 | A
607 | DHI | GRT-DN02-P0QC-830008 | 830008 | [Commissioning Procedure] Chemical Dosing System | FA | 2018-03-30 | 2018-05-30 | 2019-11-25 | GRT-DS-IP-DT-190164 | FC | 1 | 2019-11-25 | 830008-2 | FC | 1 | A
608 | DHI | GRT-DN02-P0QU-830009 | 830009 | [Commissioning Procedure] Sampling System | FA | 2018-03-30 | 2018-05-30 | 2019-11-25 | GRT-DS-IP-DT-190165 | FC | 1 | 2019-11-25 | 830009-2 | FC | 1 | A
609 | DHI | GRT-DN02-P0LBD-830010 | 830010 | [Commissioning Procedure] Condesate Filter System | FA | 2018-02-28 | 2018-04-30 | 2019-11-21 | GRT-DS-IP-DT-190159 | FC | 1 | 2019-11-21 | 830010-2 | FC | 1 | A
610 | DHI | GRT-DN02-P0MAJ-830011 | 830011 | [Commissioning Procedure] Condenser Vacuum System | FA | 2018-02-28 | 2018-04-30 | 2019-11-22 | GRT-DS-IP-DT-190160 | FC | 1 | 2019-11-22 | 830011-2 | FC | 1 | A
611 | DHI | GRT-DN02-P1H-830012 | 830012 | [Commissioning Procedure] HRSG | FA | 2018-03-30 | 2018-05-30 | 2019-12-03 | GRT-DS-IP-DT-190175 | FC | 1 | 2019-12-03 | 830012-2 | FC | 1 | A
612 | DHI | GRT-DN02-P1LBF-830013 | 830013 | [Commissioning Procedure] HRSG Safety Valve Popping Test | FA | 2018-03-30 | 2018-05-30 | 2020-01-04 | GRT-DS-IP-DT-200001 | FC | 2 | 2020-01-04 | 830013-4 | FC | 2 | A
613 | DHI | GRT-DN02-P0MAJ-830014 | 830014 | [Commissioning Procedure] Water box vacuum | FA | 2018-02-28 | 2018-04-30 | 2019-11-25 | GRT-DS-IP-DT-190167 | FC | 1 | 2019-11-25 | 830014-2 | FC | 1 | A
614 | DHI | GRT-DN02-P0PAH-830015 | 830015 | [Commissioning Procedure] CTCS / Debris filter | FA | 2018-02-28 | 2018-04-30 | 2019-11-25 | GRT-DS-IP-DT-190166 | FC | 1 | 2019-11-25 | 830015-2 | FC | 1 | A
615 | DHI | GRT-DN02-P1H-830016 | 830016 | [Commissioning Procedure] CEMS | FA | 2018-03-30 | 2018-05-30 | 2020-05-14 | GRT-DS-IP-DT-200048 | FC | 3
616 | DHI | GRT-DN02-P1H-830017 | 830017 | [Commissioning Procedure]_Bypass Damper | FA | 2019-07-15 | 2019-09-15 | 2019-08-22 | GRT-DS-IP-DT-190108 | FC | 0 | 2019-08-22 | 830017-1 | FC | 0 | A
617 | DHI | GRT-DN02-P0MAV-830018 | 830018 | [Commissioning Procedure] STG | FA | 2018-03-30 | 2018-05-30 | 2020-01-31 | GRT-DS-IP-DT-200020 | FC | 2 | 2019-11-28 | 830018-2 | FC | 1 | A
618 | DHI | GRT-DN02-P1ZEN-830019 | 830019 | [Commissioning Procedure] Disturbance Test | FA | 2018-04-30 | 2018-06-30 | 2020-06-12 | GRT-DS-IP-DT-200052 | FC | 3 | 2020-06-17 | 830016-6 | FC | 3 | A
619 | DHI | GRT-DN02-P1ZEN-830020 | 830020 | [Commissioning Procedure] Start-up Test | FA | 2018-04-30 | 2018-06-30 | 2020-07-10 | GRT-DS-IP-DT-200060 | FC | 2
620 | DHI | GRT-DN02-P1ZEN-830021 | 830021 | [Commissioning Procedure] Load Change Test | FA | 2018-04-30 | 2018-06-30 | 2020-06-15 | GRT-DS-IP-DT-200053 | FC | 4 | 2020-06-17 | 830021-6 | FC | 4 | A
621 | DHI | GRT-DN02-P1ZEN-830022 | 830022 | [Commissioning Procedure] Capacity Test | FA | 2018-04-30 | 2018-06-30 | 2019-11-25 | GRT-DS-IP-DT-190163 | FC | 1 | 2019-11-25 | 830022-2 | FC | 1 | A
622 | DHI | GRT-DN02-P1ZEN-830023 | 830023 | [Commissioning Procedure]_Fast cut back | FA | 2020-03-17 | 2020-04-17 | 2020-05-08 | GRT-DS-IP-DT-200046 | FC | 0 | 2020-05-08 | 830023-1 | FC | 0 | A
623 | DHI | GRT-DN02-P1ZEN-830026 | 830026 | [Commissioning Procedure] Reliability Test | FA | 2018-04-30 | 2018-06-30 | 2019-12-20 | GRT-DS-IP-DT-190183 | FC | 1 | 2019-12-20 | 830026-2 | FC | 1 | A
624 | DHI | GRT-DN02-P1ZEN-830027 | 830027 | [Commissioning Procedure] Performance Test | FA | 2018-07-30 | 2018-10-30 | 2019-12-10 | GRT-DS-IP-DT-190179 | FC | 1 | 2019-12-10 | 830027-3 | FC | 1 | A
625 | DHI | GRT-DN02-P1ZEN-830028 | 830028 | [Commissioning Procedure] Noise Test | FA | 2018-07-30 | 2018-10-30 | 2019-12-10 | GRT-DS-IP-DT-190178 | FC | 1 | 2019-12-10 | 830028-3 | FC | 1 | A
626 | DHI | GRT-DN02-P1ZEN-830024 | 830024 | [Commissioning Procedure]_Load Rejection | FA | 2020-03-20 | 2020-04-20 | 2020-05-06 | GRT-DS-IP-DT-200044 | FC | 0 | 2020-05-06 | 830024-1 | FC | 0 | A
627 | DHI | GRT-DN02-P1ZEN-830025 | 830025 | [Commissioning Procedure]_Island operation | FA | 2020-04-24 | 2020-05-22 | 2020-05-06 | GRT-DS-IP-DT-200043 | FC | 0 | 2020-05-06 | 830025-1 | FC | 0 | A
628 | PP | GRT-YD00-P0MAG-410103 | 410103 | Cathodic Protection System for Condenser_The Location of Anode (Inlet Waterbox) DCR 0008 | FA | 2019-10-14 | 2019-11-13 | 2019-11-13 | GRT-PP-IP-DT-191482 | FC | 1 | 2019-11-29 | 057/061/GRT/UPR/2019 |  | 1 | A
629 | PP | GRT-YD00-P0MAG-410104 | 410104 | Cathodic Protection System for Condenser_The Location of Anode (Outlet Waterbox) DCR 0008 | FA | 2019-10-14 | 2019-11-13 | 2019-11-13 | GRT-PP-IP-DT-191482 | FC | 1 | 2019-11-29 | 057/061/GRT/UPR/2019 |  | 1 | A
630 | PP | GRT-DA06-P0ZEN-115001 | 115001 | [Process General] Line List | FA | 2017-04-25 | 2017-05-25 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
631 | PP | GRT-DA06-P0ZEN-115002 | 115002 | [Process General] Equipment list | FA | 2017-04-27 | 2017-05-27 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
632 | PP | GRT-DA06-P0ZEN-115003 | 115003 | [Process General] Tie-In List | FA | 2017-05-02 | 2017-06-01 | 2017-05-02 | GRT-PP-IP-DT-170064 | FI | A | 2017-05-02 | 0002.001/C.1.2.17.01/E04/PLNE/V/2017 | FA | A | I
633 | PP | GRT-XG02-P0ZEN-115004 | 115004 | [Process General] Piping and Instrument Diagram (PID) Legends | FA | 2017-02-17 | 2017-03-19 | 2017-02-13 | GRT-PP-IP-DT-170012 | FI | A | 2017-02-03 | 0003.001/ADDONGRT150MW/E04/PLNE/II/2017 | FA | A | I
634 | PP | GRT-XG08-P0ZEN-115005 | 115005 | [Process General] Utility Flow Diagram for Sea Water Intake & Circulating Sea Water Cooling System | FA | 2017-04-01 | 2017-05-01 | 2017-09-27 | GRT-PP-IP-DT-170242 | FC | 0 | 2017-09-27 | N.A | FC | 0 | A
635 | PP | GRT-XG08-P0ZEN-115006 | 115006 | [Process General] Utility Flow Diagram for Raw Water System | FA | 2017-03-30 | 2017-04-29 | 2017-09-27 | GRT-PP-IP-DT-170242 | FC | 0 | 2017-09-27 | N.A | FC | 0 | A
636 | PP | GRT-XG08-P0ZEN-115007 | 115007 | [Process General] Water Balance Calculation | FA | 2017-03-28 | 2017-04-27 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
637 | PP | GRT-XS03-P0ZEN-115008 | 115008 | [Process General] Process Description for BOP | FA | 2017-03-21 | 2017-04-20 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
638 | PP | GRT-XS03-P0ZEN-115009 | 115009 | [Process General] Process Control Philosophy for BOP | FA | 2017-06-12 | 2017-07-12 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
639 | PP | GRT-XW01-P0ZEN-115010 | 115010 | [Process General] Process Design Basis | FA | 2017-02-18 | 2017-03-20 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
640 | PP | GRT-XW01-P0ZEN-115011 | 115011 | [Process General] BEDD | FA | 2017-02-18 | 2017-03-20 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
641 | PP | GRT-XW01-P0ZEN-115012 | 115012 | [Process General] Overpressure study | FA | 2017-06-15 | 2017-07-15 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
642 | PP | GRT-XW01-P0ZEN-115013 | 115013 | [Process General] Process Simulation Report | FA | 2017-03-30 | 2017-04-29 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
643 | PP | GRT-XW03-P0ZEN-115014 | 115014 | [Process General] Process Calculation for IA & PA consumption | FA | 2017-06-15 | 2017-07-15 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A
644 | PP | GRT-XW03-P0ZEN-115015 | 115015 | [Process General] Line Sizing Calculation | FA | 2017-04-14 | 2017-05-14 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
645 | PP | GRT-XW03-P0ZEN-115016 | 115016 | [Process General] Hydraulic Calculation | FA | 2017-05-13 | 2017-06-12 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
646 | PP | GRT-DP00-P0ZEN-125019 | 125019 | [Mechanical General] Specification for Storage Tank | FA | 2017-02-25 | 2017-03-27 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
647 | PP | GRT-DP00-P0ZEN-125020 | 125020 | [Mechanical General] Specification for Centrifugal Pump | FA | 2017-02-25 | 2017-03-27 | 2017-09-06 | GRT-PP-IP-DT-170209 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
648 | PP | GRT-DP00-P0ZEN-125021 | 125021 | [Mechanical General] Specification & Design Criteria for HVAC | FA | 2017-02-25 | 2017-03-27 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A
649 | PP | GRT-YL19-P0ZEN-125022 | 125022 | [Mechanical General] Power Consumption List | FA | 2017-07-10 | 2017-08-09 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | B | 2017-10-24 | 0024.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | B | I
650 | PP | GRT-CC00-P0ZEN-145023 | 145023 | [Piping General] Plot Plan for BOP | FA | 2017-02-04 | 2017-03-06 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A
651 | PP | GRT-CC00-P0ZEN-145024 | 145024 | [Piping General] Information Drawing for Loading Data & Local Foundation Water Treatment Area | FA | 2017-06-07 | 2017-07-07 | 2017-06-02 | GRT-PP-IP-DT-170105 | FI | A | 2017-06-12 | 0012.001/C.1.2.17.01/E04/PLNE/VI/2017 | FA | A | I
652 | PP | GRT-CC00-P0ZEN-145025 | 145025 | [Piping General] Layout Crossing Road & Electrical Underground | FA | 2017-02-24 | 2017-09-07 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A
653 | PP | GRT-CC00-P0ZEN-145026 | 145026 | [Piping General] Detail Crossing Road & Electrical Underground | FA | 2017-02-24 | 2017-03-26 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A
654 | PP | GRT-CC00-P0ZEN-145027 | 145027 | [Piping General] Piping Layout Drawing for Sea Water System | FA | 2017-02-04 | 2017-03-06 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A
655 | PP | GRT-CC05-P0ZEN-145028 | 145028 | [Piping General] Support Standard Drawing | FA | 2017-03-18 | 2017-04-17 | 2017-05-23 | GRT-PP-IP-DT-170089 | FC | I | 2017-05-29 | 0029.001/C.1.2.17.01/E04/PLNE/V/2017 | FA | I | I
656 | PP | GRT-CC07-P0ZEN-145029 | 145029 | [Piping General] Piping Wall Thickness Calculation | FA | 2017-02-10 | 2017-03-12 | 2017-05-22 | GRT-PP-IP-DT-170086 | FC | 0 | 2017-05-22 | N.A | FC | 0 | A
657 | PP | GRT-CV03-P0ZEN-145030 | 145030 | [Piping General] Piping Design Specification | FA | 2017-03-04 | 2017-04-03 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A
658 | PP | GRT-DE00-P0ZEN-145031 | 145031 | [Piping General] Piping Fabrication and Installation | FA | 2017-03-15 | 2017-04-14 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
659 | PP | GRT-DE00-P0ZEN-145032 | 145032 | [Piping General] Specification for Wrapping Tape Material | FA | 2017-03-02 | 2017-04-01 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
660 | PP | GRT-DE00-P0ZEN-145033 | 145033 | [Piping General] Piping Material Specification | FA | 2017-02-11 | 2017-03-13 | 2017-12-20 | GRT-PP-IP-DT-170369 | FC | 1 | 2017-12-22 | 0022.001/C.I.2.17.01/E04/PLNE/XII/2017 | FC | 1 | A
661 | PP | GRT-DE00-P0ZEN-145034 | 145034 | [Piping General] Specification for Cement Lined for Carbon Stell pipe | FA | 2017-02-23 | 2017-03-25 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
662 | PP | GRT-XJ00-P0ZEN-145035 | 145035 | [Piping General] Isometric Drawing | FA | 2017-06-07 | 2017-07-07 | 2020-05-14 | GRT-PP-IP-DT-201593 (DCR 00054) | FC | 2DCR0 | 2020-06-18 | 024-GRT-M-U-GPE-2020 |  | 2DCR0 | A
663 | PP | GRT-XV00-P0ZEN-145036 | 145036 | [Piping General] Pipe Support List | FA | 2017-06-07 | 2017-07-07 | 2019-04-02 | GRT-PP-IP-DT-191115 (DCR 00035) | FC | DCR | 2019-04-24 | 028/061/GRT/UPR/2019 | FC | DCR | B
664 | PP | GRT-XN00-P0ZEN-145037 | 145037 | [Piping General] Valve List | FA | 2017-03-11 | 2017-04-10 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A
665 | PP | GRT-YT01-P0ZEN-145038 | 145038 | [Piping General] Data Sheet for Valve | FA | 2017-03-18 | 2017-04-17 | 2017-10-12 | GRT-PP-IP-DT-170267 | FC | 0 | 2017-10-12 | N.A | FC | 0 | A
666 | PP | GRT-YT01-P0ZEN-145039 | 145039 | [Piping General] Data Sheet for Special Item | FA | 2017-03-18 | 2017-04-17 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
667 | PP | GRT-YE00-P0ZEN-155040 | 155040 | [Electrical General] General Electrical Symbol List | FI | 2017-03-01 | 2017-03-31 | 2017-10-23 | GRT-PP-IP-DT-170282 | FI | B | 2017-10-25 | 0025.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | I
668 | PP | GRT-YE00-P0ZEN-155041 | 155041 | [Electrical General] Standard Installation Drawing for Electrical | FI | 2017-03-01 | 2017-03-31 | 2017-10-23 | GRT-PP-IP-DT-170282 | FI | B | 2017-10-25 | 0025.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | I
669 | PP | GRT-YE00-P0ZEN-155042 | 155042 | [Electrical General] General Area Clock System Wiring Layout | FA | 2017-03-15 | 2017-04-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
670 | PP | GRT-YE00-P0ZEN-155043 | 155043 | [Electrical General] General Area Clock System Wiring Layout | FA | 2017-03-15 | 2017-04-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
671 | PP | GRT-YE00-P0ZEN-155045 | 155045 | [Electrical General] Cable Tray, Trench and Power Wiring Layout for General Area | FA | 2017-06-10 | 2017-07-10 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 1 | 2017-09-08 | N.A | FC | 1 | A
672 | PP | GRT-YE06-P0ZEN-155046 | 155046 | [Electrical General] Grounding Wiring Layout for General Area | FA | 2017-03-10 | 2017-04-09 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 1 | 2017-08-22 | N.A | FC | 1 | A
673 | PP | GRT-YE06-P0ZEN-155047 | 155047 | [Electrical General] Lightning Protection Layout for General Area | FA | 2017-03-23 | 2017-06-10 | 2017-07-25 | GRT-PP-IP-DT-170155 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A
674 | PP | GRT-YL16-P0ZEN-155048 | 155048 | [Electrical General] Power and Control Cable Schedule | FI | 2017-07-14 | 2017-08-13 | 2017-10-23 | GRT-PP-IP-DT-170282 | FI | C | 2017-10-25 | 0025.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | C | I
675 | PP | GRT-YQ01-P0ZEN-155049 | 155049 | [Electrical General] Flood Light Wiring Layout for Outfall Area | FA | 2017-07-14 | 2017-08-13 | 2017-07-24 | GRT-PP-IP-DT-170151 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A
676 | PP | GRT-YQ01-P0ZEN-155050 | 155050 | [Electrical General] Lighting and Receptacle Panel Schedule and Connection Diagram for Oufall Area | FA | 2017-06-22 | 2017-07-22 | 2017-07-24 | GRT-PP-IP-DT-170151 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A
677 | PP | GRT-YR02-P0ZEN-155074 | 155074 | [Electrical General] Datasheet for Electrical Bulk Material | FA | 2017-03-11 | 2017-06-20 | 2017-10-31 | GRT-PP-IP-DT-170301 | FC(D) | C | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | C | A
678 | PP | GRT-YR02-P0ZEN-155073 | 155073 | [Electrical General] Datasheet for Cable Tray & Accessories | FA | 2017-03-11 | 2017-04-10 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A
679 | PP | GRT-YR02-P0ZEN-155072 | 155072 | [Electrical General] Datasheet for Lighting Fixture & Accessories | FA | 2017-03-11 | 2017-04-10 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A
680 | PP | GRT-YR02-P0ZEN-155071 | 155071 | [Electrical General] Datasheet for Busduct | FA | 2017-03-11 | 2017-04-10 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A
681 | PP | GRT-YR02-P0ZEN-155070 | 155070 | [Electrical General] Datasheet for UPS, Battery & Battery Charger | FA | 2017-03-11 | 2017-04-10 | 2019-03-05 | GRT-PP-IP-DT-191041 | FC | 4 | 2019-03-13 | 019/061/GRT/UPR/2019 | FC | 4 | B
682 | PP | GRT-YR02-P0ZEN-155069 | 155069 | [Electrical General] Datasheet for Cable and Wire | FA | 2017-03-08 | 2017-04-07 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
683 | PP | GRT-YR02-P0ZEN-155068 | 155068 | [Electrical General] Datasheet for Distribution & Lighting Panel | FA | 2017-03-08 | 2017-04-07 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
684 | PP | GRT-YR02-P0ZEN-155067 | 155067 | [Electrical General] Datasheet for Low Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
685 | PP | GRT-YR02-P0ZEN-155066 | 155066 | [Electrical General] Datasheet for Medium Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
686 | PP | GRT-YR02-P0ZEN-155065 | 155065 | [Electrical General] Datasheet for Auxiliary & Service Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
687 | PP | GRT-YR02-P0ZEN-155064 | 155064 | [Electrical General] Datasheet for Main Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
688 | PP | GRT-YR02-P0ZEN-155063 | 155063 | [Electrical General] Datasheet for Emergency Diesel Generator | FA | 2017-03-07 | 2017-04-06 | 2017-05-10 | GRT-PP-IP-DT-170077 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
689 | PP | GRT-YR02-P0ZEN-155061 | 155061 | [Electrical General] Specification for Busduct | FA | 2017-03-11 | 2017-04-10 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A
690 | PP | GRT-YR02-P0ZEN-155060 | 155060 | [Electrical General] Specification for UPS, Battery & Battery Charger | FA | 2017-03-11 | 2017-04-10 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
691 | PP | GRT-YR02-P0ZEN-155059 | 155059 | [Electrical General] Specification for Induction Motor | FA | 2017-03-02 | 2017-04-01 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A
692 | PP | GRT-YR02-P0ZEN-155058 | 155058 | [Electrical General] Specification for Cable and Wire | FA | 2017-03-08 | 2017-04-07 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A
693 | PP | GRT-YR02-P0ZEN-155057 | 155057 | [Electrical General] Specification for Distribution & Lighting Panel | FA | 2017-03-08 | 2017-04-07 | 2017-06-30 | GRT-PP-IP-DT-170102 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A
694 | PP | GRT-YR02-P0ZEN-155056 | 155056 | [Electrical General] Specification for Low Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
695 | PP | GRT-YR02-P0ZEN-155055 | 155055 | [Electrical General] Specification for Medium Voltage Switchgear and MCC | FA | 2017-03-07 | 2017-04-06 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
696 | PP | GRT-YR02-P0ZEN-155054 | 155054 | [Electrical General] Specification for Auxiliary & Service Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
697 | PP | GRT-YR02-P0ZEN-155053 | 155053 | [Electrical General] Specification for Main Transformer | FA | 2017-02-18 | 2017-03-20 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
698 | PP | GRT-YR02-P0ZEN-155052 | 155052 | [Electrical General] Specification for Emergency Diesel Generator | FA | 2017-03-07 | 2017-04-06 | 2017-05-10 | GRT-PP-IP-DT-170077 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
699 | PP | GRT-YR02-P0ZEN-155051 | 155051 | [Electrical General] General Specification for Electrical | FA | 2017-03-01 | 2017-03-31 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
700 | PP | GRT-YS02-P0ZEN-155075 | 155075 | [Electrical General] Connection Diagram For Power and Control Cable | FI | 2017-06-14 | 2017-07-14 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | B | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | I
701 | PP | GRT-YU01-P0ZEN-155076 | 155076 | [Electrical General] Overall Single Line Diagram for 150 kv | FA | 2017-02-19 | 2017-03-21 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 1 | 2017-11-24 | N.A | FC | 1 | A
702 | PP | GRT-YU01-P0ZEN-155077 | 155077 | [Electrical General] Single Line Diagram for MV System | FA | 2017-02-25 | 2017-03-27 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
703 | PP | GRT-YU01-P0ZEN-155078 | 155078 | [Electrical General] Single Line Diagram for LV System | FA | 2017-02-25 | 2017-03-27 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 1 | 2017-11-21 | N.A | FC | 1 | A
704 | PP | GRT-YU01-P0ZEN-155079 | 155079 | [Electrical General] Single Line Diagram for UPS & DC System | FA | 2017-02-28 | 2017-03-30 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
705 | PP | GRT-YU01-P0ZEN-155080 | 155080 | [Electrical General] Single Line Diagram for Protection & Metering System | FA | 2017-03-02 | 2017-04-01 | 2018-06-28 | GRT-PP-IP-DT-180654 | FC | 1 | 2017-07-13 | Comment Sheet IP | FC | 1 | A
706 | PP | GRT-XW03-P0ZEN-155081 | 155081 | [Electrical General] Electrical Load Data Calculation | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
707 | PP | GRT-XW03-P0ZEN-155082 | 155082 | [Electrical General] Voltage Drop and Power Flow Study | FA | 2017-03-14 | 2017-04-13 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
708 | PP | GRT-XW03-P0ZEN-155083 | 155083 | [Electrical General] Short Circuit Calculation | FA | 2017-03-14 | 2017-04-13 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
709 | PP | GRT-XW03-P0ZEN-155084 | 155084 | [Electrical General] Protective Relay Coordination Study for MV & LV Switcgear | FA | 2017-06-14 | 2017-07-14 | 2017-10-18 | GRT-PP-IP-DT-170274 | FC(D) | C | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FA | C | A
710 | PP | GRT-XW03-P0ZEN-155085 | 155085 | [Electrical General] Emergency Diesel Capacity Calculation | FA | 2017-03-15 | 2017-04-14 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
711 | PP | GRT-XW03-P0ZEN-155086 | 155086 | [Electrical General] Transformer Sizing Calculation | FA | 2017-02-18 | 2017-03-20 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
712 | PP | GRT-XW03-P0ZEN-155087 | 155087 | [Electrical General] UPS, Battery & Battery Charger Capacity | FA | 2017-03-15 | 2017-04-14 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
713 | PP | GRT-XW03-P0ZEN-155088 | 155088 | [Electrical General] Lighting Illumination Level Calculation | FA | 2017-06-14 | 2017-07-14 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
714 | PP | GRT-XW03-P0ZEN-155089 | 155089 | [Electrical General] Grounding System Calculation | FA | 2017-03-01 | 2017-03-31 | 2017-04-18 | GRT-PP-IP-DT-170048 | FC | 0 | 2017-05-04 | N.A | FA | 0 | A
715 | PP | GRT-XW03-P0ZEN-155090 | 155090 | [Electrical General] Lightning Protection System Calculation | FA | 2017-03-16 | 2017-04-15 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
716 | PP | GRT-XW03-P0ZEN-155091 | 155091 | [Electrical General] Cable Size Calculation | FA | 2017-03-30 | 2017-04-29 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
717 | PP | GRT-XW03-P0ZEN-155092 | 155092 | [Electrical General] MOTOR STARTING ANALYSIS | FA | 2017-04-01 | 2017-05-01 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
718 | PP | GRT-XW03-P0ZEN-155095 | 165095 | [Electrical General] Busduct Sizing Calculation | FA | 2017-03-16 | 2017-04-15 | 2017-05-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-05-30 | N.A | FC | 0 | A
719 | PP | GRT-XW03-P0ZEN-155096 | 155096 | [Electrical General] Electrical Load List | FA | 2017-02-20 | 2017-03-22 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
720 | PP | GRT-CV03-P0ZEN-165097 | 165097 | [Instrument General] Data Sheet for CCTV Camera | FA | 2017-06-14 | 2017-07-14 | 2019-11-28 | GRT-PP-IP-DT-191509 | FC | 3 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 3 | A
721 | PP | GRT-CV03-P0ZEN-165098 | 165098 | [Instrument General] Data Sheet for Telephone System | FA | 2017-06-14 | 2017-07-14 | 2018-01-26 | GRT-PP-IP-DT-180397 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
722 | PP | GRT-CV03-P0ZEN-165099 | 165099 | [Instrument General] Data Sheet for Paging System | FA | 2017-07-19 | 2017-08-18 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A
723 | PP | GRT-YD00-P0ZEN-165100 | 165100 | [Instrument General] Instrument Layout Keyplan | FA | 2017-09-14 | 2017-06-20 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
724 | PP | GRT-YD00-P0ZEN-165101 | 165101 | [Instrument General] Instrument Main Cable Way Layout | FA | 2017-07-19 | 2017-08-18 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A
725 | PP | GRT-YD00-P0ZEN-165102 | 165102 | [Instrument General] CCTV Location Plan Layout | FA | 2017-09-14 | 2017-07-30 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 3 | 2018-02-21 | stempel approved | FC | 3 | A
726 | PP | GRT-YD00-P0ZEN-165103 | 165103 | [Instrument General] CCTV Cable Wiring Layout | FA | 2017-10-05 | 2017-07-30 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 1 | 2018-02-21 | stempel approved | FC | 1 | A
727 | PP | GRT-YD00-P0ZEN-165104 | 165104 | [Instrument General] Telephone Location Plan Layout | FA | 2017-08-08 | 2017-06-20 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A
728 | PP | GRT-YD00-P0ZEN-165105 | 165105 | [Instrument General] Telephone Cable Wiring Layout | FA | 2017-06-14 | 2017-07-30 | 2017-09-20 | GRT-PP-IP-DT-170232 | FC | 0 | 2017-09-20 | N.A | FC | 0 | A
729 | PP | GRT-YD00-P0ZEN-165106 | 165106 | [Instrument General] Paging Location Plan Layout | FA | 2017-06-23 | 2017-07-23 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
730 | PP | GRT-YD00-P0ZEN-165107 | 165107 | [Instrument General] Paging Cable Wiring Layout | FA | 2017-07-19 | 2017-08-18 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
731 | PP | GRT-YD00-P0ZEN-165108 | 165108 | [Instrument General] Instrument Grounding Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A
732 | PP | GRT-YD00-P0ZEN-165109 | 165109 | [Instrument General] Instrument Panel Arrangement for BOP | FA | 2017-07-19 | 2017-08-18 | 2019-05-23 | DRM_22-24MAY2019 (DCR 0041) | FC | 2DCR1 | 2019-05-23 | 031/061/GRT/UPR/2018 |  | 2DCR1 | B
733 | PP | GRT-YD00-P0ZEN-165110 | 165110 | [Instrument General] Instrument Panel Base Frame & Hole Opening | FA | 2017-07-19 | 2017-08-18 | 2018-01-26 | GRT-PP-IP-DT-180397 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A
734 | PP | GRT-YD00-P0ZEN-165111 | 165111 | [Instrument General] Instrument Wiring Layout Inside Control Room | FA | 2017-07-19 | 2017-08-18 | 2018-01-26 | GRT-PP-IC-FCR-00028 | FC | 1FCR3 |  | 0185/SMGRT.IP-TEI/VII/2019 |  | 1FCR3 | A
735 | PP | GRT-YF00-P0ZEN-165112 | 165112 | [Instrument General] Instrument Control Logic for Sea Water Intake System | FA | 2017-07-07 | 2017-08-06 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 1 | 2018-11-14 | Comment Sheet IP | FC | 1 | A
736 | PP | GRT-YL01-P0ZEN-165114 | 165114 | [Instrument General] Instrument Index for BOP | FA | 2017-03-17 | 2017-04-16 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
737 | PP | GRT-YL15-P0ZEN-165115 | 165115 | [Instrument General] Instrument Cable Drum Schedule for BOP | FA | 2017-04-29 | 2017-05-29 | 2017-11-03 | GRT-PP-IP-DT-170305 | FC(D) | B | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | B
738 | PP | GRT-YK00-P0ZEN-165116 | 165116 | [Instrument General] Instrument Typical Drawing for Installation | FA | 2017-06-14 | 2017-07-14 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A
739 | PP | GRT-YK00-P0ZEN-165117 | 165117 | [Instrument General] CCTV Typical Drawing for Installation | FA | 2017-04-22 | 2017-05-22 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
740 | PP | GRT-YK00-P0ZEN-165118 | 165118 | [Instrument General] Telephone Typical Drawing for Installation | FA | 2017-04-25 | 2017-05-25 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
741 | PP | GRT-YK00-P0ZEN-165119 | 165119 | [Instrument General] Paging Typical Drawing for Installation | FA | 2017-04-26 | 2017-05-26 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
742 | PP | GRT-YQ07-P0ZEN-165120 | 165120 | [Instrument General] General Specification for Telephone System | FA | 2017-04-17 | 2017-05-17 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
743 | PP | GRT-YR04-P0ZEN-165121 | 165121 | [Instrument General] Instrument General Symbol & Index | FA | 2017-02-18 | 2017-03-20 | 2017-02-16 | GRT-PP-IP-DT-170013 | FI | A | 2017-03-27 | 0027.001/ADDONGRT150MW/E04/PLNE/III/2017 | FA | A | I
744 | PP | GRT-YR05-P0ZEN-165123 | 165123 | [Instrument General] General Specification for CCTV | FA | 2017-04-16 | 2017-05-16 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
745 | PP | GRT-YS01-P0ZEN-165124 | 165124 | [Instrument General] CCTV Block Diagram | FA | 2017-04-22 | 2017-05-22 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 3 | 2018-02-21 | stempel approved | FC | 3 | A
746 | PP | GRT-YS01-P0ZEN-165125 | 165125 | [Instrument General] Telephone System Block Diagram | FA | 2017-04-25 | 2017-05-25 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A
747 | PP | GRT-YS01-P0ZEN-165126 | 165126 | [Instrument General] Paging System Block Diagram | FA | 2017-06-14 | 2017-07-14 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
748 | PP | GRT-CA07-P0ZEN-175127 | 175127 | [Civil General] Design Specification for Civil and Structural | FA | 2017-02-23 | 2017-03-25 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
749 | PP | GRT-YT01-P0PAC-115136 | 115136 | Sea Water Intake Pump Process Data Sheet | FA | 2017-02-03 | 2017-03-05 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A
750 | PP | GRT-YT01-P0PAC-115137 | 115137 | [Circulating Water Pump] Sea Water Intake Basin Process Data Sheet | FA | 2017-02-10 | 2017-03-12 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
751 | PP | GRT-YD00-P0PAC-125139 | 125139 | [Circulating Water Pump] GA Drawing Stop Log Screen | FA | 2017-07-15 | 2017-08-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
752 | PP | GRT-YD00-P0PAC-125140 | 125140 | [Circulating Water Pump] GA Drawing Bar Screen | FA | 2017-07-15 | 2017-08-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
753 | PP | GRT-YD00-P0PAC-125141 | 125141 | [Circulating Water Pump] GA Drawing Travelling Screen | FA | 2017-07-15 | 2017-08-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
754 | PP | GRT-YT01-P0PAC-125142 | 125142 | [Circulating Water Pump] Mech. Data Sheet for CWP Pump | FA | 2017-02-11 | 2017-03-13 | 2017-05-09 | GRT-PP-IP-DT-170075 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
755 | PP | GRT-CC00-P0PAC-145145 | 145145 | [Circulating Water Pump] Piping Layout Drawing for Sea Water Intake System | FA | 2017-02-03 | 2017-03-05 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A
756 | PP | GRT-CC00-P0PAC-145146 | 145146 | [Circulating Water Pump] Detail & Section Drawing for Sea Water Intake System | FA | 2017-02-03 | 2017-03-05 | 2017-09-07 | GRT-PP-IP-DT-170212 | FC | 0 | 2017-09-07 | N.A | FC | 0 | A
757 | PP | GRT-XW03-P0PAC-155147 | 155147 | [Circulating Water Pump] Electrical Load Data Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
758 | PP | GRT-XW03-P0PAC-155148 | 155148 | [Circulating Water Pump] Grounding System Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
759 | PP | GRT-XW03-P0PAC-155149 | 155149 | [Circulating Water Pump] Cable Size Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
760 | PP | GRT-XW03-P0PAC-155001 | 155001 | [Circulating Water Pump] Lighting Illumination Level Calculation for Sea Water Intake | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
761 | PP | GRT-YD16-P0PAC-155151 | 155151 | [Circulating Water Pump] Cable Tray and Power Wiring Layout | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
762 | PP | GRT-YE03-P0PAC-155152 | 155152 | [Circulating Water Pump] Grounding and Lightning Protection Layout | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
763 | PP | GRT-YQ01-P0PAC-155153 | 155153 | [Circulating Water Pump] Lighting and Receptacle Wiring Layout | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
764 | PP | GRT-YQ01-P0PAC-155154 | 155154 | [Circulating Water Pump] Lighting and Receptacle Connection Diagram | FA | 2017-02-03 | 2017-03-05 | 2017-08-23 | GRT-PP-IP-DT-170193 | FC | 0 | 2017-08-23 | N.A | FC | 0 | A
765 | PP | GRT-CV03-P0PAC-165155 | 165155 | [Circulating Water Pump] Instrument Data Sheet for Circulating Water Pump | FA | 2017-03-11 | 2017-04-10 | 2017-07-24 | GRT-PP-IP-DT-170151 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A
766 | PP | GRT-YD00-P0PAC-165156 | 165156 | [Circulating Water Pump] Instrument Main Cable & JB Layout | FA | 2017-03-11 | 2017-04-10 | 2017-07-17 | GRT-PP-IP-DT-170140 | FC | 0 | 2017-07-17 | N.A | FC | 0 | A
767 | PP | GRT-YD00-P0PAC-165157 | 165157 | [Circulating Water Pump] Instrument Location Plan Layout | FA | 2017-03-11 | 2017-04-10 | 2017-07-17 | GRT-PP-IP-DT-170140 | FC | 0 | 2017-07-17 | N.A | FC | 0 | A
768 | PP | GRT-YD00-P0PAC-165158 | 165158 | [Circulating Water Pump] Instrument Cable Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-07-17 | GRT-PP-IP-DT-170140 | FC | 0 | 2017-07-17 | N.A | FC | 0 | A
769 | PP | GRT-YL01-P0PAC-165160 | 165160 | [Circulating Water Pump] I/O List | FA | 2017-03-11 | 2017-04-10 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A
770 | PP | GRT-YL15-P0PAC-165161 | 165161 | [Circulating Water Pump] Instrument Cable Schedule | FI | 2017-03-11 | 2017-04-10 | 2019-05-26 | GRT-PP-IP-DT-191210 | FC | 0DCR1 |  | 0029.001/C.I.2.17.01/E04/PLNE/V/2019 |  | 0DCR1 | A
771 | PP | GRT-YS02-P0PAC-165162 | 165162 | [Circulating Water Pump] Instrument Termination Diagram for Circulating Water Pump | FA | 2017-03-11 | 2017-04-10 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
772 | PP | GRT-CC03-P0PAC-175164 | 175164 | [Circulating Water Pump] Circulating Water Pump Framing Plan | FA | 2017-02-14 | 2017-03-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
773 | PP | GRT-CC03-P0PAC-175165 | 175165 | [Circulating Water Pump] Circulating Water Pump Section, Slab Schedule and Wall Schedule | FA | 2017-02-14 | 2017-03-16 | 2019-11-29 | MINI DRM 28-29NOV19 | FC | 2 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 2 | A
774 | PP | GRT-CC03-P0PAC-175166 | 175166 | [Circulating Water Pump] Circulating Water Pump Sections | FA | 2017-02-14 | 2017-03-16 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
775 | PP | GRT-CC03-P0PAC-175167 | 175167 | [Circulating Water Pump] Circulating Water Pump Detail 1 & 2 | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
776 | PP | GRT-CC03-P0PAC-175168 | 175168 | [Circulating Water Pump] Circulating Water Pump Detail 3 | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
777 | PP | GRT-CC03-P0PAC-175169 | 175169 | [Circulating Water Pump] Circulating Water Pump Detail 4,5 and Suction Chamber | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
778 | PP | GRT-CC03-P0PAC-175170(1OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Stop Log Detail and Section | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
779 | PP | GRT-CC03-P0PAC-175170(2OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Gantry Crane and Traveling Screen Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
780 | PP | GRT-CC03-P0PAC-175170(3OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Bar Screen and Mechanical Rake/Car Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
781 | PP | GRT-CC03-P0PAC-175170(4OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Screen Wash Pumps and Sea Water Feed Pumps Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
782 | PP | GRT-CC03-P0PAC-175170(5OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump CWP Pedestal Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
783 | PP | GRT-CC03-P0PAC-175170(6OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Gantry Crane Rail-2 Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
784 | PP | GRT-CC03-P0PAC-175170(7OF7) | 175170 | [Circulating Water Pump] Circulating Water Pump Pipe Header Pedestal Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
785 | PP | GRT-CC03-P0PAC-175170 | 175170 | [Circulating Water Pump] Circulating Water Pump Pipe Header Pedestal Detail | FA | 2017-02-14 | 2017-03-16 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
786 | PP | GRT-CC07-P0PAC-175174 | 175174 | [Circulating Water Pump] Calculation Sheet for Cooling Water Intake Basin | FA | 2017-02-14 | 2017-03-16 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
787 | PP | GRT-CC00-P0PAD-145176 | 145176 | [Circulating Water Pump Outfall] Piping Layout Drawing for Sea Water Outfall | FA | 2017-07-15 | 2017-08-14 | 2017-10-12 | GRT-PP-IP-DT-170267 | FC | 0 | 2017-10-12 | N.A | FC | 0 | A
788 | PP | GRT-CC00-P0PAD-145177 | 145177 | [Circulating Water Pump Outfall] Detail & Section Drawing for Sea Water Outfall | FA | 2017-07-07 | 2017-08-06 | 2017-10-12 | GRT-PP-IP-DT-170267 | FC | 0 | 2017-10-12 | N.A | FC | 0 | A
789 | PP | GRT-CC07-P0PAD-175178(1OF3) | 175178 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Plan | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A
790 | PP | GRT-CC07-P0PAD-175178(2OF3) | 175178 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Section Slab Schedule and Wall Schedule | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A
791 | PP | GRT-CC07-P0PAD-175178(3OF3) | 175178 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Section and Detail | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A
792 | PP | GRT-CC07-P0PAD-175179(1OF2) | 175179 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Details | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A
793 | PP | GRT-CC07-P0PAD-175179(2OF2) | 175179 | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Details | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 1 | 2017-09-18 | N.A | FC | 1 | A
794 | PP | GRT-CC07-P0PAD-175180 | 175180 | [Circulating Water Pump Outfall] Calculation Sheet for Circulating Water Pump Outfall | FA | 2017-02-11 | 2017-03-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
795 | PP | GRT-XG02-P0UGX-115183 | 115183 | [Chlorination System] Piping and instrument diagram (PID) Chlorination System | FA | 2017-06-07 | 2017-07-07 | 2017-12-20 | GRT-PP-IP-DT-170367 | FC | 0 | 2017-12-21 | N.A | FC | 0 | A
796 | PP | GRT-XW01-P0UGX-115184 | 115184 | [Chlorination System] Process specification for Chlorination system | FA | 2017-06-07 | 2017-07-07 | 2017-10-31 | GRT-PP-IP-DT-170301 | FC(D) | C | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | C | B
797 | PP | GRT-CA05-P0UGX-125185 | 125185 | [Chlorination System] Chlorination Plant Building Cold Water Layout & Isometric | FA | 2017-03-11 | 2017-04-10 | 2017-04-07 | GRT-PP-PLN-E-170041 | FC(D) | A | 2017-04-21 | 0021.001/C.1.2.17.01/E04/PLNE/IV/2017 | FA | A | B
798 | PP | GRT-CA05-P0UGX-125186 | 125186 | [Chlorination System] Chlorination Plant Building Grey, Black Water Layout & Isometric | FA | 2017-03-11 | 2017-04-10 | 2017-04-07 | GRT-PP-PLN-E-170041 | FC(D) | A | 2017-04-21 | 0021.001/C.1.2.17.01/E04/PLNE/IV/2017 | FA | A | B
799 | PP | GRT-HM01-P0UGX-125187 | 125187 | [Chlorination System] Chlorination Plant Building HVAC Flow Schematic Diagram | FA | 2017-03-11 | 2017-04-10 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A
800 | PP | GRT-HM01-P0UGX-125188 | 125188 | [Chlorination System] Chlorination Plant Building HVAC Ducting Layout | FA | 2017-03-11 | 2017-04-10 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A
801 | PP | GRT-HM01-P0UGX-125189 | 125189 | [Chlorination System] Chlorination Plant Building HVAC Elevation, Equipment Layout | FA | 2017-03-11 | 2017-04-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
802 | PP | GRT-HM01-P0UGX-125190 | 125189 | [Chlorination System] Chlorination Plant Building HVAC, Elevation, Section & Detail | FA | 2017-03-11 | 2017-04-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
803 | PP | GRT-HM05-P0UGX-125191 | 125191 | [Chlorination System] HVAC Calculation for Chlorination Plant Building | FA | 2017-07-07 | 2017-08-06 | 2017-09-06 | GRT-PP-IP-DT-170209 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
804 | PP | GRT-CC00-P0UGX-145192 | 145192 | [Chlorination System] Piping Layout Drawing for Chlorination | FA | 2017-07-15 | 2017-08-14 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
805 | PP | GRT-YD16-P0UGX-155193 | 155193 | [Chlorination System] Cable Tray and Power Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-12-28 | GRT-PP-IP-DT-170376 | FC | 1 | 2017-12-29 | N.A | FC | 1 | A
806 | PP | GRT-YE07-P0UGX-155194 | 155194 | [Chlorination System] Grounding Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
807 | PP | GRT-YE07-P0UGX-155195 | 155195 | [Chlorination System] Lightning Protection Layout | FA | 2017-03-11 | 2017-04-10 | 2019-09-19 | GRT-PP-IP-DT-191389 (DCR 0040) | FC | 0DCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) |  | 0DCR2 | A
808 | PP | GRT-YQ01-P0UGX-155196 | 155196 | [Chlorination System] Lighting and Receptale Wiring Layout | FA | 2017-03-11 | 2017-04-10 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
809 | PP | GRT-YQ01-P0UGX-155197 | 155197 | [Chlorination System] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-03-11 | 2017-04-10 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
810 | PP | GRT-CA00-P0UGX-175206 | 175206 | [Chlorination System] Chlorination System Architectural Plan, View, Section & Finishing Schedule | FA | 2017-03-04 | 2017-04-03 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
811 | PP | GRT-CA00-P0UGX-175207 | 175207 | [Chlorination System] Section, Detail & Finishing Schedule | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
812 | PP | GRT-CA01-P0UGX-175208 | 175208 | [Chlorination System] Foundation Plan | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
813 | PP | GRT-CA01-P0UGX-175209 | 175209 | [Chlorination System] Foundation Detail | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
814 | PP | GRT-CA01-P0UGX-175210 | 175210 | [Chlorination System] Steel Structure Framing Plan | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
815 | PP | GRT-CA01-P0UGX-175211 | 175211 | [Chlorination System] Steel Structure Framing Elevation and Detail | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
816 | PP | GRT-CA06-P0UGX-175212 | 175212 | [Chlorination System] Calculation Sheet for Chlorination System Building | FA | 2017-06-23 | 2017-07-23 | 2017-08-24 | GRT-PP-IP-DT-170198 | FC | 0 | 2017-08-25 | N.A | FC | 0 | A
817 | PP | GRT-YE00-P1UHA-155213 | 155213 | [HRSG] Cable Tray and Power Wiring Layout | FA | 2017-06-15 | 2017-07-15 | 2017-09-14 | GRT-PP-IP-DT-170226 | FC | 0 | 2017-09-14 | N.A | FC | 0 | A
818 | PP | GRT-YE00-P1UHA-155214 | 155214 | [HRSG] Clock System Wiring Layout | FA | 2017-10-31 | 2017-06-20 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A
819 | PP | GRT-YE06-P1UHA-155215 | 155215 | [HRSG] Grounding Wiring Layout | FA | 2017-06-06 | 2017-06-20 | 2017-06-06 | GRT-PP-IP-DT-170110 | FC | 0 | 2017-06-06 | N.A | FC | 0 | A
820 | PP | GRT-YE06-P1UHA-155216 | 155216 | [HRSG] Lightning Protection Layout | FA | 2017-06-15 | 2017-07-15 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A
821 | PP | GRT-YQ01-P1UHA-155217 | 155217 | [HRSG] Lighting and Receptale Wiring Layout | FA | 2017-06-15 | 2017-07-15 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A
822 | PP | GRT-YQ01-P1UHA-155218 | 155218 | [HRSG] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-07-12 | 2017-07-12 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A
823 | PP | GRT-YD00-P1UHA-165219 | 165219 | [HRSG] Instrument Main Cable & JB Layout | FA | 2017-06-15 | 2017-07-15 | 2017-11-03 | GRT-PP-IP-DT-170306 | FC | 0 | 2017-11-03 | N.A | FC | 0 | A
824 | PP | GRT-CC03-P1UHA-175220 | 175220 | [HRSG] Foundation Plan | FA | 2017-03-25 | 2017-04-24 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A
825 | PP | GRT-CC03-P1UHA-175221 | 175221 | [HRSG] Foundation Detail (1/2) | FA | 2017-03-25 | 2017-04-24 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A
826 | PP | GRT-CC03-P1UHA-175222 | 175222 | [HRSG] Foundation Detail (2/2) | FA | 2017-03-25 | 2017-04-24 | 2017-05-26 | GRT-PP-IP-DT-170094 | FC | 0 | 2017-05-26 | N.A | FC | 0 | A
827 | PP | GRT-HM01-P0UMA-125233 | 0.12523 | [STG BUILDING] Steam Turbine Building HVAC Flow Schematic Diagram | FA | 2017-03-11 | 2017-04-10 | 2017-06-16 | GRT-PP-IP-DT-170119 | FC | 0 | 2017-06-16 | N.A | FC | 0 | A
828 | PP | GRT-HM01-P0UMA-125234 | 125234 | [STG BUILDING] Steam Turbine Building HVAC Ducting Layout | FA | 2017-03-11 | 2017-04-10 | 2017-03-30 | GRT-PP-IP-DT-170099 | FC | 0 | 2017-03-30 | N.A | FC | 0 | A
829 | PP | GRT-HM01-P0UMA-125235 | 125235 | [STG BUILDING] Steam Turbine Building HVAC Equipment Layout | FA | 2017-03-11 | 2017-04-10 | 2019-09-26 | GRT-PP-IP-DT-191407 | FC | 1 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 1 | A
830 | PP | GRT-HM01-P0UMA-125236 | 125236 | [STG BUILDING] Steam Turbine Building HVAC Elevation, Section & Detail | FA | 2017-03-11 | 2017-04-10 | 2019-09-26 | GRT-PP-IP-DT-191407 | FC | 1 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 1 | A
831 | PP | GRT-HM05-P0UMA-125237 | 125237 | [STG BUILDING] HVAC Calculation for Steam Turbine Generator Building | FA | 2017-06-20 | 2017-07-20 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A
832 | PP | GRT-YD16-P0UMA-155238 | 155238 | [STG BUILDING] Cable Tray & Power Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
833 | PP | GRT-YE07-P0UMA-155240 | 155240 | [STG BUILDING] Grounding Wiring Layout | FA | 2017-04-08 | 2017-05-08 | 2017-06-06 | GRT-PP-IP-DT-170110 | FC | 0 | 2017-06-06 | N.A | FC | 0 | A
834 | PP | GRT-YE07-P0UMA-155241 | 155241 | [STG BUILDING] Lightning Protection Layout | FA | 2017-04-08 | 2017-05-08 | 2019-09-26 | GRT-PP-IP-DT-191407 (DCR 00052) | FC | 0DCR1 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0DCR1 | A
835 | PP | GRT-YQ01-P0UMA-155242 | 155242 | [STG BUILDING] Lighting and Receptacle Wiring Layout | FA | 2017-04-08 | 2017-05-08 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
836 | PP | GRT-YQ01-P0UMA-155243 | 155243 | [STG BUILDING] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-07-12 | 2017-08-11 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
837 | PP | GRT-YD00-P0UMA-165244 | 165244 | [STG BUILDING] Instrument Main Cable & JB Layout | FA | 2017-07-06 | 2017-08-05 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A
838 | PP | GRT-CA00-P0UMA-175245 | 175245 | [STG BUILDING] Floor Plan, Roof Plan & Finishing Schedule | FA | 2017-03-04 | 2017-04-03 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00027) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | B
839 | PP | GRT-CA00-P0UMA-175246 | 175246 | [STG BUILDING] Architectural Door & Window Schedule | FA | 2017-06-05 | 2017-07-05 | 2017-11-17 | GRT-PP-IP-DT-170326 | FC | 2 | 2017-11-17 | DRM SEOUL 7-NOVEMBER-2017 | FA | C | A
840 | PP | GRT-CA01-P0UMA-175250 | 175250 | [STG BUILDING] Foundation Plan (1/2) | FA | 2017-03-07 | 2017-04-06 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
841 | PP | GRT-CA01-P0UMA-175251 | 175251 | [STG BUILDING] Condenser Foundation Detail | FA | 2017-03-07 | 2017-04-06 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
842 | PP | GRT-CA01-P0UMA-175252 | 175252 | [STG BUILDING] Basement Floor Plan, El +3.104,EL+2.604, EL.+0.544, EL-0.496, & El-1.150 ( T.O.C ) | FA | 2017-03-07 | 2017-04-06 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00029) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
843 | PP | GRT-CA01-P0UMA-175253 | 175253 | [STG BUILDING] Floor Plan EL. +.104 (T.O.C) | FA | 2017-06-05 | 2017-07-05 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00028) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FA | 1 | B
844 | PP | GRT-CA01-P0UMA-175254 | 175254 | [STG BUILDING] Foundation Framing Elevation | FA | 2017-03-07 | 2017-04-06 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
845 | PP | GRT-CA01-P0UMA-175259 | 175259 | [STG BUILDING] Location Foundation Plant and Detail | FA | 2017-06-05 | 2017-07-05 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 0 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | A | A
846 | PP | GRT-CA03-P0UMA-175260 | 175260 | [STG BUILDING] Steam Turbine Building Steel Structure Column Layout Plan | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
847 | PP | GRT-CA03-P0UMA-175261 | 175261 | [STG BUILDING] Steam Turbine Building Steel Structure Mezzanine Floor El +11.604 (F.F.L) | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
848 | PP | GRT-CA03-P0UMA-175262 | 175262 | [STG BUILDING] Steam Turbine Building Steel Structure Operating Floor El +17.104 (F.F.L) | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
849 | PP | GRT-CA03-P0UMA-175263 | 175263 | [STG BUILDING] Steam Turbine Building Steel Structure Roof Plan #1 | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
850 | PP | GRT-CA03-P0UMA-175264 | 175264 | [STG BUILDING] Steam Turbine Building Steel Structure Runway Girder El +28.604 (T.O.R) | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
851 | PP | GRT-CA03-P0UMA-175265 | 175265 | [STG BUILDING] Steam Turbine Building Steel Structure Roof Plan #2 | FA | 2017-03-07 | 2017-04-06 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00034) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
852 | PP | GRT-CA03-P0UMA-175266 | 175266 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SA0 & SA | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
853 | PP | GRT-CA03-P0UMA-175267 | 175267 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SB, SC & SE | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
854 | PP | GRT-CA03-P0UMA-175268 | 175268 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SD & SE | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
855 | PP | GRT-CA03-P0UMA-175269 | 175269 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line S8, S9 & S10 | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
856 | PP | GRT-CA03-P0UMA-175270 | 175270 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line S11 & S12 | FA | 2017-03-07 | 2017-04-06 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 1a | 2017-08-04 | N.A | FC | 1a | A
857 | PP | GRT-CA06-P0UMA-175271 | 175271 | [STG BUILDING] Calculation Sheet for Steel Structure and Foundation | FA | 2017-03-07 | 2017-04-06 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
858 | PP | GRT-CC03-P0UMA-175272 | 175272 | [STG ] Concrete Structure Foundation Plan & Section | FA | 2017-04-08 | 2017-05-08 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
859 | PP | GRT-CC03-P0UMA-175273 | 175273 | [STG BUILDING] Concrete Structure Framing Elevation | FA | 2017-04-08 | 2017-05-08 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
860 | PP | GRT-CC03-P0UMA-175274 | 175274 | [STG BUILDING] Foundation Elevation, Section and Detail (2/2) | FA | 2017-03-07 | 2017-04-06 | 2017-05-12 | GRT-PP-IP-DT-170079 | FC | 0 | 2017-05-19 | 0019.001/C.1.2.17.01/E04/PLNEV/2017 | FA | A | A
861 | PP | GRT-CC03-P0UMA-175277(1OF2) | 175277 | [STG ] Concrete structure Insert Plate Plant and Detail | FA | 2017-06-05 | 2017-05-07 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
862 | PP | GRT-CC03-P0UMA-175277(2OF2) | 175277 | [STG ] Concrete structure Insert Plate Plant and Detail | FA | 2017-06-05 | 2017-05-07 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
863 | PP | GRT-CC07-P0UMA-175278 | 175278 | [STG BUILDING] Calculation Sheet for Foundation | FA | 2017-04-08 | 2017-05-08 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
864 | PP | GRT-XG02-P0UGD-115279 | 115279 | [WTP] Piping and instrument diagram (PID) Raw Water System | FA | 2017-02-23 | 2017-03-25 | 2019-01-10 | GRT-PP-IP-DT-190929 | FC | 4 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 4 | A
865 | PP | GRT-XG02-P0UGD-115280 | 115280 | [WTP] Piping and instrument diagram (PID) Demin Make-up System | FA | 2017-02-23 | 2017-03-25 | 2019-01-10 | GRT-PP-IP-DT-190929 | FC | 4 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 4 | A
866 | PP | GRT-XG02-P0UGD-115281 | 115281 | [WTP] Piping and instrument diagram (PID) Water Treatment System | FA | 2017-02-21 | 2017-03-23 | 2018-12-20 | GRT-PP-IP-DT-170367 | FC | 0 | 2017-12-21 | N.A | FC | 0 | A
867 | PP | GRT-YT01-P0UGD-115282 | 115282 | [WTP] Process data sheet for raw water tank | FA | 2017-02-23 | 2017-03-25 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 1 | 2017-10-04 | N.A | FC | 1 | A
868 | PP | GRT-YT01-P0UGD-115283 | 115283 | [WTP] Process data sheet for make-up demin water tank | FA | 2017-02-23 | 2017-03-25 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 1 | 2017-10-17 | N.A | FC | 1 | A
869 | PP | GRT-YT01-P0UGD-115284 | 115284 | [WTP] Process data sheet for make up demin for closed cooling system pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
870 | PP | GRT-YT01-P0UGD-115285 | 115285 | [WTP] Process data sheet for Portable Water Pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
871 | PP | GRT-XG02-P0UGD-115286 | 115286 | [WTP] Piping and instrumentation Diagram for Auxiliary Service Water System | FA | 2017-02-21 | 2017-03-23 | 2017-11-30 | GRT-PP-IP-DT-170343 | FC | 1 | 2017-11-30 | N.A | FC | 1 | A
872 | PP | GRT-XG02-P0UGD-115287 | 115287 | [WTP] Piping and instrument diagram (PID) Service Water System | FA | 2017-02-21 | 2017-03-23 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 1 | 2017-10-17 | N.A | FC | 1 | A
873 | PP | GRT-YT01-P0UGD-115288 | 115288 | [WTP] Process data sheet for raw water pump | FA | 2017-02-21 | 2017-03-23 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
874 | PP | GRT-YT01-P0UGD-115289 | 115289 | [WTP] Process data sheet for service water pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
875 | PP | GRT-YT01-P0UGD-115290 | 115290 | [WTP] Process data sheet for sump pumps | FA | 2017-04-06 | 2017-05-06 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
876 | PP | GRT-XG02-P0UGD-115291 | 115291 | [WTP] Piping and Instrumentation Diagram for Interconnecting System | FA | 2017-02-21 | 2017-06-05 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 1 | 2017-10-31 | N.A | FC | 1 | A
877 | PP | GRT-XW03-P0UGD-115292 | 115292 | [WTP] Process calculation for service water pump | FA | 2017-02-23 | 2017-03-25 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
878 | PP | GRT-XW03-P0UGD-115293 | 115293 | [WTP] Process calculation for sump pumps | FA | 2017-04-06 | 2017-05-06 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
879 | PP | GRT-XW01-P0UGD-115294 | 115294 | [WTP] Process idividual specification for Water treatment system | FA | 2017-02-21 | 2017-03-23 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A
880 | PP | GRT-XW03-P0UGD-115295 | 115295 | [WTP] Process calculation for raw water tank | FA | 2017-06-10 | 2017-07-10 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
881 | PP | GRT-XW03-P0UGD-115296 | 115296 | [WTP] Process calculation for make-up demin water tank | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
882 | PP | GRT-XW03-P0UGD-115297 | 115297 | [WTP] Process calculation for make up demin system pump | FA | 2017-02-23 | 2017-03-25 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
883 | PP | GRT-XW03-P0UGD-115298 | 115298 | [WTP] Process calculation for auxiliary service water pump | FA | 2017-02-23 | 2017-03-25 | 2017-09-27 | GRT-PP-IP-DT-170242 | FC | 1 | 2017-09-27 | N.A | FC | 1 | A
884 | PP | GRT-XW03-P0UGD-115299 | 115299 | [WTP] Process calculation for raw water pump | FA | 2017-02-21 | 2017-03-23 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
885 | PP | GRT-YT01-P0UGD-125300 | 125300 | [WTP] Mech. Data Sheet for Make-up Demin Water Tank | FA | 2017-06-23 | 2017-07-23 | 2017-10-06 | GRT-PP-IP-DT-170257 | FC | 0 | 2017-10-06 | N.A | FC | 0 | A
886 | PP | GRT-YT01-P0UGD-125301 | 125301 | [WTP] Mech. Data Sheet for Make up Demin for Closed Cooling System Pump | FA | 2017-03-02 | 2017-04-01 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | B | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | B | B
887 | PP | GRT-YT01-P0UGD-125451 | 125451 | [WTP] Mech. Data Sheet for Portable Water Pump | FA | 2017-02-28 | 2017-03-30 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | B | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | B | B
888 | PP | GRT-YT01-P0UGD-125303 | 125303 | [WTP] Mech. Data Sheet for Raw Water Tank | FI | 2017-06-12 | 2017-07-12 | 2017-10-16 | GRT-PP-IP-DT-170270 | FI | A | 2017-10-19 | 019.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
889 | PP | GRT-YT01-P0UGD-125304 | 125304 | [WTP] Mech. Data Sheet for Service Water Pump | FA | 2017-03-02 | 2017-04-01 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | B | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | B | B
890 | PP | GRT-YT01-P0UGD-125305 | 125305 | [WTP] Mech. Data Sheet for Sump Pumps | FA | 2017-04-13 | 2017-05-13 | 2017-07-25 | GRT-PP-IP-DT-170154 | FC(D) | C | 2017-08-01 | 0001.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | C | B
891 | PP | GRT-CC00-P0UGD-145306 | 145306 | [WTP] Piping Layout Drawing for Water Treatment Area | FA | 2017-02-28 | 2017-03-30 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | A
892 | PP | GRT-CC00-P0UGD-145307 | 145307 | [WTP] Piping Layout Drawing Demin Water Area | FA | 2017-06-23 | 2017-07-23 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
893 | PP | GRT-CC00-P0UGD-145308 | 145308 | [WTP] Piping Layout Drawing Demin to HRSG Area | FA | 2017-03-02 | 2017-04-01 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
894 | PP | GRT-YD16-P0UGD-155309 | 155309 | [WTP] Cable Tray and Power Wiring Layout | FA | 2017-03-22 | 2017-04-21 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 1 | 2017-08-22 | N.A | FC | 1 | A
895 | PP | GRT-YE07-P0UGD-155310 | 155310 | [WTP] Grounding Wiring Layout | FA | 2017-03-22 | 2017-04-21 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
896 | PP | GRT-YE07-P0UGD-155311 | 155311 | [WTP] Lightning Protection Layout | FA | 2017-03-22 | 2017-04-21 | 2019-09-19 | GRT-PP-IP-DT-191389 (DCR 0040) | FC | 0DCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0DCR2 | A
897 | PP | GRT-YQ01-P0UGD-155312 | 155312 | [WTP] Lighting and Receptacle Wiring Layout | FA | 2017-03-22 | 2017-04-21 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0DCR2 | A
898 | PP | GRT-YQ01-P0UGD-155313 | 155313 | [WTP] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-03-22 | 2017-04-21 | 2017-09-22 | GRT-PP-IP-DT-170236 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
899 | PP | GRT-CV03-P0UGD-165314 | 165314 | [WTP] Instrument Data sheet for Potable Water System | FA | 2017-03-02 | 2017-04-01 | 2018-03-19 | GRT-PP-IP-DT-180471 | FC | 0 | 2018-03-21 | Stempel Approved | FC | 0 | A
900 | PP | GRT-CV03-P0UGD-165315 | 165315 | [WTP] Instrument Data Sheet for Raw Water System | FA | 2017-03-02 | 2017-04-01 | 2017-05-10 | GRT-PP-IP-DT-170077 | FC | 0 | 2017-05-15 | N.A | FC | 0 | A
901 | PP | GRT-CV03-P0UGD-165316 | 165316 | [WTP] Instrument Data Sheet for Demin Make up System | FA | 2017-03-03 | 2017-04-02 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A
902 | PP | GRT-CV03-P0UGD-165317 | 165317 | [WTP] Instrument Data Sheet for Service Water System | FA | 2017-06-02 | 2017-07-02 | 2017-10-20 | GRT-PP-IP-DT-170280 | FC | 0 | 2017-10-23 | N.A | FC | 0 | A
903 | PP | GRT-YD00-P0UGD-165318 | 165318 | [WTP] Instrument Location Plan Layout for Potable Water System | FA | 2017-03-16 | 2017-04-15 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
904 | PP | GRT-YD00-P0UGD-165319 | 165319 | [WTP] Instrument Main Cable & JB Layout for Potable Water System | FA | 2017-03-22 | 2017-04-21 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
905 | PP | GRT-YD00-P0UGD-165320 | 165320 | [WTP] Instrument Cable Wiring Layout for Raw Water System | FA | 2017-03-29 | 2017-04-28 | 2017-08-01 | GRT-PP-IP-DT-170164 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A
906 | PP | GRT-YD00-P0UGD-165321 | 165321 | [WTP] Instrument Location Plan Layout for Raw Water System | FA | 2017-07-07 | 2017-08-06 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
907 | PP | GRT-YD00-P0UGD-165322 | 165322 | [WTP] Instrument Location Plan Layout for Service Water System | FA | 2017-03-16 | 2017-04-15 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
908 | PP | GRT-YD00-P0UGD-165323 | 165323 | [WTP] Instrument Main Cable & JB Layout for Raw Water System | FA | 2017-03-22 | 2017-04-21 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
909 | PP | GRT-YD00-P0UGD-165324 | 165324 | [WTP] Instrument Main Cable & JB Layout for Service Water System | FA | 2017-03-22 | 2017-04-21 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
910 | PP | GRT-YD00-P0UGD-165325 | 165325 | [WTP] Instrument Cable Wiring Layout for Potable Water System | FA | 2017-03-29 | 2017-04-28 | 2017-08-01 | GRT-PP-IP-DT-170164 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A
911 | PP | GRT-YD00-P0UGD-165326 | 165326 | [WTP] Instrument Cable Wiring Layout for Water Treatment System | FA | 2017-03-29 | 2017-04-28 | 2017-08-01 | GRT-PP-IP-DT-170164 | FC | 0 | 2017-08-01 | N.A | FC | 0 | A
912 | PP | GRT-YD00-P0UGD-165327 | 165327 | [WTP] Instrument Location Plan Layout for Water Treatment System | FA | 2017-03-16 | 2017-04-15 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
913 | PP | GRT-YD00-P0UGD-165328 | 165328 | [WTP] Instrument Main Cable & JB Layout for Water Treatment System | FA | 2017-03-22 | 2017-04-21 | 2017-07-07 | GRT-PP-IP-DT-170133 | FC | 0 | 2017-07-07 | N.A | FC | 0 | A
914 | PP | GRT-YL01-P0UGD-165333 | 165333 | [DCS] I/O List for Demin Makeup System | FA | 2017-02-28 | 2017-08-16 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A
915 | PP | GRT-YL01-P0UGD-165334 | 165334 | [DCS] I/O List for Raw Water System | FA | 2017-02-28 | 2017-03-30 | 2017-11-13 | GRT-PP-IP-DT-170314 | FC | 0 | 2017-11-13 | N.A | FC | 0 | A
916 | PP | GRT-YL01-P0UGD-165335 | 165335 | [DCS] I/O List for Service Water System | FA | 2017-02-28 | 2017-03-30 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FA | 0 | A
917 | PP | GRT-YL01-P0UGD-165336 | 165336 | [DCS] I/O List for Auxiliary Service Water System | FA | 2017-02-28 | 2017-03-30 | 2017-10-05 | GRT-PP-IP-DT-170254 | FC(D) | C | 2017-10-17 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | C | A
918 | PP | GRT-YS02-P0UGD-165341 | 165341 | [WTP] Instrument Termination Diagram for Potable Water System | FA | 2017-07-07 | 2017-08-06 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
919 | PP | GRT-YS02-P0UGD-165342 | 165342 | [WTP] Instrument Termination Diagram for Raw Water System | FA | 2017-07-07 | 2017-08-06 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
920 | PP | GRT-YS02-P0UGD-165343 | 165343 | [WTP] Instrument Termination Diagram for Water Treatment System | FA | 2017-07-07 | 2017-08-06 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
921 | PP | GRT-YS02-P0UGD-165344 | 165344 | [WTP] Instrument Termination Diagram for Service Water System | FA | 2017-07-07 | 2017-08-06 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
922 | PP | GRT-CA00-P0UGD-175345 | 175345 | [WTP] Water Treatment Plant Architectural Plan, View, Section & Finishing Schedule | FA | 2017-03-15 | 2017-04-14 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A
923 | PP | GRT-CA00-P0UGD-175346 | 175346 | [WTP] Architectural door & Window key Plant and Schedule | FA | 2017-06-12 | 2017-07-12 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
924 | PP | GRT-CA01-P0UGD-175347 | 175347 | [WTP] Foundation Plan | FA | 2017-03-22 | 2017-04-21 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A
925 | PP | GRT-CA01-P0UGD-175348 | 175348 | [WTP] Concrete Structure Floor Plan, Section & Member Schedule | FA | 2017-03-22 | 2017-04-21 | 2017-07-25 | GRT-PP-IP-DT-170155 | FC | 0 | 2017-07-25 | N.A | FC | 0 | A
926 | PP | GRT-CA03-P0UGD-175349 | 175349 | [WTP] Steel Structure Framing Plan | FA | 2017-03-22 | 2017-04-21 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A
927 | PP | GRT-CA03-P0UGD-175350 | 175350 | [WTP] Steel Structure Framing Elevation and Detail | FA | 2017-06-23 | 2017-07-23 | 2017-06-05 | GRT-PP-IP-DT-170107 | FC | 0 | 2017-06-05 | N.A | FC | 0 | A
928 | PP | GRT-CC03-P0UGD-175352 | 175352 | [WTP] Make Up Closed Cooling Foundation | FA | 2017-06-23 | 2017-07-23 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B
929 | PP | GRT-CC03-P0UGD-175353 | 175353 | [WTP] Make Up Demin for Deaerator Pump Foundation | FA | 2017-06-23 | 2017-07-23 | 2018-12-21 | GRT-PP-IP-DT-180910 | FC | 1 | 2019-01-15 | Comment Sheet IP | FC | 1 | A
930 | PP | GRT-CC03-P0UGD-175354 | 175354 | [WTP] Service Water Pump Foundation | FA | 2017-06-23 | 2017-07-23 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B
931 | PP | GRT-CC03-P0UGD-175355 | 175355 | [WTP] Raw Water Tank Pump Foundation | FA | 2017-06-23 | 2017-07-23 | 2017-12-18 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B
932 | PP | GRT-CC03-P0UGD-175357 | 175357 | Sum Pit at STG Area Foundation Plan, Section and Detail | FA | 2017-06-23 | 2017-07-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
933 | PP | GRT-YD16-P0UAG-155358 | 155358 | [Transformer] Cable Tray and Power Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 1 | 2017-10-24 | N.A | FC | 1 | A
934 | PP | GRT-YE06-P0UAG-155359 | 155359 | [Transformer] Grounding Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
935 | PP | GRT-YE06-P0UAG-155360 | 155360 | [Transformer] Lightning Protection Layout | FA | 2017-06-23 | 2017-07-23 | 2017-08-21 | GRT-PP-IP-DT-170187 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
936 | PP | GRT-YQ01-P0UAG-155361 | 155361 | [Transformer] Lighting and Receptale Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
937 | PP | GRT-YQ01-P0UAG-155362 | 155362 | [Transformer] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-06-20 | 2017-07-20 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
938 | PP | GRT-CC03-P0UAG-175363 | 175363 | [Transformer] FOUNDATION PLAN, PLAN EL. +5.672 (T.O.S) SECTION, DETAIL & MEMBER SCHEDULE | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
939 | PP | GRT-CC03-P0UAG-175364 | 175364 | [Transformer] Section Detail | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
940 | PP | GRT-CC03-P0UAG-175365 | 175365 | [Transformer] Foundation Detail | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
941 | PP | GRT-CC07-P0UAG-175366 | 175366 | [Transformer] Calculation Sheet for Foundation | FA | 2017-06-20 | 2017-07-20 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
942 | PP | GRT-YD16-P0UAA-155367 | 155367 | [Switchyard] Cable Tray and Power Wiring Layout | FA | 2017-06-19 | 2017-07-19 | 2017-09-13 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A
943 | PP | GRT-YQ01-P0UAA-155369 | 155369 | [Switchyard] Lighting and Receptale Wiring Layout | FA | 2017-06-19 | 2017-07-19 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
944 | PP | GRT-YQ01-P0UAA-155370 | 155370 | [Switchyard] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-06-19 | 2017-07-19 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
945 | PP | GRT-YW06-P0UAA-155371 | 155371 | [Switchyard] Grounding Wiring Layout | FA | 2017-06-23 | 2017-07-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
946 | PP | GRT-CC03-P0UAA-175372 | 175372 | [Switchyard] Foundation Layout | FA | 2017-06-23 | 2017-07-23 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00026) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
947 | PP | GRT-CC03-P0UAA-175373 | 175373 | [Switchyard] Type 1 Foundation Plan, Section & Detail | FA | 2017-06-23 | 2017-07-23 | 2017-11-30 | GRT-PP-IP-DT-170343 | FC | 0 | 2017-11-30 | N.A | FC | 0 | A
948 | PP | GRT-CC07-P0UAA-175376 | 175376 | [Switchyard] Calculation Sheet for Foundation | FA | 2017-07-07 | 2017-07-06 | 2017-11-30 | GRT-PP-IP-DT-170343 | FC | 0 | 2017-11-30 | N.A | FC | 0 | A
949 | PP | GRT-CE00-P0SG-115377 | 115377 | [Fire Fighting System] Lay out fire protection equipment | FA | 2017-07-07 | 2017-07-06 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0017) | FC | 1 | 2019-01-15 | Comment Sheet IP | FC |  | A
950 | PP | GRT-CE00-P0SG-115378 | 115378 | [Fire Fighting System] Escape route lay out | FA | 2017-07-07 | 2017-07-06 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
951 | PP | GRT-YT01-P0SG-115379 | 115379 | [Fire Fighting System] Process data sheet for Jockey Pump | FA | 2017-07-07 | 2017-07-06 | 2017-04-18 | GRT-PP-IP-DT-170047 | FC | 0 | 2017-04-21 | 0021.001/C.1.2.17.01/E04/PLNE/IV/2017 | FC | 0 | I
952 | PP | GRT-YT01-P0SG-115380 | 115380 | [Fire Fighting System] Process data sheet for Fire Water Pump | FA | 2017-07-07 | 2017-07-06 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
953 | PP | GRT-YT01-P0SG-115381 | 115381 | [Fire Fighting System] Datasheet for Fire Protection Equipment | FA | 2017-03-20 | 2017-04-19 | 2017-11-27 | GRT-PP-IP-DT-170339 | FC | 0 | 2017-11-27 | N.A | FC | 0 | A
954 | PP | GRT-XG02-P0SG-115382 | 115382 | [Fire Fighting System] Piping & Instrument Diagram for firewater system | FA | 2017-03-20 | 2017-04-19 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00023) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
955 | PP | GRT-XG08-P0SG-115383 | 115383 | [Fire Fighting System] Utility Flow Diagram Fire water system | FA | 2017-03-20 | 2017-04-19 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
956 | PP | GRT-XW01-P0SG-115384 | 115384 | [Fire Fighting System] Fire Protection Design Basis | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
957 | PP | GRT-XW01-P0SG-115385 | 115385 | [Fire Fighting System] Fire Design Basis | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
958 | PP | GRT-XW01-P0SG-115386 | 115386 | [Fire Fighting System] Specification for Fire Protection Equipment | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
959 | PP | GRT-XW03-P0SG-115387 | 115387 | [Fire Fighting System] Process Calculation for Jockey Pump | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
960 | PP | GRT-XW03-P0SG-115388 | 115388 | [Fire Fighting System] Process Calculation for Fire Water Pump | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
961 | PP | GRT-XW03-P0SG-115389 | 115389 | [Fire Fighting System] Process Calculation for Fire Water Consumption | FA | 2017-03-20 | 2017-04-19 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
962 | PP | GRT-XW03-P0SG-115390 | 115390 | [Fire Fighting System] Fire Water Hydraulic Calculation | FA | 2017-03-20 | 2017-04-19 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
963 | PP | GRT-YT01-P0SG-125391 | 125391 | [Fire Fighting System] Mech. Data Sheet for Jockey Pump | FA | 2017-03-27 | 2017-04-26 | 2017-10-06 | GRT-PP-IP-DT-170257 | FC | 0 | 2017-10-06 | N.A | FC | 0 | A
964 | PP | GRT-YT01-P0SG-125392 | 125392 | [Fire Fighting System] Mech. Data Sheet for Fire Water Pump | FA | 2017-03-27 | 2017-04-26 | 2017-10-06 | GRT-PP-IP-DT-170257 | FC | 0 | 2017-10-06 | N.A | FC | 0 | A
965 | PP | GRT-YD16-P0UGD-155393 | 155393 | [Fire Fighting Shelter] Cable Tray and Power Wiring Layout | FA | 2017-07-14 | 2017-08-13 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 0 | 2017-09-08 | N.A | FC | 0 | A
966 | PP | GRT-YE07-P0UGD-155394 | 155394 | [Fire Fighting Shelter] Grounding Wiring Layout | FA | 2017-07-14 | 2017-08-13 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 0 | 2017-09-08 | N.A | FC | 0 | A
967 | PP | GRT-YE07-P0UGD-155395 | 155395 | [Fire Fighting Shelter] Lightning Protection Layout | FA | 2017-07-14 | 2017-08-13 | 2019-09-19 | GRT-PP-IP-DT-191389 (DCR 0040) | FC | 0DCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC |  | A
968 | PP | GRT-YQ01-P0UGD-155396 | 155396 | [Fire Fighting Shelter] Lighting and Receptale Wiring Layout | FA | 2017-07-14 | 2017-08-13 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0 | A
969 | PP | GRT-YQ01-P0UGD-155397 | 155397 | [Fire Fighting Shelter] Lighting and Receptacle Panel Schedule and Connection Diagram | FA | 2017-07-07 | 2017-08-13 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
970 | PP | GRT-CA01-P0UGD-175399 | 175399 | [Fire Fighting Shelter] Foundation, Foundation Plan & Detail | FA | 2017-07-14 | 2017-08-13 | 2019-06-28 | GRT-PP-IP-DT-191235 (DCR 00048) | FC | 1 | 2019-07-19 | 040/061/GRT/UPR/2019 |  | 1 | B
971 | PP | GRT-CA03-P0UGD-175400 | 175400 | [Fire Fighting Shelter] Steel Structure Framing Plan & Elevation | FA | 2017-07-14 | 2017-08-13 | 2017-08-08 | GRT-PP-IP-DT-170175 | FC | 0 | 2017-08-08 | N.A | FC | 0 | A
972 | PP | GRT-CA06-P0UGD-175401 | 175401 | [Fire Fighting Shelter] Calculation Sheet for Fire Fighting Shelter Stricture and Foundation | FA | 2017-07-14 | 2017-08-13 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
973 | PP | GRT-YD16-P0UCA-155408 | 155408 | [Control Building] Cable Tray and Power Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 1 | 2017-11-21 | N.A | FC | 1 | A
974 | PP | GRT-YE00-P0UCA-155409 | 155409 | [Electrical Room] Clock System Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-31 | GRT-PP-IP-DT-170293 | FC | 0 | 2017-10-31 | N.A | FC | 0 | A
975 | PP | GRT-YE07-P0UCA-155410 | 155410 | [Electrical Room] Grounding Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-09-18 | GRT-PP-IP-DT-170230 | FC | 0 | 2017-09-18 | N.A | FC | 0 | A
976 | PP | GRT-YM02-P0UCA-155411 | 155411 | [Electrical Room] Electrical Equipment Layout | FA | 2017-07-16 | 2017-08-06 | 2019-11-13 | GRT-PP-IP-DT-191482 | FC | 3 | 2019-11-29 | 057/061/GRT/UPR/2019 |  | 3 | A
977 | PP | GRT-YM02-P0UCA-155412 | 155412 | Electrical Room Section & Detail Cable Tray Layout | FA | 2017-06-14 | 2017-07-14 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 1 | 2017-11-21 | N.A | FC | 1 | A
978 | PP | GRT-YD16-P0UBN-155413 | 155413 | [Engine Diesel Generator] Cable Tray and Power Wiring Layout | FA | 2017-06-14 | 2017-07-14 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 1 | 2017-10-24 | N.A | FC | 1 | A
979 | PP | GRT-CC07-P0UZA-175420 | 175420 | [Structure for Transport, Trafic & Other Purpose] Calculation for Sheet Pile and Concrete Batter Pile for Thermal Barier | FA | 2017-07-14 | 2017-08-13 | 2017-08-16 | GRT-PP-IP-DT-170183 | FC | 0 | 2017-08-16 | N.A | FC | 0 | A
980 | PP | GRT-CC03-P0UZA-175421 | 175421 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pilling Plan and List | FA | 2017-07-14 | 2017-08-13 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A
981 | PP | GRT-CC03-P0UZA-175422 | 175422 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Layout | FA | 2017-07-14 | 2017-08-13 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A
982 | PP | GRT-CC03-P0UZA-175423 | 175423 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Cross Section | FA | 2017-07-14 | 2017-08-13 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A
983 | PP | GRT-CC03-P0UZA-175424(1OF2) | 175424 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pile Cap, Plan, Long Section and Detail | FA | 2017-02-28 | 2017-03-30 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A
984 | PP | GRT-CC03-P0UZA-175424(2OF2) | 175424 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pile Cap Rebar Arrangement and Section | FA | 2017-02-28 | 2017-03-30 | 2017-08-04 | GRT-PP-IP-DT-170168 | FC | 0 | 2017-08-04 | N.A | FC | 0 | A
985 | PP | GRT-CC03-P0UZA-175425 | 175425 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan and Detail (1/8) | FA | 2017-07-20 | 2017-03-30 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | A
986 | PP | GRT-CC03-P0UZA-175426 | 175426 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | FA | 2017-07-20 | 2017-03-30 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | 2019-05-24 | DRM_22-24MAY2019 (DCR 0042) | FC | 1 | A
987 | PP | GRT-CC03-P0UZA-175427 | 175427 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | FA | 2017-07-20 | 2017-03-30 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A
988 | PP | GRT-CC03-P0UZA-175428 | 175428 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | FA | 2017-07-20 | 2017-03-30 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A
989 | PP | GRT-CC07-P0UZA-175429 | 175429 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Calculation Sheet | FA | 2017-07-30 | 2017-08-19 | 2017-08-18 | GRT-PP-IP-DT-170184 | FC | 0 | 2017-08-22 | 022.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FA | A | B
990 | PP | GRT-CC07-P0UZA-175430 | 175430 | [Structure for Transport, Trafic & Other Purpose] CALCULATION SHEET FOR LOCAL FOUNDATION AND PIPE SLEEPER | FA | 2017-07-30 | 2017-08-19 | 2017-11-22 | GRT-PP-IP-DT-170334 | FC | 0 | 2017-11-22 | N.A | FC | 0 | A
991 | PP | GRT-CC09-P0UZA-175447 | 175447 | [Structure for Transport, Trafic & Other Purpose] Calculation Sheet for Piperack Structure | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
992 | PP | GRT-CC09-P0UZA-175448(1OF2) | 175448 | [Structure for Transport, Trafic & Other Purpose] Pipe Rack Foundation Plan & Grade Beam Schedule | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
993 | PP | GRT-CC09-P0UZA-175448(2OF2) | 175448 | [Structure for Transport, Trafic & Other Purpose] Pipe Rack Foundation Detail | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
994 | PP | GRT-CC09-P0UZA-175449(1OF5) | 175449 | PIPERACK STEEL STRUCTURE COLUMN ARRANGEMENT & MEMBER SCHEDULE | FA | 2017-07-30 | 2017-08-29 | 2019-08-15 | GRT-PP-IP-DT-191312 (DCR 00049) | FC | 1 | 2019-08-22 | 045/061/GRT/UPR/2019 | FC | 1 | B
995 | PP | GRT-CC09-P0UZA-175449(2OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 10.604 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
996 | PP | GRT-CC09-P0UZA-175449(3OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 14.604 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
997 | PP | GRT-CC09-P0UZA-175449(4OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 15.604 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
998 | PP | GRT-CC09-P0UZA-175449(5OF5) | 175449 | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 17.304 (T.O.S) | FA | 2017-07-30 | 2017-08-29 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
999 | PP | GRT-CC09-P0UZA-175450(1OF3) | 175450 | PIPE RACK STEEL STRUCTURE PLAN EL. +19.004(T.O.S) & FRAMING ELEVATION LINE | FA | 2017-05-01 | 2017-05-31 | 2017-08-22 | GRT-PP-IP-DT-170190 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
1000 | PP | GRT-CC09-P0UZA-175450(2OF3) | 175450 | PIPE RACK STEEL STRUCTURE ELEVATION LINE SAD -5 & SAD-6 | FA | 2017-05-01 | 2017-05-31 | 2019-09-13 | GRT-PP-IP-DT-191376 (DCR 00050) | FC | 1 | 2019-09-27 | 053/061/GRT/UPR/2019 |  | 1 | A
1001 | PP | GRT-CC09-P0UZA-175450(3OF3) | 175450 | PIPE RACK STEEL STRUCTURE ELEVATION LINE S8-A & S8-B | FA | 2017-05-01 | 2017-05-31 | 2019-08-15 | GRT-PP-IP-DT-191312 (DCR 00049) | FC | 1 | 2019-08-22 | 045/061/GRT/UPR/2019 | FC | 1 | B
1002 | PP | GRT-CA06-P0UGD-175351 | 175351 | Calculation Sheet for Water Treatment Plant Building Structure and Foundation | FA | 2017-06-05 | 2017-07-05 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
1003 | PP | GRT-CA07-P0ZEN-179029 | 179029 | Study Thermal Barrier and Sedimentation | FA | 2017-06-05 | 2017-07-05 | 2017-06-19 | GRT-PP-IP-DT-170123 | FC | 1 | 2017-06-22 | 0022.001/C.1.2.17.01/E04/PLNE/VI/2017 | FC | 1 | I
1004 | PP | GRT-CC03-P0UGD-175581 | 175581 | Sump Pit at HRSG Area Foundation Plan, Section and Detail | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
1005 | PP | GRT-CC07-P0ZEN-175582 | 175582 | Calculation Sheet for Sump Pit | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
1006 | PP | GRT-CC07-P0UMA-175583 | 175583 | Calculation Sheet for Equipment Foundation on STG Building Grounding Floor | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1007 | PP | GRT-CC03-P0UMA-175584 | 175584 | Steam Turbine Building ACW & CCW Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1008 | PP | GRT-CC03-P0UMA-175585 | 175585 | Steam Turbine Building Condenser Vacuum pump & Air Compressore Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1009 | PP | GRT-CC03-P0UMA-175586 | 175586 | Steam Turbine Building Air Dryer & Air Reciver Tank Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1010 | PP | GRT-CC03-P0UMA-175587 | 175587 | Steam Turbine Building HP Feedwater Pump & LP feedwater Pump Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1011 | PP | GRT-CC03-P0UMA-175588 | 175588 | Steam Turbine Building Chemical Dosing System Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1012 | PP | GRT-CC03-P0UMA-175589 | 175589 | Steam Turbine Building Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1013 | PP | GRT-CC03-P0UMA-175590 | 175590 | Steam Turbine Building Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | B
1014 | PP | GRT-CC03-P0UMA-175591 | 175591 | Steam Turbine Building Foundation Detail | FA | 2017-10-11 | 2017-11-10 | 2017-10-11 | GRT-PP-IP-DT-170264 | FC | 0 | 2017-10-11 | 0017.001/C.1.2.17.01/E04/PLNE/X/2017 | FA | A | A
1015 | PP | GRT-DN06-P0ZEN-145458 | 145458 | [Piping General] Piping Pressure Test Procedure | FA | 2017-06-05 | 2017-07-05 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
1016 | PP | GRT-CC00-P0ZEN-145452 | 145452 | Drawing Index Balance of Plant BOP | FA | 2017-10-09 | 2017-10-09 | 2017-10-09 | GRT-PP-IP-DT-170259 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1017 | PP | GRT-CC00-P0UMA-145453-1 | 145453 | Piping Layout Drawing Steam Turbine Generator Area | FA | 2017-09-13 | 2017-09-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A
1018 | PP | GRT-CC00-P0UMA-145453-2 | 145453 | Piping Layout Drawing Steam Turbine Generator Area | FA | 2017-09-13 | 2017-09-13 | 2017-09-13 | GRT-PP-IP-DT-170218 | FC | 0 | 2017-09-13 | N.A | FC | 0 | A
1019 | PP | GRT-CC00-P1UHA-145454 | 145454 | Piping Layout Drawing for HRSG Area | FA | 2017-10-19 | 2017-10-19 | 2017-10-19 | GRT-PP-IP-DT-170277 | FC | 0 | 2017-10-23 | N.A | FC | 0 | A
1020 | PP | GRT-YT001-P0ZEN-145626 | 145626 | Data Sheet for Check Valve | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1021 | PP | GRT-YT001-P0ZEN-145427 | 145427 | General Arrangement for Check Valve | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1022 | PP | GRT-YT001-P0ZEN-145628 | 145628 | Data Sheet for Butterfly MOV Valve | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1023 | PP | GRT-YT001-P0ZEN-145548 | 145548 | General Arrangement Butterfly MOV Valve | FA | 2017-11-20 | 2017-11-20 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
1024 | PP | GRT-YT001-P0ZEN-145547 | 145547 | Valve Closing Time Calculation Sheet | FA | 2017-10-16 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1025 | PP | GRT-HM05-P0UGD-125452 | 125452 | HVAC Calculation for Water Treatment Building | FA | 2017-10-04 | 2017-10-04 | 2017-10-04 | GRT-PP-IP-DT-170249 | FC | 0 | 2017-10-04 | N.A | FC | 0 | A
1026 | PP | GRT-YD00-P0GAD-125624 | 125624 | General Arrangement Circulating Water Pump | FA | 2017-11-20 | 2017-11-20 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
1027 | PP | GRT-FF01-P0SGC-125440 | 125440 | Water Spray Layout for Transformer | FI | 2017-11-28 | 2017-12-28 | 2019-06-28 | GRT-PP-IP-DT-191236 (DCR 00043) | FC | 0DCR1 | 2019-07-19 | 040/061/GRT/UPR/2019 |  | 0DCR1 | B
1028 | PP | GRT-FF03-P0SGM-125442 | 125442 | Fire Suppression/FM/200 Layout | FI | 2017-11-28 | 2017-12-28 | 2017-11-28 | GRT-PP-IP-DT-170342 | FI | A | 2017-12-22 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I
1029 | PP | GRT-FF04-P0SGM-125443 | 125443 | Fire Suppression/FM/200 Isometric | FI | 2017-11-28 | 2017-12-28 | 2017-11-28 | GRT-PP-IP-DT-170342 | FI | A | 2017-12-22 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I
1030 | PP | GRT-FF04-P0SGM-125445 | 125445 | Technical Data Sheet FM200 | FI | 2017-11-28 | 2017-12-28 | 2017-11-28 | GRT-PP-IP-DT-170342 | FI | A | 2017-12-22 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I
1031 | PP | GRT-XW03-P0PAC-115135 | 115135 | [Circulating Water Pump] Process calculation for sea water for closed cooling system booster pump | FA | 2017-02-07 | 2017-03-09 | 2017-09-25 | GRT-PP-IP-DT-170239 | FC | 0 | 2017-09-25 | N.A | FC | 0 | A
1032 | PP | GRT-XG02-P0UGD-115469-1 | 115469 | P & ID For Waste Water Transfer System ( 1 of 2 ) | FA | 2017-06-12 | 2017-07-12 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1033 | PP | GRT-XG02-P0UGD-115469-2 | 115469 | P & ID For Waste Water Transfer System ( 2 of 2 ) | FA | 2017-06-12 | 2017-07-12 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1034 | PP | GRT-XW03-P1UHA-115456 | 115456 | [WTP] Process calculation for blowdown transfer pump | FA | 2017-08-18 | 2017-08-18 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
1035 | PP | GRT-YT01-P1UHA-115457 | 115457 | [WTP] Process data sheet for blowdown transfer pump | FA | 2017-08-18 | 2017-08-18 | 2017-08-18 | GRT-PP-IP-DT-170185 | FC | 0 | 2017-08-22 | N.A | FC | 0 | A
1036 | PP | GRTH-YR01-P0ZEN-115017 | 115017 | Procedure for Hazop Study | FI | 2017-06-09 | 2017-07-09 | 2017-06-09 | GRT-PP-IP-DT-170117 | FI | A | 2017-06-16 | 0016.001/C.1.2.17.01/E04/PLNE/VI/2017 | FI | A | I
1037 | PP | GRTH-YR01-P0ZEN-115471 | 115471 | Hazop Study Report | FI | 2017-06-12 | 2017-07-12 | 2017-06-09 | GRT-PP-IP-DT-170117 | FI | A | 2017-06-16 | 0016.001/C.1.2.17.01/E04/PLNE/VI/2017 | FI | A | I
1038 | PP | GRT-DC01-P0GDN-125913 | 125913 | Data Sheet Sea Water Booster Pump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1039 | PP | GRT-DC01-P0GDN-125914 | 125914 | Data Sheet Sea Water Strainer | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1040 | PP | GRT-DC01-P0GDN-125915 | 125915 | Data Sheet Electrolyzer | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1041 | PP | GRT-DC01-P0GDN-125916 | 125916 | Data Sheet Acid Cleaning Pump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1042 | PP | GRT-DC01-P0GDN-125917 | 125917 | Data Sheet Dilunation air Blower | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1043 | PP | GRT-DC01-P0GDN-125918 | 125918 | Data Sheet Continuos Dosing Pump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1044 | PP | GRT-DC01-P0GDN-125919 | 125919 | Data Sheet Shock DosingPump | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1045 | PP | GRT-YT02-P0GD-165921 | 165921 | Data sheet Pressure Indicator | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1046 | PP | GRT-YT02-P0GD-165922 | 165922 | Data Sheet Flow Transmitter | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1047 | PP | GRT-YT02-P0GD-165923 | 165923 | Data Sheet Level Transmitter | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1048 | PP | GRT-YT02-P0GD-165924 | 165924 | Data sheet Clorination Analyzer | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1049 | PP | GRT-YT02-P0GD-165925 | 165925 | Data Sheet Pressure Switch | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1050 | PP | GRT-YT02-P0GD-165926 | 165926 | Data Sheet Pressure Diffrential | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1051 | PP | GRT-YT02-P0GD-165927 | 165927 | Data Sheet Flow Indicator | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1052 | PP | GRT-YT02-P0GD-165928 | 165928 | Data Sheet Level Switch Electrochlorination | FI | 2017-09-15 | 2017-10-15 | 2017-09-15 | GRT-PP-IP-DT-170227 | FI | B | 2017-10-03 | 0003.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | B | A
1053 | PP | GRT-YT02-P0GD-165929 | 165929 | Data Sheet Temperatur Transmitter | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-24 | 0024.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | A
1054 | PP | GRT-CC08-P0GAC-135930 | 135930 | Equipment Lay out | FI | 2017-09-14 | 2017-10-14 | 2019-04-25 | GRT-PP-IP-DT-191151 | FI | 0 | 2019-05-09 | 029/061/GRT/UPR/2019 | FI | 0 | A
1055 | PP | GRT-XB02-P0GAC-135931 | 135931 | Foundation Layout ELECTROCHLORINATION | FI | 2017-07-21 | 2017-08-20 | 2018-08-30 | GRT-PP-IP-DT-180752 (DCR 00010) | FC | 1 | 2018-09-14 | 14.006/E04/PLNE/IX/2018 |  | 1 | A
1056 | PP | GRT-XG07-P0GAC-135936 | 135936 | PFD | FI | 2017-07-21 | 2017-08-20 | 2019-11-29 | MINI DRM 28-29NOV19 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 0 | A
1057 | PP | GRT-XG02-P0GAC-135937 | 135937 | P & ID | FI | 2017-10-13 | 2017-11-12 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00038) | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1058 | PP | GRT-DC01-P0LDF-125815 | 125815 | DATA SHEET MIXED BED FEED PUMP | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1059 | PP | GRT-DC01-P0LDH-125816 | 125816 | DATA SHEET AIR BLOWER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1060 | PP | GRT-DC01-P0LDP-125817 | 125817 | DATA SHEET REGENERATION PUMP | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1061 | PP | GRT-DC01-P0LDN-125818 | 125818 | DATA SHEET ACID DOSING PUMP FOR NEUTRALIZING SYSTEM | FI | 2017-10-13 | 2017-11-12 | 2017-10-13 | GRT-PP-IP-DT-170268 | FI | D | 2017-10-19 | 0019.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | D | A
1062 | PP | GRT-DC01-P0LDN-125819 | 125819 | DATA SHEET CAUSTIC DOSING PUMP FOR NUTRALIZING SYSTEM | FI | 2017-10-13 | 2017-11-12 | 2017-10-13 | GRT-PP-IP-DT-170268 | FI | D | 2017-10-19 | 0019.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | D | A
1063 | PP | GRT-DC01-P0LDR-125820 | 125820 | DATA SHEET NEUTRALIZATION DISCHARGE PUMP | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1064 | PP | GRT-YT02-P0LD-165822 | 165822 | DATA SHEET PRESSURE INDICATOR | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1065 | PP | GRT-YT02-P0LD-165823 | 165823 | DATA SHEET FLOW TRANSMITTER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1066 | PP | GRT-YT02-P0LD-165824 | 165824 | DATA SHEET PH TRANSMITTER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1067 | PP | GRT-YT02-P0LD-165825 | 165825 | DATA SHEET CONDUCTIVITY TRANSMITTER | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1068 | PP | GRT-YT02-P0LD-165826 | 165826 | DATA SHEET LEVEL SWITCH WTP MIXED BED | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1069 | PP | GRT-YT02-P0LD-165827 | 165827 | DATA SHEET PRESSURE SWITCH | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1070 | PP | GRT-YT02-P0LD-165828 | 165828 | DATA SHEET FLOW INDICATOR | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1071 | PP | GRT-YT02-P0LD-165829 | 165829 | DATA SHEET PRESSURE DIFFERENTIAL SWITCH | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1072 | PP | GRT-XK58-P0GCK-125830 | 125830 | GENERAL ARRANGEMENT ACID METERING TANK | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1073 | PP | GRT-XK58-P0GCK-125840 | 125840 | GENERAL ARRANGEMENT NAME PLATE OF TANK | FI | 2017-09-14 | 2017-10-14 | 2017-09-14 | GRT-PP-IP-DT-170225 | FI | B | 2017-09-20 | 0020.001/C.1.2.17.01/E04/PLNE/IX/2017 | FI | B | A
1074 | PP | GRT-CC08-P0GCK-135834 | 135834 | EQUIPMENT LAYOUT | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1075 | PP | GRT-XB02-P0GCK-135835 | 135835 | FOUNDATION LAYOUT | FI | 2017-07-21 | 2017-08-20 | 2017-07-21 | GRT-PP-IP-DT-170149 | FI | A | 2017-08-03 | 0003.001/C.1.2.17.01/E04/PLNE/VIII/2017 | FI | A | I
1076 | PP | GRT-XG02-P0GCK-135841 | 135841 | P & ID Mixed BED System | FI | 2017-10-19 | 2017-11-18 | 2019-03-04 | GRT-PP-IP-DT-191030 | FC | 1 | 2019-03-13 | 019/061/GRT/UPR/2019 | FC | 1 | B
1077 | PP | GRT-CC07-P0LD-135842 | 135842 | MASS BALANCE Mixed BED System | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1078 | PP | GRT-YL25-P0LD-165852 | 165852 | MODBUST LIST | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170275 | FC | 0 | 2017-10-23 | N.A | FI | 0 | A
1079 | PP | GRT-XM01-P0LD-195856 | 195856 | CONTROL PHILOSOPHY | FA | 2017-12-06 | 2018-01-05 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 4 |  | 2018-05-18 | FC | 4 | A
1080 | PP | GRT-DC01-P0GD-125920 | 125920 | Data Sheet Rectifier | FA | 2017-11-27 | 2017-12-27 | 2019-11-29 | MINI DRM 28-29NOV19 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 0 | A
1081 | PP | GRT-YL01-P0ZEN-165462 | 165462 | DCS IO List for Electrical Interface System | FA | 2017-10-20 | 2017-08-20 | 2017-10-20 | GRT-PP-IP-DT-170280 | FC | 0 | 2017-10-23 | N.A | FC | 0 | A
1082 | PP | GRT-YL01-P0ZEN-165463 | 165463 | DCS IO List for LDC Interface | FA | 2017-10-20 | 2017-08-20 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00036) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
1083 | PP | GRT-YL01-P0ZEN-165203 | 165203 | IO List for Package Equipment | FA | 2017-11-21 | 2017-11-21 | 2017-11-21 | GRT-PP-IP-DT-170332 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
1084 | PP | GRT-CV03-P0UGD-165559 | 165559 | Instrument Data Sheet for Waste Water Transfer System | FA | 2017-08-07 | 2017-08-07 | 2017-08-07 | GRT-PP-IP-DT-170172 | FC | 0 | 2017-08-07 | N.A | FC | 0 | A
1085 | PP | GRT-YL01-P0UGD-165558 | 165558 | DCS IO List for Waste Water Transfer System | FA | 2017-09-08 | 2017-09-08 | 2017-09-08 | GRT-PP-IP-DT-170215 | FC | 0 | 2017-09-08 | N.A | FC | 0 | A
1086 | PP | GRT-YD00-P0UGD-165560 | 165560 | Instrument Loscation Plant Layout for Waste Water Transfer System | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
1087 | PP | GRT-YS02-P0ZEN-165568 | 165568 | Instrument Termination Dagaram for Waste Water Transfer System | FA | 2017-09-20 | 2017-09-20 | 2017-09-20 | GRT-PP-IP-DT-170232 | FC | 0 | 2017-09-20 | N.A | FC | 0 | A
1088 | PP | GRT-YF00-P0ZEN-165568 | 165568 | Instrument Control Loop for Sea Water Intake System | FA | 2017-09-20 | 2017-09-20 | 2019-01-16 | GRT-PP-IP-DT-190939 | FC | 2 | 2019-02-01 | 006/061/GRT/UPR/2019 | FC | 2 | A
1089 | PP | GRT-YF00-P0ZEN-165569 | 165569 | Instrument Control Logic for Circulating Sea Water Cooling System | FA | 2017-11-20 | 2017-11-20 | 2017-11-20 | GRT-PP-IP-DT-170329 | FC | 0 | 2017-11-21 | N.A | FC | 0 | A
1090 | PP | GRT-YF00-P0ZEN-165570 | 165570 | Instrument Control Logic for Raw Water System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A
1091 | PP | GRT-YF00-P0ZEN-165571 | 165571 | Instrument Control loop for Raw Water System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A
1092 | PP | GRT-YF00-P0ZEN-165572 | 165572 | Instrument Control Logic for Demin Make up System | FA | 2017-12-12 | 2017-12-12 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A
1093 | PP | GRT-YF00-P0ZEN-165573 | 165573 | Instrument Control Loop for Demin Make up System | FA | 2017-12-12 | 2017-12-12 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A
1094 | PP | GRT-YF00-P0ZEN-165574 | 165574 | INSTRUMENT CONTROL LOGIC FOR AUXILIARY SERVICE WATER SYSTEM | FA | 2017-11-13 | 2017-12-13 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 1 | 2018-02-23 | Comment Sheet IP | FC | 1 | A
1095 | PP | GRT-YF00-P0ZEN-165575 | 165575 | Instrument Control Logic for Service Water System | FA | 2017-11-03 | 2017-12-03 | 2018-02-21 | GRT-PP-IP-DT-180425 | FC | 0 | 2018-02-23 | Comment Sheet IP | FC | 0 | A
1096 | PP | GRT-YF00-P0ZEN-165576 | 165576 | Instrument Control Loop for Waste water Transfer System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A
1097 | PP | GRT-YF00-P0ZEN-165577 | 165577 | Instrument Control Loop for Waste water Transfer System | FA | 2017-10-24 | 2017-10-24 | 2017-10-24 | GRT-PP-IP-DT-170286 | FC | 0 | 2017-10-25 | N.A | FC | 0 | A
1098 | PP | GRT-YF00-P0ZEN-165578 | 165578 | Instrument Control Loop for Electrical | FA | 2017-11-03 | 2017-11-03 | 2017-11-03 | GRT-PP-IP-DT-170306 | FC | 0 | 2017-11-03 | N.A | FC | 0 | A
1099 | PP | GRT-YF00-P0ZEN-165579 | 165579 | Instrument Control Logic for Electrical System | FA | 2017-11-03 | 2017-11-03 | 2020-05-11 | GRT-PP-IP-DT-201589 (EMAIL) | FC | 1 |  |  | FC | 0 | A
1100 | PP | GRT-YF00-P0ZEN-165580 | 165580 | Instrument Control Loop for Condenser Circulating Sea Water Cooling System | FA | 2017-12-12 | 2017-12-12 | 2017-12-12 | GRT-PP-IP-DT-170355 | FC | 0 | 2017-12-13 | N.A | FC | 0 | A
1101 | PP | GRT-YQ05-P0BYA-165651 | 165651 | DCS System Alarm Diagram | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1102 | PP | GRT-YD07-P0BYA-165652 | 165652 | DCS Input / Output Signal List of DAS | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1103 | PP | GRT-YD07-P0BYA-165653 | 165653 | DCS Input / Output Signal List of GTC | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1104 | PP | GRT-YD07-P0BYA-165654 | 165654 | DCS Input / Output Signal List of GWC | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1105 | PP | GRT-YD07-P0BYA-165655 | 165655 | DCS Input / Output Signal List of SRS | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1106 | PP | GRT-YD07-P0BYA-165671 | 165671 | DCS Input / Output Signal List of H/W | FI | 2017-10-26 | 2017-11-25 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1107 | PP | GRT-YS02-P0BYA-165643 | 165643 | DCS Lan Configuration | FI | 2017-10-31 | 2017-11-30 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1108 | PP | GRT-DC01-P0BYA-165644 | 165644 | DCS Hardware Specification | FI | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FC | 0 | A
1109 | PP | GRT-YR00-P0BYA-165645 | 165645 | DCS Software Specification og GTC | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | B
1110 | PP | GRT-DC01-P0BYA-165646 | 165646 | DCS SRS Specification of GTC | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-15 | 0015.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | B
1111 | PP | GRT-YR05-P0BYA-165650 | 165650 | DCS Outline Drawing of SRS | FA | 2017-10-31 | 2017-11-30 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FI | 0 | A
1112 | PP | GRT-CV03-P0ZEN-165674 | 165674 | Data Sheet for Waste Water Transfer System | FI | 2017-11-17 | 2017-12-17 | 2017-12-19 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A
1113 | PP | GRT-CV03-P0ZEN-165675 | 165675 | Data Sheet for Service Water System | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A
1114 | PP | GRT-CV03-P0ZEN-165676 | 165676 | Data Sheet for Raw Water System | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A
1115 | PP | GRT-CV03-P0ZEN-165677 | 165677 | Data Sheet for Portable Water System | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A
1116 | PP | GRT-CV03-P0ZEN-165678 | 165678 | Data Sheet for Demin Make up Sysytem | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A
1117 | PP | GRT-CV03-P0ZEN-165679 | 165679 | Data Sheet for Circulating Water Pump | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2017-11-29 | Comment Sheet IP | FI | A | A
1118 | PP | GRT-YR05-P0BYA-165647 | 165647 | DCS Outline Drawing of DAS | FA | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1119 | PP | GRT-YR05-P0BYA-165648 | 165648 | DCS Outline Drawing of GTC | FA | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1120 | PP | GRT-YR05-P0BYA-165649 | 165649 | DCS Outline Drawing of GWC | FA | 2017-11-17 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1121 | PP | GRT-YS01-P0BYA-165656 | 165656 | GTCS-Schematic Diagram of DAS | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1122 | PP | GRT-YS01-P0BYA-165657 | 165657 | GTCS-Schematic Diagram of GTC | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1123 | PP | GRT-YS01-P0BYA-165668 | 165668 | GTCS-Spare Part List | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1124 | PP | GRT-YS01-P0BYA-165658 | 165658 | GTCS-Schematic Diagram of GWC | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | A
1125 | PP | GRT-YS01-P0BYA-165659 | 165659 | GTCS-Schematic Diagram of SRS | FA | 2017-12-05 | 2017-12-19 | 2017-12-19 | GRT-PP-IP-DT-170361 | FC | 0 | 2018-01-03 | Comment Sheet IP | FC | 0 | B
1126 | PP | GRT-YF02-P0BYA-165673 | 165673 | GTCS-System Configuration for GTC | FA | 2017-12-18 | 2018-01-17 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
1127 | PP | GRT-YR02-P0ZEN-156250 | 156250 | 150KV Grati Switchgear Surge Arrester Technical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
1128 | PP | GRT-YR02-P0ZEN-156251 | 156251 | 150KV Grati Switchgear Circuit Breaker Technical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
1129 | PP | GRT-YR02-P0ZEN-156252 | 156252 | 150KV Grati Switchgear Current Transfoemer Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
1130 | PP | GRT-YR02-P0ZEN-156253 | 156253 | 150KV Grati Switchgear Disconnector Switch Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
1131 | PP | GRT-YR02-P0ZEN-156254 | 156254 | 150KV Grati Switchgear Capacotator Voltage Transformer Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
1132 | PP | GRT-YR02-P0ZEN-156255 | 156255 | 150 KV Grati Switchgear Disconnector Swich Tecnical Particular & Guarantee | FA | 2017-10-05 | 2017-10-05 | 2017-10-05 | GRT-PP-IP-DT-170255 | FC | 0 | 2017-10-05 | N.A | FC | 0 | A
1133 | PP | GRT-YR02-P0AT-156106 | 156106 | Technical Specification UAT 15kV | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1134 | PP | GRT-YR02-P0AT-156117 | 156117 | Technical Specification SST 15kV | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1135 | PP | GRT-YD00-P0AT-156128 | 156128 | General Arrangement Drawing 150/15.75 kV – 250 MVA | FI | 2017-10-06 | 2017-11-05 | 2019-09-26 | GRT-PP-IP-DT-191407 (DCR 0039) | FC | 0FCR2 | 2019-09-26 | APPROVED ON SITE (PLN E) | FC | 0FCR2 | A
1136 | PP | GRT-XB02-P0AT-156129 | 156129 | Foundation Drawing 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1137 | PP | GRT-YS01-P0AT-156130 | 156130 | Rating & Schematic Plate 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1138 | PP | GRT-CC01-P0AT-156131 | 156131 | Oil Piping & Valve Location Plate 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1139 | PP | GRT-YS01-P0AT-156132 | 156132 | Schematic Diagram of Contorl Cubicle 150/15.75 kV-250 MVA Power Transformer | FI | 2017-10-19 | 2017-11-18 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | A | 2017-10-23 | 0023.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1140 | PP | GRT-YS01-P0AT-156133 | 156133 | Schematic Diagram of Remote Control Panel 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1141 | PP | GRT-XM00-P0AT-156134 | 156134 | Heaviest Part for Transformer Drawing Plate 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1142 | PP | GRT-YT01-P0AT-156135 | 156135 | Tecnical Specification (TPG) 150/15.75 kV – 250 MVA Power Transformer | FI | 2017-10-06 | 2017-11-05 | 2017-10-06 | GRT-PP-IP-DT-170256 | FI | A | 2017-10-09 | 0009.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1143 | PP | GRT-YD00-P0AT-156304 | 156304 | General Arrangement Drawing of 1000 KVA | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I
1144 | PP | GRT-YD00-P0AT-156305 | 156305 | General Arrangement Drawing of 2000 KVA | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I
1145 | PP | GRT-YD00-P0AT-156306 | 156306 | General Arrangement Drawing of 3000 KVA | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I
1146 | PP | GRT-YD00-P0AT-156107 | 156107 | General Arrangement Drawing of Unit Auxiliary Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1147 | PP | GRT-YD00-P0AT-156108 | 156108 | Termination Drawing of Auxiliary Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1148 | PP | GRT-YT01-P0AT-156110 | 156110 | Rating Plate UAT | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1149 | PP | GRT-YD00-P0AT-156118 | 156118 | General Arrangement Drawing of Unit Station Service Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1150 | PP | GRT-YD00-P0AT-156119 | 156119 | Termination drawing of Station Service Transformer 25MVA | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1151 | PP | GRT-YT01-P0AT-156121 | 156121 | Rating Plate SST | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1152 | PP | GRT-YS01-P0AT-156111 | 156111 | Layout and Schematic Diagram for Mashalling Kiosk Transformer 25000KVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1153 | PP | GRT-YV02-P0AT-156114 | 156114 | Layout and Schematic Diagram for Remote Tap Charger Control Panel Transformer 25MVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 0 | 2019-03-21 | 021/061/GRT/UPR/2019 | FI | 0 | A
1154 | PP | GRT-YS01-P0AT-156122 | 156122 | Layout and Schematic Diagram for Mashalling Kiosk Transformer 25000KVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2017-10-18 | GRT-PP-IP-DT-170274 | FI | A | 2017-10-23 | 0023.001/C.1.2.15.01/E04/PLNE/X/2017 | FI | A | I
1155 | PP | GRT-YV02-P0AT-156125 | 156125 | Layout and Schematic Diagram for Remote Tap Charger Control Panel Transformer 25MVA 15.75/6.3kV | FI | 2017-10-18 | 2017-11-17 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FI | 0 | B
1156 | PP | GRT-YD00-P0AT-156283 | 156283 | Surge Arrester Drawing of Station Service Transformer 25MVA | FI | 2017-10-19 | 2017-11-18 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | A | 2017-10-23 | 0023.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1157 | PP | GRT-YD00-P0AT-156284 | 156284 | NGR Drawing SST & UAT | FI | 2017-10-19 | 2017-11-18 | 2017-10-19 | GRT-PP-IP-DT-170276 | FI | A | 2017-10-23 | 0023.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1158 | PP | GRTBCP-YD00-P0BBA-156003 | 156003 | General Arrangement MV Switchgear 6,3kV | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1159 | PP | GRTBCP-YD00-P0BBA-156006 | 156006 | Data Sheet MV Switchgear 6,3 kV | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1160 | PP | GRT-DP00-P0MJY-156158 | 156158 | Diesel Genset Specification Sheet | FI | 2017-10-31 | 2017-11-30 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC | 3 | 2019-02-06 | 008/061/GRT/UPR/2019 | FC | 3 | B
1161 | PP | GRT-XK00-P0EGB-156154 | 156154 | General Arrangement Daily Tank Drawing | FI | 2017-10-31 | 2017-11-30 | 2018-10-26 | GRT-PP-IP-DT-180831 | FC | 1 | 2018-11-06 | Comment Sheet IP | FC | 1 | B
1162 | PP | GRT-YK08-P0MJA-156152 | 156152 | General Arrangement Diesel Genset Drawings | FI | 2017-10-31 | 2017-11-30 | 2019-12-11 | GRT-PP-IP-DT-191520 | FC | 2 |  |  | FC | 2 | A
1163 | PP | GRT-YT01-P0MKA-156159 | 156159 | Generator Data Sheets | FI | 2017-12-11 | 2018-01-10 | 2018-03-28 | GRT-PP-IP-DT-180498 | FC | 1 | 2018-04-18 | DRM 5 | FC | 1 | A
1164 | PP | GRT-YT01-P0MJA-156160 | 156160 | Diesel Engine Data Sheet | FI | 2017-12-11 | 2018-01-10 | 2018-03-28 | GRT-PP-IP-DT-180498 | FC | 1 | 2018-04-18 | DRM 5 | FC | 1 | A
1165 | PP | GRT-YD00-P0BAC-156285 | 156285 | GCB General Arrangement Drawing for FKG 1X | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1166 | PP | GRT-YD00-P0BAC-156286 | 156286 | GCB General Arrangement Drawing for FKG 1X | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1167 | PP | GRTBCP-YD00-P0BBA-156004 | 156004 | Single Line Diagram MV Switchgear 6,3 kV | FI | 2017-10-31 | 2017-11-30 | 2017-10-31 | GRT-PP-IP-DT-170301 | FI | A | 2017-11-02 | 0002.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1168 | PP | GRT-YD00-P0BVC-156357 | 156357 | General Arrangement UPS System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1169 | PP | GRT-YD00-P0BRA-156358 | 156358 | General Arrangement AC Distribution Board 400/230V for UPS System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1170 | PP | GRT-YD00-P0BTL-156363 | 156363 | General Arrangement DC System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1171 | PP | GRT-YD00-P0BVC-156364 | 156364 | General Arrangement DC Distribution Board 220V for DC System | FI | 2017-11-14 | 2017-12-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-21 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1172 | PP | GRT-YD00-P0BFA-156376 | 156376 | General Arrangement NSPB-A | FA | 2017-11-14 | 2017-12-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1173 | PP | GRT-YD00-P0BFA-156379 | 156379 | General Arrangement NSPB-B | FI | 2017-11-14 | 2017-12-14 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1174 | PP | GRT-XW03-P0ZEN-156243 | 156243 | Switchgear Steel Structures SA Support H=2. 1M - IB573 | FA | 2017-11-16 | 2017-12-16 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1175 | PP | GRT-XW03-P0ZEN-156240 | 156240 | Switchgear Steel Structures CB Support IB562 ( GL314 – TYPE F1 ) | FA | 2017-11-16 | 2017-12-16 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A
1176 | PP | GRT-XW03-P0ZEN-156179 | 156179 | 150kV Grati, Switchgear Calculation Note Compatibility CT / Protection (exclude GSUT & SST Area) | FA | 2017-11-16 | 2017-12-16 | 2017-12-18 | GRT-PP-IP-DT-170357 | FC(D) | B | 2017-12-22 | 0022.001/C.1.2.17.01/E04/PLNE/XII/2017 | FA | B | A
1177 | PP | GRT-XW03-P0ZEN-156190 | 156190 | 150kV Grati, Switchgear Calculation Steel Structures - Gantries | FA | 2017-11-16 | 2017-12-16 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1178 | PP | GRT-YT01-P0BAA-156304 | 156304 | Technical Data Sheet for 15.75kV IPBD | FI | 2017-10-09 | 2017-11-08 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B
1179 | PP | GRT-YK10-P0BAA-156305 | 156305 | Standar Sub-assembly Drawing for 15.75kV IPBD | FI | 2017-10-09 | 2017-11-08 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B
1180 | PP | GRT-YB10-P0BAA-156314 | 156314 | Terminationn Details of 15.75kV IPBD | FI | 2017-12-13 | 2018-01-12 | 2018-09-04 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B
1181 | PP | GRT-YK08-P0BAA-156316 | 156316 | GA & Wiring Diagram of Pressurisation Cubicle for 15.75kV IPBD | FI | 2017-12-13 | 2018-01-12 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B
1182 | PP | GRT-YD00-P0BFA-156123 | 156123 | General Arrangement NSPB-1 | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2018-10-05 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | 1 | I
1183 | PP | GRT-YD00-P0BFA-156126 | 156126 | General Arrangement NSPB-2 | FI | 2017-11-17 | 2017-12-17 | 2017-11-17 | GRT-PP-IP-DT-170326 | FI | A | 2018-10-05 | 0021.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | 1 | I
1184 | PP | GRT-XW03-P0ZEN-156192 | 156192 | 150kV Grati Switchgear Single Line Diagram Diameter | FA | 2017-11-14 | 2017-12-14 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 1 | 2018-05-18 | Comment Sheet IP | FC | 1 | A
1185 | PP | GRT-VS02-P0BTL-156359 | 156359 | Battery Rack 2000AH for UPS System | FI | 2017-11-24 | 2017-12-24 | 2018-11-08 | GRT-PP-IP-DT-180852 | FC | 2 | 2018-12-13 | Comment Sheet IP | FC | 2 | B
1186 | PP | GRT-VS02-P0BTL-156365 | 156365 | Battery Rack 800AH for DC System | FI | 2017-11-24 | 2017-12-24 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-06 | Comment Sheet IP | FC | 1 | B
1187 | PP | GRT-XB02-P0BAA-156313 | 156313 | Layout Foundation Detail of 15. 75kV IPBD | FI | 2017-11-24 | 2017-12-24 | 2018-09-04 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B
1188 | PP | GRT-YD00-P0BFA-156018 | 156018 | General Arrangement LV Switchgear 1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1189 | PP | GRT-YD00-P0BFB-156023 | 156023 | General Arrangement LV Switchgear 2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1190 | PP | GRT-YD00-P0BFC-156028 | 156028 | General Arrangement LV Switchgear 3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1191 | PP | GRT-YD00-P0BFD-156033 | 156033 | General Arrangement LV Switchgear 4 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1192 | PP | GRT-YD00-P0BJA-156038 | 156038 | General Arrangement STG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | B
1193 | PP | GRT-YD00-P0BJA-156043 | 156043 | General Arrangement STG PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1194 | PP | GRT-YD00-P0BJC-156048 | 156048 | General Arrangement HRSG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1195 | PP | GRT-YD00-P0BJD-156053 | 156053 | General Arrangement LV Switchgear 3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1196 | PP | GRT-YD00-P0BJE-156058 | 156058 | General Arrangement Valve PDB | FI | 2017-11-24 | 2017-12-24 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 1 | 2019-03-21 | 021/061/GRT/UPR/2019 | FC | 1 | A
1197 | PP | GRT-YD00-P0BJF-156063 | 156063 | General Arrangement BOP Essential MCC | FI | 2017-11-24 | 2017-12-24 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 1 | 2019-03-21 | 021/061/GRT/UPR/2019 | FC | 1 | A
1198 | PP | GRT-YD00-P0BJG-156068 | 156068 | General Arrangement Space Heater Panel | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1199 | PP | GRT-YD00-P0BJG-156073 | 156073 | General Arrangement BOP Essential PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1200 | PP | GRT-YD00-P0BJJ-156078 | 156078 | General Arrangement Feeder UPS-01 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1201 | PP | GRT-YD00-P0BJK-156083 | 156083 | General Arrangement Feeder UPS-02 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1202 | PP | GRT-YD00-P0BJL-156088 | 156088 | General Arrangement Feeder Normal Lighting | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1203 | PP | GRT-YD00-P0BJN-156093 | 156093 | General Arrangement HVAC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1204 | PP | GRT-YT01-P0BJP-156315 | 156315 | Data Sheet HRSG PDB-3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1205 | PP | GRT-YT01-P0BJ0-156315 | 156315 | Data Sheet HRSG PDB-2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1206 | PP | GRT-YT01-P0BJN-156310 | 156310 | Data Sheet HRSG PDB-1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1207 | PP | GRT-YT01-P0BJN-156096 | 156096 | Data Sheet Feeder HVAC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1208 | PP | GRT-YT01-P0BJL-156091 | 156091 | Data Sheet Feeder Normal Lighting | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1209 | PP | GRT-YT01-P0BJK-156086 | 156086 | Data Sheet Feeder UPS-2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1210 | PP | GRT-YT01-P0BJJ-156081 | 156081 | Data Sheet Feeder UPS-1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1211 | PP | GRT-YT01-P0BJH-156076 | 156076 | Data Sheet BOP Essensial PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1212 | PP | GRT-YT01-P0BJG-156071 | 156071 | Data Sheet Space Heater Panel | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1213 | PP | GRT-YT01-P0BJF-156066 | 156066 | Data Sheet BOP Essential MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1214 | PP | GRT-YT01-P0BJE-156061 | 156061 | Data Sheet Valve PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1215 | PP | GRT-YT01-P0BJC-156051 | 156051 | Data Sheet HRSG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1216 | PP | GRT-YT01-P0BJB-156046 | 156046 | Data Sheet STG PDB | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1217 | PP | GRT-YT01-P0BJA-156041 | 156041 | Data Sheet STG Unit MCC | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1218 | PP | GRT-YT01-P0BFD-156036 | 156036 | Data Sheet LV Switchgear 4 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1219 | PP | GRT-YT01-P0BFC-156031 | 156031 | Data Sheet LV Switchgear 3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1220 | PP | GRT-YT01-P0BFB-156026 | 156026 | Data Sheet LV Switchgear 2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1221 | PP | GRT-YT01-P0BFA-156021 | 156021 | Data Sheet LV Switchgear 1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1222 | PP | GRT-YT01-P0BJP-156317 | 156317 | General Arrangement HRSG PDB-3 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1223 | PP | GRT-YT01-P0BJ0-156312 | 156312 | General Arrangement HRSG PDB-2 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1224 | PP | GRT-YT01-P0BJN-156307 | 156307 | General Arrangement HRSG PDB-1 | FI | 2017-11-24 | 2017-12-24 | 2017-11-24 | GRT-PP-IP-DT-170336 | FI | A | 2017-12-07 | 0007.001/C.1.2.15.01/E04/PLNE/XII/2017 | FI | A | I
1225 | PP | GRT-DD00-P0BAA-156306 | 156306 | Type Test Reports for 15.75kV IPBD | FI | 2017-10-09 | 2017-11-08 | 2017-10-09 | GRT-PP-IP-DT-170260 | FI | A | 2017-10-17 | 0030.001/C.1.2.17.01/E04/PLNE/V/2017 | FI | A | I
1226 | PP | GRT-DN03-P0BAA-156308 | 156308 | Site Inspection &Test Plan for 15.75kV IPBD | FI | 2017-12-07 | 2018-01-06 | 2017-12-07 | GRT-PP-IP-DT-170353 | FI | A | 2018-01-08 | 0008.001/C.1.2.17.01/E04/PLNE/XII/2017 | FI | A | I
1227 | PP | GRT-YB10-P0UBL-156315 | 156315 | Support Structure Detail of 15.75kV IPBD | FI | 2017-11-24 | 2017-12-24 | 2018-04-09 | GRT-PP-IP-DT-180741 | FC | 1 | 2018-10-05 | Comment Sheet IP | FC | 1 | B
1228 | PP | GRT-CC03-P0UGD-175466 | 175466 | Raw Water Tank Concrete Structure Foundation Plan, Detail & Schedule | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
1229 | PP | GRT-CC03-P0UGD-175468 | 175468 | Make up Demin Water Tank Concrete Structure Foundation Plant, Detail & Schedule | FA | 2017-09-05 | 2017-09-05 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
1230 | PP | GRT-CC07-P0UGD-175465 | 175465 | Calculation Sheet for Raw Water Tank Foundation | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
1231 | PP | GRT-CC07-P0UGD-175467 | 175467 | Calculation Sheet for Make –up Demin Water Tank Foundation | FA | 2017-09-05 | 2017-09-05 | 2017-09-05 | GRT-PP-IP-DT-170208 | FC | 0 | 2017-09-06 | N.A | FC | 0 | A
1232 | PP | GRT-CC06-P0UMA-175272 | 175272 | Calculation Sheet for Steam Turbine Building Foundation | FA | 2017-04-08 | 2017-05-08 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
1233 | PP | GRT-CC00-P0UGD-175395 | 175395 | Fire Fighting Shelter Architectural Plan, View, Section & Finishing Schedule | FA | 2017-08-09 | 2017-08-09 | 2017-08-09 | GRT-PP-IP-DT-170178 | FC | 0 | 2017-08-09 | N.A | FC | 0 | A
1234 | PP | GRT-CA01-P0UGD-175563 | 175563 | Water Treatment Plant Concrete Structure Section and Detail | FA | 2017-09-04 | 2017-09-04 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
1235 | PP | GRT-CA01-P0UGD-175564 | 175564 | Water Treatment Plant Concrete Structure Section and Detail | FA | 2017-09-04 | 2017-09-04 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
1236 | PP | GRT-CC03-P0UBN-175568 | 175568 | Emergency Diesel Generator Concrete Structure Foundation Plan & Detail | FA | 2017-09-13 | 2017-09-13 | 2019-06-28 | GRT-PP-IP-DT-191235 (DCR 00048) | FC | 1 | 2019-07-19 | 040/061/GRT/UPR/2019 |  | 1 | B
1237 | PP | GRT-CC07-P0UBN-175569 | 175569 | Calculation Sheet for EDG Foundation | FA | 2017-09-04 | 2017-09-04 | 2017-09-04 | GRT-PP-IP-DT-170206 | FC | 0 | 2017-09-04 | N.A | FC | 0 | A
1238 | PP | GRT-CC03-P0UMA-175596 | 175596 | Calculation Sheet for Underground Facility | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-21 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1239 | PP | GRT-CC03-P0UMA-175597 | 175597 | Cable Trench and Duct Bank General Layout | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1240 | PP | GRT-CC03-P0UMA-175598 | 175598 | Cable Trench and Duct Bank Lay out Area 1 | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1241 | PP | GRT-CC03-P0UMA-175599 | 175599 | Cable Trench and Duct Bank Lay out Area 2 | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1242 | PP | GRT-CC03-P0UMA-175600 | 175600 | Cable Trench and Duct Bank Lay out Area 3 | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1243 | PP | GRT-CC03-P0UMA-175601 | 175601 | Cable Trench and Duct Bank Detail | FA | 2017-11-21 | 2017-12-21 | 2018-04-07 | GRT-PP-IP-DT-180524 (EMAIL) | FC | 1 | 2018-04-18 | DRM 5 |  | 1 | A
1244 | PP | GRT-CC03-P0UMA-175602 | 175602 | Cable Trench and Duct Bank Detail | FA | 2017-11-21 | 2017-12-21 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0015) | FC | 1 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 1 | B
1245 | PP | GRT-CC03-P0UMA-175603 | 175603 | Cable Pit Foundation Detail | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1246 | PP | GRT-CC03-P0UMA-175604 | 175604 | Culvert Detail, Section & Schedule (1/2) | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1247 | PP | GRT-CC03-P0UMA-175605 | 175605 | Culvert Detail, Section & Schedule (2/2) | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1248 | PP | GRT-CC03-P0UMA-175606 | 175606 | Culvert, Detail & Section | FA | 2017-11-21 | 2017-12-21 | 2017-11-21 | GRT-PP-IP-DT-170333 | FC | 1 | 2017-11-27 | 0027.001/C.1.2.17.01/E04/PLNE/XI/2017 | FA | B | A
1249 | PP | GRT-CA00-P0PAC-175607 | 175607 | Calculation Sheet for Intake Electrical Building | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
1250 | PP | GRT-CA01-P0PAC-175608 | 175608 | Intake Electrical Building Architectural Plan, View, Section, & Finishing Schedule | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
1251 | PP | GRT-CA01-P0PAC-175609 | 175609 | Intake Electrical Building Foundation, Floor, & Roof Plant, Section, Detail Grade Beam, Slab, & Column Schedule | FA | 2017-10-23 | 2017-10-23 | 2017-10-23 | GRT-PP-IP-DT-170283 | FC | 0 | 2017-10-24 | N.A | FC | 0 | A
1252 | PP | GRT-CC07-P0UZEN-175475 | 175475 | Calculation Sheet for Liquefaction potential Check | FA | 2017-09-28 | 2017-09-28 | 2017-09-28 | GRT-PP-IP-DT-170244 | FC | 0 | 2017-09-28 | N.A | FC | 0 | A
1253 | PP | GRT-CC04-P1UHA-175617 | 175617 | HRSG Foundation Plan and Section | FA | 2017-12-06 | 2017-12-06 | 2019-03-08 | GRT-PP-IP-DT-191050 | FC | 1 | 2019-04-01 | 024/061/GRT/UPR/2019 | FC | 1 | A
1254 | PP | GRT-CC04-P1UHA-175616 | 175616 | HRSG Concrete Layout | FA | 2017-12-06 | 2017-12-06 | 2019-03-08 | GRT-PP-IP-DT-191050 | FC | 1 | 2019-04-01 | 024/061/GRT/UPR/2019 | FC | 1 | A
1255 | PP | GRTBCP-YS01-P0BJP-156020 | 156020 | Schematic Diagram LV Switch Gear 1 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1256 | PP | GRTBCP-YS01-P0BFB-156025 | 156025 | Schematic Diagram LV Switch Gear 2 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1257 | PP | GRTBCP-YS01-P0BFC-156030 | 156030 | Schematic Diagram LV Switch Gear 3 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 27-Des-17 | Comment Sheet IP | FI | A | I
1258 | PP | GRTBCP-YS01-P0BFD-156035 | 156035 | Schematic Diagram LV Switch Gear 4 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1259 | PP | GRTBCP-YS01-P0BJA-156040 | 156040 | Schematic Diagram STG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1260 | PP | GRTBCP-YS01-P0BJB-156045 | 156045 | Schematic Diagram STG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1261 | PP | GRTBCP-YS01-P0BJC-156050 | 156050 | Schematic Diagram HRSG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1262 | PP | GRTBCP-YS01-P0BJD-156055 | 156055 | Schematic Diagram HRSG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1263 | PP | GRTBCP-YS01-P0BJE-156060 | 156060 | Schematic Diagram Valve PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1264 | PP | GRTBCP-YS01-P0BJF-156065 | 156065 | Schematic Diagram BOP Essential MCC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1265 | PP | GRTBCP-YS01-P0BJG-156070 | 156070 | Schematic Diagram Space Heater Panel | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1266 | PP | GRTBCP-YS01-P0BJH-156075 | 156075 | Schematic Diagram BOP Essential PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1267 | PP | GRTBCP-YS01-P0BJJ-156080 | 156080 | Schematic Diagram Feeder UPS-01 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1268 | PP | GRTBCP-YS01-P0BJK-156085 | 156085 | Schematic Diagram Feeder UPS-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1269 | PP | GRTBCP-YS01-P0BJL-156090 | 156090 | Schematic Diagram Feeder Normal Lighting | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1270 | PP | GRTBCP-YS01-P0BJM-156095 | 156095 | Schematic Diagram Feeder HVAC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1271 | PP | GRTBCP-YS01-P0BJN-156398 | 156398 | Schematic Diagram HRSG PDB-01 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1272 | PP | GRTBCP-YS01-P0BJO-156403 | 156403 | Schematic Diagram HRSG PDB-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1273 | PP | GRTBCP-YS01-P0BJP-156408 | 156408 | Schematic Diagram HRSG PDB-03 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1274 | PP | GRT-YU01-P0BFA-156019 | 156019 | Single Line Diagram LV Switchgear 1 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1275 | PP | GRT-YU01-P0BFB-156024 | 156024 | Single Line Diagram LV Switchgear 2 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1276 | PP | GRT-YU01-P0BFC-156029 | 156029 | Single Line Diagram LV Switchgear 3 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2018-01-08 | Comment Sheet IP | FI | A | B
1277 | PP | GRT-YU01-P0BFD-156034 | 156034 | Single Line Diagram LV Switchgear 4 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1278 | PP | GRT-YU01-P0BJA-156039 | 156039 | Single Line Diagram STG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2019-11-07 | GRT-PP-IP-DT-191475 | FC | 1 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | 1 | A
1279 | PP | GRT-YU01-P0BJA-156044 | 156044 | Single Line Diagram STG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1280 | PP | GRT-YU01-P0BJC-156049 | 156049 | Single Line Diagram HRSG Unit MCC | FI | 2018-01-26 | 2018-02-25 | 2019-11-07 | GRT-PP-IP-DT-191475 | FC | 1 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | 1 | A
1281 | PP | GRT-YU01-P0BJP-156054 | 156054 | Single Line Diagram HRSG PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1282 | PP | GRT-YU01-P0BJE-156059 | 156059 | Single Line Diagram Valve PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1283 | PP | GRT-YU01-P0BJF-156064 | 156064 | Single Line Diagram BOP Essensial MCC | FI | 2018-01-26 | 2018-02-25 | 2019-11-07 | GRT-PP-IP-DT-191475 | FC | 1 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | 1 | A
1284 | PP | GRT-YU01-P0BJG-156069 | 156069 | Single Line Diagram Space Heater Panel | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1285 | PP | GRT-YU01-P0BJH-156074 | 156074 | Single Line Diagram BOP Essensial PDB | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1286 | PP | GRT-YU01-P0BJJ-156079 | 156079 | Single Line Diagram Feeder UPS-01 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1287 | PP | GRT-YU01-P0BJK-156084 | 156084 | Single Line Diagram Feeder UPS-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1288 | PP | GRT-YU01-P0BJL-156089 | 156089 | Single Line Diagram Feeder Normal Lighting | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1289 | PP | GRT-YU01-P0BJM-156094 | 156094 | Single Line Diagram Feeder HVAC | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1290 | PP | GRT-YU01-P0BJM-156099 | 156099 | Single Line Diagram Feeder PDB-01 | FI | 2017-12-07 | 2018-01-06 | 2017-12-07 | GRT-PP-IP-DT-170353 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1291 | PP | GRT-YU01-P0BJO-156104 | 156104 | Single Line Diagram Feeder PDB-02 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1292 | PP | GRT-YU01-P0BJP-156109 | 156109 | Single Line Diagram Feeder PDB-03 | FI | 2018-01-26 | 2018-02-25 | 2017-12-18 | GRT-PP-IP-DT-170357 | FI | A | 2017-12-27 | Comment Sheet IP | FI | A | I
1293 | PP | GRT-CC07-PIUHA-175610 | 175610 | Calculation Sheet for Elevator Structure and Foundation | FA | 2018-01-04 | 2018-01-04 | 2018-02-02 | GRT-PP-IP-DT-180405 | FC | 0 | 2018-02-12 | Comment Sheet IP | FC | 0 | A
1294 | PP | GRT-CC03-P1UHA-175611 | 175611 | Elevation HRSG Foundation Plan, detail & Section | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B
1295 | PP | GRT-CC04-P1UHA-175612 | 175612 | Elevation HRSG Steel Structure Column Arrangement & Member Schedule | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B
1296 | PP | GRT-CC04-P1UHA-175613 | 175613 | Elevation HRSG Steel Structure Framing Elevation | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B
1297 | PP | GRT-CC04-P1UHA-175614 | 175614 | Elevation HRSG Steel Structure Stairway Detail & Section | FA | 2018-01-04 | 2018-01-04 | 2019-01-08 | GRT-PP-IP-DT-190925 (DCR0014) | FC | 2 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | 2 | B
1298 | PP | GRT-CC04-P1UHA-175615 | 175615 | Elevator HRSG Architectural Plan, Detail, & Finishing Schedule | FA | 2017-12-06 | 2017-12-06 | 2017-12-06 | GRT-PP-IP-DT-170352 | FC | 0 | 2017-12-08 | N.A | FC | 0 | A
1299 | PP | GRT-FF01-P0SGA-125501 | 125501 | General Arrangement Drawing Fire Pump | FA | 2017-06-10 | 2017-10-16 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1300 | PP | GRT-YD00-P0ZEN-120003 | 120003 | General Arrangement Make up Demin Tank Capacity 1000 M3 | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1301 | PP | GRT-YD00-P0ZEN-120007 | 120007 | Roof Rafter Assembly Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1302 | PP | GRT-YD00-P0ZEN-120010 | 120010 | Shell Manhole Section & Detail Make Up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1303 | PP | GRT-YD00-P0ZEN-120018 | 120018 | Anchor Bolt Arrangemnt Section & Detail Make Up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1304 | PP | GRT-YD00-P0ZEN-120004 | 120004 | Shell Plate Arrangement Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1305 | PP | GRT-YD00-P0ZEN-120005 | 120005 | Bottom Plate Arrangement Section & Detail Make Up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1306 | PP | GRT-YD00-P0ZEN-120006 | 120006 | Roof Plate Arrangement Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1307 | PP | GRT-YD00-P0ZEN-120017 | 120017 | Roof Manhole Section & Detail Make up Demin Tank | FA | 2017-11-09 | 2017-10-10 | 2017-10-10 | GRT-PP-IP-DT-170263 | FC | 0 | 2017-10-10 | N.A | FC | 0 | A
1308 | PP | GRT-YD00-P0UGD-120032 | 120032 | General Arrangement Drawing | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1309 | PP | GRT-YD00-P0UGD-120034 | 120034 | Roof Manhole Scetion and Detail | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1310 | PP | GRT-YD00-P0UGD-120035 | 120035 | Roof Structure Assembling Section & Detail | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1311 | PP | GRT-XW03-P0UGD-120002 | 120002 | Mechanical Calculation & Orentation | FI | 2017-03-11 | 2017-03-11 | 2017-03-11 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1312 | PP | GRT-YD00-P0UGD-120033 | 120033 | Bottom Plate Arrangement Section & Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170305 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1313 | PP | GRT-YD00-P0UGD-120036 | 120036 | Stairway Arrangement | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1314 | PP | GRT-YD00-P0UGD-120037 | 120037 | Shell Manhole Section & Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1315 | PP | GRT-YD00-P0UGD-120038 | 120038 | Roof Plate Arrangement Section & Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1316 | PP | GRT-YD00-P0UGD-120039 | 120039 | Roof Handril Detail | FI | 2017-11-14 | 2017-11-14 | 2017-11-14 | GRT-PP-IP-DT-170317 | FI | A | 2017-11-29 | 0020.001/C.1.2.17.01/E04/PLNE/XI/2017 | FI | A | I
1317 | PP | GRT-YT01-P0ZEN-145568 | 145568 | Data Sheet for rubber Expansion Join | FI | 2017-10-20 | 2017-10-20 | 2017-10-20 | GRT-PP-IP-DT-170279 | FI | A | 2017-07-11 | 0024.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1318 | PP | GRT-UE00-P0ZEN-145571 | 145571 | General Arrangement for Rubber Expansion Joint | FI | 2017-10-20 | 2017-10-20 | 2017-10-20 | GRT-PP-IP-DT-170279 | FI | A | 2017-07-11 | 0024.001/C.1.2.17.01/E04/PLNE/X/2017 | FI | A | I
1319 | PP | GRT-PP-KSB-P1702024-ME-002 | ME-002 | Mechanical Data Sheet for CWP Pump | FA | 2017-06-10 | 2017-06-10 | 2017-10-16 | GRT-PP-IP-DT-170271 | FC | 0 | 2017-10-17 | N.A | FC | 0 | A
1320 | PP | GRT - YL16 - P0LD - 155944 | 155944 | Cable Schedule Electrical for EC | FI | 2018-02-02 | 2018-02-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1321 | PP | GRT - YL16 - P0LD - 155945 | 155945 | Cable Schedule Instrument for EC | FI | 2018-02-02 | 2018-02-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1322 | PP | GRT - YL16 - P0LD - 155848 | 155848 | Cable Schedule Electrical for WTP | FI | 2018-02-02 | 2018-02-16 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1323 | PP | GRT - YL16 - P0LD - 155949 | 155849 | Cable Schedule Instrument for WTP | FI | 2018-02-02 | 2018-02-16 | 2019-01-10 | GRT-PP-IP-DT-190929 (DCR0018) | FC | 0DCR1 | 2019-01-22 | 004/061/GRT/UPR/2019 | FC | DCR | A
1324 | PP | GRT - YT01 - P0GCK - 126801 | 126801 | Data Sheet Make Up Demin Water Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1325 | PP | GRT - YT01 - P0GCK - 126802 | 126802 | Data Sheet Blow Down Transfer Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1326 | PP | GRT - YT01 - P0GCK - 126803 | 126803 | Data Sheet Service Water Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1327 | PP | GRT - YT01 - P0GCK - 126804 | 126804 | Data Sheet Auxiliary Service Water Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1328 | PP | GRT - YT01 - P0GCK - 126805 | 126805 | Data Sheet Accumulation Sump Pit Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1329 | PP | GRT - YT01 - P0GCK - 126806 | 126806 | Data Sheet HRSG Sump Pit Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1330 | PP | GRT - YT01 - P0GCK - 126807 | 126807 | Data Sheet CEP Sump Pit Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1331 | PP | GRT - YT01 - P0GCK - 126808 | 126808 | Data Sheet Sea Water Drain Pump | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FC | 0 | 2018-02-15 | Comment Sheet IP | FI | 0 | B
1332 | PP | GRT-PP-MAR-0000 | 0000 | Material Approval Painting Raw Tank | FI | 2018-02-02 | 2018-02-16 | 2018-02-02 | GRT-PP-IP-DT-180407 | FI | B | 2018-02-15 | Comment Sheet IP | FA | 0 | B
1333 | PP | GRT-XW03-P0ZEN-156273 | 156273 | 150 kV Grati Switchgear Calculation Note High Voltage | FA | 2018-02-05 | 2018-02-19 | 2018-11-08 | GRT-PP-IP-DT-180852 | FC | 1 | 2018-11-14 | Comment Sheet IP | FC | 1 | B
1334 | PP | GRT-XW03-P0ZEN-156274 | 156274 | 150 kV Grati Switchgear Calculation Note lightning Arrester Checking | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-15 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | A
1335 | PP | GRT-XW03-P0ZEN-156276 | 156276 | 150 kV Grati Switchgear Calculation Note lightning Protection Zone | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1336 | PP | GRT-YR02-P0ZEN-156185 | 156185 | Common Switchgear Technical Specification Insulators | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1337 | PP | GRT-YR02-P0ZEN-156186 | 156186 | 150 kV Grati Switchgear Technical Soecification Earthing Material | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1338 | PP | GRT-YR02-P0ZEN-156187 | 156187 | Common Switchgear Technical Specification Conductor | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-15 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | A
1339 | PP | GRT-YR02-P0ZEN-156188 | 156188 | Common Switchgear Technical Specification String Hardware | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1340 | PP | GRT-YR02-P0ZEN-156189 | 156189 | Common Switchgear Technical Specification Connector | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180569 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A
1341 | PP | GRT-YS01-P0ZEN-156196 | 156196 | 150 kV Grati Switchgear Schematic Diagram Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-15 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | B
1342 | PP | GRTBCP-YS01-P0BBA-156005 | 156005 | Schematic Diagram MV Switchgear 6,3kV | FA | 2018-02-05 | 2018-02-19 | 2018-05-08 | GRT-PP-IP-DT-180574 | FC | 0 | 2018-05-23 | Comment Sheet IP | FC | 0 | A
1343 | PP | GRTSCH-YD00-P0BAC-150005 | 150005 | SF6 Pressure Scale | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FI | A | 2018-02-21 | 0009.001/C.I.2.17.01/E04/PLNE/II/2018 | FA | A | I
1344 | PP | GRTSCH-YD00-P0BAC-150004 | 150004 | Name Plate | FA | 2018-02-05 | 2018-02-19 | 2018-02-05 | GRT-PP-IP-DT-180408 | FC(D) | A | 2018-02-21 | Comment Sheet IP | FA | A | B
1345 | PP | GRTSCH-YD00-P0BAC-150003 | 150003 | Interlocking Diagram | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | MINI DRM 28-29NOV19 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FA | B | B
1346 | PP | GRTSCH-YS01-P0BAC-150006 | 150006 | Electrical Diagram | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | MINI DRM 28-29NOV19 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FA | B | B
1347 | PP | GRT-YS18-P0BTL-156176 | 156176 | Battery Charger Circuit | FA | 2018-02-05 | 2018-02-19 | 2018-03-28 | GRT-PP-IP-DT-180498 | FC | 0 | 2018-04-18 | DRM 5 | FC | 0 | A
1348 | PP | GRT-YT02-P0MJY-156171 | 156171 | Flame and Smoke Detector Specification Sheet | FA | 2018-02-05 | 2018-02-19 | 2019-12-09 | GRT-PP-IP-DT-191518 | FC(D) | C |  |  | FA | C | A
1349 | PP | GRT-US02-P0MJY-156156 | 156156 | Local Electrical Panel Bom and Drawing | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A
1350 | PP | GRT-MA01-P0AY-156172 | 156172 | IO List Communication to DCS | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | GRT-PP-IP-DT-191512 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FA | B | B
1351 | PP | GRT-YF01-P0MJ-156169 | 156169 | Termination Diagram for EDG | FA | 2018-02-05 | 2018-02-19 | 2019-11-29 | GRT-PP-IP-DT-191510 | FC | 1 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 1 | A
1352 | PP | GRT-CC04-P0ZEN-156244 | 156244 | Common Switchgear Steel Structure C.V.T. SUPPORT H=2.1m - IB575 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1353 | PP | GRT-CC04-P0ZEN-156239 | 156239 | Common Switchgear Steel Structure C.T. SUPPORT - H = 4M - IB560 | FA | 2018-02-05 | 2018-02-19 | 2018-10-23 | GRT-PP-IP-DT-180826 | FC | 2 | 2018-12-13 | stempel approved | FC | 2 | A
1354 | PP | GRT-CC04-P0ZEN-156241 | 156241 | Common Switchgear Steel Structure 3 Pole Disconnector Support - IB571 (S2DA) | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A
1355 | PP | GRT-CC04-P0ZEN-156242 | 156242 | Common Switchgear Steel Structure Disconnector Support - IB572 (S2DAT) | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A
1356 | PP | GRT-CC04-P0ZEN-156247 | 156247 | Common Switchgear Steel Structure CSE SUPPORT - IB583 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-10-22 | Comment Sheet IP |  | 2 | A
1357 | PP | GRT-CC04-P0ZEN-156249 | 156249 | Common Switchgear Steel Structure SA SUPPORT H=4M - IB574 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A
1358 | PP | GRT-XW03-P0ZEN-156181 | 156181 | 150 KV Switchgear Calculation Note Battery & Chargear | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1359 | PP | GRT-XG11-P0AE-156349 | 156349 | Schematic Line Diagram Cable 150KV | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-10-30 | Comment Sheet IP | FC | 1 | B
1360 | PP | GRT-XW03-P0ZEN-156183 | 156183 | 150kV Grati Switchgear Technical Specification Protective Relays | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180569 | FC | 1 | 2018-05-18 | Comment Sheet IP | FC | 1 | I
1361 | PP | GRT-XW03-P0ZEN-156184 | 156184 | 150kV Grati Switchgear Technical Specification Low Voltage Cable | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-10-30 | Comment Sheet IP | FC | 1 | A
1362 | PP | GRT-XW03-P0ZEN-156193 | 156193 | 150kV Grati Switchgear 110V DC Single Line Diagram | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A
1363 | PP | GRT-XW03-P0ZEN-156209 | 156209 | 150KV Grati Switchgear Outdoor Installation Switchyard Layout | FA | 2018-02-05 | 2018-02-19 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
1364 | PP | GRT-XW03-P0ZEN-156195 | 156195 | 150 KV Switchgear Principle Diagram | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A
1365 | PP | GRT-XW03-P0ZEN-156206 | 156206 | 150 KV Switchgear Technical Specification Cable Sealing End (CSE) | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1366 | PP | GRT-XW03-P0ZEN-156210 | 156210 | 150kV Grati Switchgear Outdoor Installation Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 1 | - | - |  | 1 | A
1367 | PP | GRT-XW03-P0ZEN-156211 | 156211 | 150kV Grati Switchgear Outdoor Installation Diameter X | FA | 2018-02-05 | 2018-02-19 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 1 | - | - |  | 1 | A
1368 | PP | GRT-XW03-P0ZEN-156213 | 156213 | 150kV Grati Switchgear Outdoor Installation Lightning Protection Zone | FA | 2018-02-05 | 2018-02-19 | 2019-03-08 | GRT-PP-IP-DT-191059 | FC | 0 |  | Deem to approved | FC |  | A
1369 | PP | GRT-XW03-P0ZEN-156221 | 156221 | 150 KV Switchgear Cable List Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2019-05-07 | GRT-PP-IP-DT-191180 | FC | 1 | 2019-05-23 | 031/061/GRT/UPR/2018 |  | 1 | A
1370 | PP | GRT-XW03-P0ZEN-156222 | 156222 | 150 KV Switchgear Cable List Diameter X | FA | 2018-02-05 | 2018-02-19 | 2019-05-07 | GRT-PP-IP-DT-191180 | FC | 1 | 2019-05-23 | 031/061/GRT/UPR/2018 |  | 1 | A
1371 | PP | GRT-XW03-P0ZEN-156226 | 156226 | 150 KV Switchgear Connection Diagram Diameter 1 | FA | 2018-02-05 | 2018-02-19 | 2019-04-02 | GRT-PP-IP-DT-191115 | FC(D) | C | 2019-04-24 | 028/061/GRT/UPR/2019 | FA | C | A
1372 | PP | GRT-XW03-P0ZEV-156227 | 156227 | 150 KV Switchgear Connection Diagram Diameter X | FA | 2018-02-05 | 2018-02-19 | 2019-04-02 | GRT-PP-IP-DT-191115 | FC(D) | C | 2019-04-24 | 028/061/GRT/UPR/2019 | FA | C | A
1373 | PP | GRT-XW03-P0ZEN-156248 | 156248 | 150 KV Switchgear Earthing And Mounting Principle Drawing | FA | 2018-02-05 | 2018-02-19 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1374 | PP | GRT-YS01-P0ZEN-156197 | 156197 | 150KV GRATI. Switchgear Schematic Diagram Diameter X | FA | 2018-02-05 | 2018-02-19 | 2019-05-24 | DRM_22-24MAY2019 | FC | 0 | 2019-05-24 | DRM_22-24MAY2019 | FC | 0 | A
1375 | PP | GRT-CC04-P0ZEN-156232 | 156232 | Common Switchgear Steel Structure Tower Type P1-Bottom Part | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1376 | PP | GRT-CC04-P0ZEN-156233 | 156233 | Common Switchgear Steel Structure Tower Type P1-Top Part | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1377 | PP | GRT-CC04-P0ZEN-156234 | 156234 | Common Switchgear Steel Structure Tower Type P1- Tower Head | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1378 | PP | GRT-CC04-P0ZEN-156236 | 156236 | Common Switchgear Steel Structure Beam Type B1 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1379 | PP | GRT-CC04-P0ZEN-156238 | 156238 | Common Switchgear Steel Structure Post Insulator Support H=4.5M-IB555 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 1 | 2018-11-05 | Comment Sheet IP | FC | 1 | A
1380 | PP | GRT-CC04-P0ZEN-156245 | 156245 | Common Switchgear Steel StructureC.T Support-H=2.1M-IB576 | FA | 2018-02-05 | 2018-02-19 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 2 | 2018-11-05 | Comment Sheet IP | FC | 2 | A
1381 | PP | GRT-XA00-P0GCK-106801 | 106801 | GA Drawing Make Up Demin Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B
1382 | PP | GRT-XA00-P0GKB-106804 | 106804 | GA Drawing Auxiliary Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B
1383 | PP | GRT-XA00-P0LCQ-106800 | 106800 | GA Drawing Sump Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B
1384 | PP | GRT-XA00-P0LCQ-106802 | 106802 | GA Drawing Blow Down Transfer Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B
1385 | PP | GRT-XA00-P0PCC-106803 | 106803 | GA Drawing Service Water Pump | FI | 2018-02-07 | 2018-02-21 | 2018-02-07 | GRT-PP-IP-DT-180414 | FC | 0 | 2018-02-19 | Comment Sheet IP | FC | 0 | B
1386 | PP | GRT-XW03-P0PCH-156393 | 156393 | TECHNICAL INFORMATION ACWP IMPRESS CURRENT CATHODIC PROTECTION | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | GRT-PP-IP-DT-191511 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 0 | A
1387 | PP | GRT-XW03-P0PCH-156394 | 156394 | TECHNICAL INFORMATION HEAT EXCHANGER IMPRESS CURRENT CATHODIC PROTECTION | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | GRT-PP-IP-DT-191511 | FC | 0 | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | 0 | A
1388 | PP | GRT-XW03-YD00-156395 | 156395 | Cathodic Protection System ACWP | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | Mini DRM 28-29 Nov 2019 | FC | 0 | 2019-11-29 | MoM Mini DRM 28-29 Nov 2019 |  | 0 | A
1389 | PP | GRT-YD00-P0PCH-156396 | 156396 | ICCP (IMPRESSED CURRENT CATHODIC PROTECTION) FOR HEAT EXCHANGER | FA | 2019-10-12 | 2019-11-11 | 2019-10-12 | Mini DRM 28-29 Nov 2019 | FC(D) | C |  |  |  |  | A
1390 | PP | GRT-XW03-P0ZEN-156275 | 156275 | 150kV Grati Switchgear Calculation Note Compatibility CVT | FA | 2019-10-30 | 2019-11-29 | 2019-11-29 | GRT-PP-IP-DT-191510 | FC | 1 | 2019-11-29 | MOM MINI DRM 28-29NOV19 | FC | 1 | B
1391 | PP | GRT-XW03-P0ZEN-156212 | 156212 | 150kV Grati Switchgear Outdoor Installation Busbar-Section | FA | 2018-04-02 | 2018-05-02 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | A
1392 | PP | GRT-YM02-P0ZEN-156207 | 156207 | 150kV Grati Switchgear Indoor Installation Control BLDG Equipment Layout | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
1393 | PP | GRT-CA07-P0ZEN-179031 | 179031 | U-Ditch Precast Cable Trench Stability | FA | 2018-04-02 | 2018-05-02 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | B
1394 | PP | GRT-CA07-P0ZEN-179033 | 179033 | ADDITIONAL WINGWALL INTAKE BLOCK 2 STABILITY | FA | 2018-04-02 | 2018-05-02 | 2018-05-02 | GRT-PP-IP-DT-180561 | FC | 0 | 2018-05-18 | Comment Sheet IP | FC | 0 | B
1395 | PP | GRT-XW03-P0ZEN-156191 | 156191 | 150KV GRATI SWITCHGEAR CALCULATION NOTE STEEL STRUCTURE – EQUIPMENT SUPPORT | FA | 2018-10-22 | 2018-11-21 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC(D) | B | 2018-11-05 | Comment Sheet IP | FA | B | A
1396 | PP | GRT-CA07-P0ZEN-179036 | 179036 | CALCULATION REPORT CABLE TRENCH | FA | 2018-04-18 | 2018-05-18 | 2018-05-18 | GRT-PP-IP-DT-180598 | FC | 0 | 2018-05-23 | Comment Sheet IP | FC | 0 | A
1397 | PP | GRT-DD02-P0ZEN-156400 | 156400 | Island Mode Operation (Commissioning Procedure) | FA | 2019-04-03 | 2019-05-03 | 2019-05-03 | GRT-PP-IP-DT-191169 | FC | 0 |  | Deem to approved |  |  | A
1398 | PP | GRT-DD02-P0ZEN-156401 | 156401 | Blackout Procedure (Commissioning Procedure) | FA | 2018-09-22 | 2018-10-22 | 2018-10-22 | GRT-PP-IP-DT-180824 | FC | 0 |  | Deem to approved |  |  | A
1399 | PP | GRT-YK08-P0SMM-146538 | 146538 | General Arrangement Rail A75 Overhead Crane | FA | 2018-07-24 | 2018-08-23 | 2018-08-23 | GRT-PP-IP-DT-180740 | FC | 0 | 2018-08-31 | Comment Sheet IP | FC | 0 | A
1400 | PP | GRT-YK08-P0SMM-146555 | 146555 | Detail Installation Rail A75 Overhead Crane | FA | 2018-07-24 | 2018-08-23 | 2018-08-23 | GRT-PP-IP-DT-180740 | FC | 0 | 2018-08-31 | Comment Sheet IP | FC | 0 | A
1401 | PP | GRT-XW03-P0ZEN-156352 | 156352 | SURGE ARRESTER OUTLINE DRAWING PACKAGE | FA | 2018-12-31 | 2019-01-30 | 2019-01-30 | GRT-PP-IP-DT-190970 | FC | 0 | 2019-02-26 | 10/061/GRT/UPR/2018 | FC | 0 | A
1402 | PP | GRT-XW03-P0ZEN-156353 | 156353 | CIRCUIT BREAKER OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A
1403 | PP | GRT-XW03-P0ZEN-156354 | 156354 | CURRENT TRANSFORMER OUTLINE DRAWING PACKAGE | FA | 2018-12-31 | 2019-01-30 | 2019-01-30 | GRT-PP-IP-DT-190970 | FC | 0 | 2019-02-26 | 10/061/GRT/UPR/2018 | FC | 0 | A
1404 | PP | GRT-XW03-P0ZEN-156355 | 156355 | DISCONNECTOR SWITCH OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A
1405 | PP | GRT-XW03-P0ZEN-156356 | 156356 | CAPACITOR VOLTAGE TRANSFORMER OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A
1406 | PP | GRT-XW03-P0ZEN-156357 | 156357 | DISCONNECTOR SWITCH with ES OUTLINE DRAWING PACKAGE | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A
1407 | PP | GRT-HM03-P0EBM-135647 | 135647 | HVAC PACKAGE | FA | 2019-03-26 | 2019-04-25 | 2019-04-25 | GRT-PP-IP-DT-191161 | FC | 0 | 2019-05-09 | 029/061/GRT/UPR/2019 | FC | 0 | A
1408 | PP | GRT-YS01-POLDY-155853 | 155853 | Schematic Diagram for WTP (Mixed Bed) | FA | 2018-10-10 | 2018-11-09 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 0 | 2018-11-09 | Comment Sheet IP | FC | 0 | A
1409 | PP | GRTBP-YS00-POGCK-155856 | 155856 | Instrument Connection Diagram for WTP (Mixed Bed) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00033) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
1410 | PP | GRT-YS00-POGCK-155951 | 155951 | ELECTRICAL CONNECTION DIAGRAM FOR EC | FA | 2018-09-25 | 2018-10-25 | 2018-10-25 | GRT-PP-IP-DT-180832 | FC | 0 | 2018-10-25 | Comment Sheet IP | FC | 0 | A
1411 | PP | GRT-YS00-POGCK-155952 | 155952 | INSTRUMENT CONNECTION DIAGRAM FOR EC | FA | 2018-10-10 | 2018-11-09 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 0 | 2018-11-09 | Comment Sheet IP | FC | 0 | A
1412 | PP | GRT-YS01-POGDY-155949 | 155949 | SCHEMATIC DIAGRAM FOR EC | FA | 2018-10-10 | 2018-11-09 | 2018-11-09 | GRT-PP-IP-DT-180849 | FC | 0 | 2018-11-09 | Comment Sheet IP | FC | 0 | A
1413 | PP | GRT-YS00-P0GCK-155855 | 155855 | ELECTRICAL CONNECTION DIAGRAM FOR MIXED BED | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1414 | PP | GRT-YD00-P0GD-155839 | 155839 | PANEL ARRANGEMENT (LAYOUT DRAWING) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1415 | PP | GRT-YS01-P0ZEN-156277 | 156277 | 150KV GRATI SWITCHGEAR FRONT AND INTERNAL VIEW ENERGY METER PANEL | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1416 | PP | GRT-YS01-P0ZEN-156278 | 156278 | 150KV GRATI SWITCHGEAR SCHEMATIC DIAGRAM ENERGY METER PANEL | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1417 | PP | GRT-XW03-P0ZEN-156182 | 156182 | 150KV GRATI GENERAL ARRANGEMENT MARSHALLING KIOSK | FA | 2018-10-09 | 2018-11-08 | 2018-11-08 | GRT-PP-IP-DT-180852 | FC | 0 | 2018-11-14 | Comment Sheet IP | FC | 0 | A
1418 | PP | GRT-YD00-YM02-156410 | 156410 | GENERAL ARRANGEMENT DIFFERENTIAL PROTECTION OVERALL & UAT SWITCHBOARD | FA | 2018-12-17 | 2019-01-16 | 2019-01-16 | GRT-PP-IP-DT-190931 | FC | 0 | 2019-02-01 | 006/061/GRT/UPR/2019 | FC | 0 | A
1419 | PP | GRT-MA01-P0ZEN-165582 | 165582 | SYSTEM CONFIGURATION OF CLOCK SYSTEM | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1420 | PP | GRT-YS02-P0ZEN-165581 | 165581 | [Instrument General] INSTRUMENT TERMINATION DIAGRAM FOR ALL AREA | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1421 | PP | GRT-YD00-P0ZEN-165683 | 165683 | GENERAL ARRANGEMENT LOCAL PANEL FIRE FIGTHING | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1422 | PP | GRTBP-YD00-P0GD-155935 | 155935 | PANEL ARRANGEMENT OF ELECTROCHLORINATION | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1423 | PP | GRT-YS01-P0ZEN-156358 | 156358 | 150KV GRATI SWITCHGEAR 400/230V AC DISTRIBUTION BOARD | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1424 | PP | GRT-YS01-P0ZEN-156359 | 156359 | 150KV GRT DC DISTRIBUTION BOARD | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1425 | PP | GRT-YT01-P0UZA-156405 | 156405 | CALCULATION CATHODIC PROTECTION FOR THERMAL BARRIER | FA | 2019-01-15 | 2019-02-14 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC(D) | B | 2019-02-08 | 009/061/GRT/UPR/2019 | FA | B | A
1426 | PP | GRT-CC03-P0PAD-175181 | 175181 | Outfall Stop Log (include calculation) | FA | 2019-03-10 | 2019-04-09 | 2019-04-09 | GRT-PP-IP-DT-191138 | FC | 0 | 2019-04-24 | 028/061/GRT/UPR/2019 | FC | 0 | A
1427 | PP | GRT-CC09-P0UZA-175451 | 175451 | Foundation Support NSPB | FA | 2019-01-20 | 2019-02-19 | 2019-02-19 | GRT-PP-IP-DT-191003 | FC | 0 | 2019-03-04 | 015/061/GRT/UPR/2019 | FC | 0 | A
1428 | PP | GRT-CC09-P0UZA-175452 | 175452 | Calculation Sheet for Foundation Support NSPB | FA | 2019-01-20 | 2019-02-19 | 2019-02-19 | GRT-PP-IP-DT-191003 | FC | 0 | 2019-03-04 | 015/061/GRT/UPR/2019 | FC | 0 | A
1429 | PP | GRT-CC03-POUMA-175592 | 175592 | Steam Turbine Building Condensate Pump Foundation Detail (include attachment calculation) | FA | 2018-12-25 | 2019-01-24 | 2019-01-24 | GRT-PP-IP-DT-190954 | FC | 0 | 2019-01-24 | 005/061/GRT/UPR/2018 | FC | 0 | A
1430 | PP | GRT-CA01-P0UMA-175255 (1 OF 2) | 175255 | Steam Turbine Building Mezzanine Floor Plan El. +11.604 (T.O.C) Slab Schedule and Sections | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A
1431 | PP | GRT-CA01-P0UMA-175255 (2 OF 2) | 175255 | Steam Turbine Building Lube Oil and Mezzanine Local Platform Foundation Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A
1432 | PP | GRT-CA01-P0UMA-175256 (1 OF 2) | 175256 | Steam Turbine Building Operating Plan El. +17.054 (T.O.C) Slab Schedule, Section and Details | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A
1433 | PP | GRT-CA01-P0UMA-175256 (2 OF 2) | 175256 | Steam Turbine Building Operating Local Platform Foundation Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A
1434 | PP | GRT-YM02-P0UCA-175452 | 175452 | Arrangement Support NSPB (include calculation) | FA | 2019-03-10 | 2019-04-09 | 2019-04-09 | GRT-PP-IP-DT-191138 | FC | 0 | 2019-04-24 | 028/061/GRT/UPR/2019 | FC | 0 | A
1435 | PP | GRT-YS00-P0GCK-145938 | 145938 | Layout Busduct Chlorination | FA | 2019-05-27 | 2019-06-26 | 2019-06-26 | GRT-PP-IP-DT-191223 | FC | 0 |  |  |  |  | A
1436 | PP | GRT-YE00-P0GAC-145940 | 145940 | Data Sheet Busduct | FA | 2019-02-04 | 2019-03-06 | 2019-03-06 | GRT-PP-IP-DT-191053 | FC | 0 | 2019-03-13 | 019/061/GRT/UPR/2019 | FC | 0 | A
1437 | PP | GRT-XW03-P0PAC-156397 | 156397 | Chatodic Protection System for Intake Screen | FA | 2019-11-29 | 2019-12-29 | 2019-11-29 | MINI DRM 28-29NOV19 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | B | B
1438 | PP | GRT-XW03-P0ZEN-156180 | 156180 | 150KV GRT Switchgear Calculation Note Protection Setting | FA | 2019-01-15 | 2019-02-14 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC(D) | A | 2019-02-08 | 009/061/GRT/UPR/2019 | FA | A | B
1439 | PP | GRT-YS01-P0ZEN-156198 | 156198 | 150KV GRT General Arrangement Protection Diameter X & 1 Switchboard | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1440 | PP | GRT-YT01-P0UZA-156407 | 156407 | Layout Cathodic Protection for Thermal Barrier | FA | 2019-01-15 | 2019-02-14 | 2019-01-15 | GRT-PP-IP-DT-190930 | FC(D) | A | 2019-02-08 | 009/061/GRT/UPR/2019 | FA | A | A
1441 | PP | GRT-YD05-P0GD-165937 | 165937 | HMI GRAPHICS ELECTROCLORINATION | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1442 | PP | GRT-YL01-P0GD-161042 | 161042 | IO LIST FOR EC | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1443 | PP | GRT-YL01-P0LD-165846 | 165846 | IO LIST FOR WTP | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1444 | PP | GRT-YL25-P0GD-165943 | 165943 | MODBUS LIST FOR EC | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1445 | PP | GRT-YL25-P0LD-165847 | 165847 | MODBUS LIST FOR WTP | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1446 | PP | GRT-YD05-P0LD-135841 | 135841 | HMI GRAPHICS WTP | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00037) | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
1447 | PP | GRT-YU01-P0ZEN-156411 | 156411 | SINGLE LINE DIAGRAM & LOGIC GT AND UNIT AUXILIARY TRANSFORMER PROTECTION | FA | 2019-01-23 | 2019-02-22 | 2019-02-22 | GRT-PP-IP-DT-191010 | FC | 0 |  | Deem to approved | FC |  | A
1448 | PP | GRT-CA01-P0UMA-175257 (1 OF 3) | 175257 | Steam Turbine Building Electrical Room Floor Plan Slab Schedule, Sections and Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A
1449 | PP | GRT-CA01-P0UMA-175257 (2 OF 3) | 175257 | Steam Turbine Building Deaerator and Battery Room Floor Plan Section and Details | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | MINI DRM_13-15MAR2019 | FC | 1 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 1 | A
1450 | PP | GRT-CA01-P0UMA-175257 (3 OF 3) | 175257 | Steam Turbine Building Deaerator Local Platform Foundation Detail | FA | 2019-01-07 | 2019-02-06 | 2019-02-06 | GRT-PP-IP-DT-190977 | FC | 0 | 2019-02-13 | 011/061/GRT/UPR/2019 | FC | 0 | A
1451 | PP | GRT-YS18-P0PAC-156398 | 156398 | CIRCUIT AND WIRING DIAGRAM MCC & PLC FOR INTAKE SCREEN | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1452 | PP | GRT-YD00-P0GAD-125625 | 125625 | CW PUMP AUXILIARY UNIT PACKAGE | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1453 | PP | GRT-YT01-P0UGD-115853 | 115853 | Process Data Sheet for Aux Service Water Tank | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1454 | PP | GRT-HM01-P0UGD-125453 | 125453 | [WTP] WTP Building HVAC Equipment Layout | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1455 | PP | GRT-HM01-P0UGD-125454 | 125454 | [WTP] WTP Building HVAC Ducting Layout | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1456 | PP | GRT-YM03-P0LD-160040 | 160040 | Instrumnet Arrangement for WTP (MIXED BED) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1457 | PP | GRT-YM03-P0GD-161036 | 161036 | Instrument Arrangement for Electro Chlorination | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-19080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1458 | PP | GRT-YS01-P0ZEN-156259 | 156259 | Instrument Substation Automation System | FA | 2019-03-08 | 2019-04-07 | 2019-03-08 | GRT-PP-IP-DT-191035 | FC(D) | A |  |  |  | A | A
1459 | PP | GRT-YD00-P0ZEN-165690 | 165690 | Panel Arrangement Intake Electrical Building | FA | 2019-05-27 | 2019-06-26 | 2019-06-26 | GRT-PP-IP-DT-191234 (DCR 00047) | FC | 0DCR1 | 2019-07-04 | 037/061/GRT/UPR/2019 |  | 0DCR1 | A
1460 | PP | GRT-CV03-P0PAC-165695 | 165695 | INSTRUMENT DATA SHEET FOR CLAW SCREEN | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1461 | PP | GRT-YR02-P0BCA-165703 | 165703 | JUNCTION BOX OUTLINE DRAWING | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1462 | PP | GRT-YR02-P0BCA-165702 | 165702 | MOV OUTLINE DRAWING | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | B
1463 | PP | GRT-YR05-P0ZEN-165692 | 165692 | OUTLINE DRAWING FIRE FIGHTING SYSTEM | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1464 | PP | GRT-YS01-P0ZEN-165687 | 165687 | LDC SYSTEM ARCHITECTURE | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1465 | PP | GRT-XG02-P0PAC-115131 | 115131 | Piping & Instrument Diagram for Sea Water Intake | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00024) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
1466 | PP | GRT-XG02-P0PAC-115132 | 115132 | Piping & Instrumentation Diagram for Circulating Sea Water Cooling System | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 (DCR 00024) | FC | 2 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 2 | A
1467 | PP | GRT-YK00-P0PAC-165689 | 165689 | Hook Up for BOP Area | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1468 | PP | GRT-YR05-P0ZEN-165691 | 165691 | Data Sheet for Fire Alarm System | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1469 | PP | GRT-YR02-P0ZEN-165691 | 165691 | Data Sheet Equipment for Clock System | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1470 | PP | GRT-XK00-P0PAC-126811 | 126811 | Piping & Instrumentation Diagram Intake Screen | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1471 | PP | GRT-YT01-P0GAF-126810 | 126810 | Feed Pump Data Sheet | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1472 | PP | GRT-YD00-P0GAF-126809 | 126809 | Feed Pump Drawing (Arrangement Drawing) | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1473 | PP | GRT-XK00-P0GAC-125950 | 125950 | General Arrangement Aux Service Water Tank | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1474 | PP | GRT-YT01-P0ZEN-165127 | 165127 | Process Data Sheet for Pressure Regulating Valve | FA | 2019-02-13 | 2019-03-15 | 2019-03-15 | GRT-PP-IP-DT-191080 | FC | 0 | 2019-03-15 | MINI DRM 13-15MAR2019 | FC | 0 | A
1475 | PP | GRT-YR02-P0ZEN-156258 | 156258 | 150KV GRATI SWITCHGEAR SYSTEM FUNCTION SPEFICATION | FA | 2019-04-24 | 2019-05-24 | 2019-04-24 | GRT-PP-IP-DT-191158 | FC(D) | A | 2019-05-09 | 029/061/GRT/UPR/2019 | FA | A | B
1476 | PP | GRT-XJ00-P0ZEN-145041 | 145041 | CALCULATION SHEET FOR FIRE FIGHTING PIPE SUPPORT | FA | 2019-05-24 | 2019-06-23 | 2019-05-24 | DRM_22-24MAY2019 | FC(D) | B | 2019-05-24 | DRM_22-24MAY2019 |  | B | B
1477 | PP | GRT-XW03-P0ZEN-156351 | 156351 | 150KV SWITCHGEAR CABLE TRAY AND WIRING LAYOUT | FA | 2019-02-19 | 2019-03-21 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 0 | 2019-03-21 | MINI DRM_21MAR2019 | FC | 0 | B
1478 | PP | GRT-YE07-P0PAC-156415 | 156415 | [Intake Electrical Building] Lightning Protection Layout | FA | 2019-09-19 | 2019-10-19 | 2019-09-19 | GRT-PP-IP-DT-191389 | FC(D) | B | 2019-09-26 | APPROVED ON SITE (PLN E) |  | B | A
1479 | PP | GRT-YE07-POPAC-156416 | 156416 | [INTAKE BUIILDING] Lighting Layout & Panel Schedule | FA | 2019-08-06 | 2019-09-05 | 2019-08-06 | GRT-PP-IP-DT-191266 | FC(D) | A | 2019-08-30 | 047/061/GRT/UPR/2019 | FA | A | B
1480 | PP | GRT-YL15-P0PAC-165616 | 165616 | TCS Cable Schedule | FA | 2020-08-29 | 2020-09-28 | 2020-08-29 | As-Built | FC | 0 | 2019-11-21 | 057/061/GRT/UPR/2019 |  | B | B
1481 | PP | GRT-YD00-P0PUR-156395 | 156395 | ICCP (IMPRESSED CURRENT CATHODIC PROTECTION) FOR AUXILIARY COOLING WATER PUMP | FA | 2019-11-29 | 2019-12-29 | 2019-11-29 | GRT-PP-IP-DT-191511 | FC(D) | B | 2019-11-29 | MOM MINI DRM 28-29NOV19 |  | B | A
1482 | PP | GRT-YR02-P0BCA-165707 | 165707 | Wiring Diagram | FA | 2020-01-30 | 2020-02-29 | 2020-01-30 | GRT-PP-IP-DT-201543 | FC(D) | A | 2020-02-03 | 002-GRT-I-U-GPE-2020 |  | A | C
1483 | PP | GRT-YR02-P0BCA-165708 | 165708 | Site Acceptance Test (SAT) LDC Panel | FA | 2020-01-30 | 2020-02-29 | 2020-01-30 | GRT-PP-IP-DT-201543 | FC(D) | A | 2020-02-03 | 002-GRT-I-U-GPE-2020 |  | A | C
1484 | PP | GRT-YS02-P0PAC-165709 | 165709 | Instrument Interconnection Diagram for TCS System | FA | 2020-08-29 | 2020-09-28 | 2020-08-29 | As-Built | FC | 0 | 2020-02-03 | 002-GRT-I-U-GPE-2020 |  | A | C
1485 | PP | GRT-CA01-P0PAC-175182 | 175182 | Architectural Waste Disposal Building Plan, Elevation & Section, Finishing Schedule | FA | 2020-10-15 | 2020-11-14 | 2020-10-15 | As-Built | FC | 0 | 2020-03-16 | 001/061/GRT/UPR/2020 |  | B | C
1486 | PP | GRT-CA01-P0PAC-175183 | 175183 | Toilet STG | FA | 2020-10-13 | 2020-11-12 | 2020-10-13 | As-Built | FC | 0 | 2020-03-16 | 001/061/GRT/UPR/2020 |  | B | C
1487 | PP | GRT-CC03-P0UGH-175353 (2 OF 2) | 175353 | Shelter for Make Up Demin Water Pump | FA | 2020-02-28 | 2020-03-29 | 2020-02-28 | GRT-PP-IP-DT-201558 | FC(D) | B | 2020-03-16 | 001/061/GRT/UPR/2020 |  | B | C
1488 | PP | GRT-YT01-P0SG-115331 | 115331 | Data Sheet Foam Extinguisher | FA | 2020-03-15 | 2020-04-14 | 2020-04-14 | GRT-PP-IP-DT-201577 (EMAIL) | FC | 0
Formulas:
First Plan = [Final Plan]-30
First Plan = [Latest Issue to Client]
Final Plan = [Latest Issue to Client]
Final Plan = [First Plan]+30

## Sheet1 (hidden)
156284
156132