## Sheet1
Document No | Title | FA | FC
GRT-YF00-P0ZEN-161404 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Warm Start-up | 2017-08-18 | 2017-11-16
GRT-YR02-P0ZEN-156254 | 150KV Grati Switchgear Capacotator Voltage Transformer Tecnical Particular & Guarantee | 2017-10-05 | 2017-10-05
GRT-CV03-P0ZEN-163705 | [Instrument Installation materials(DHI)]_Technical Specification for Instrument Installation Materials | 2017-07-19 | 2017-10-31
GRT-XJ00-P0LBG-140003 | Piping ISO (Large Bore) - Aux. Steam | 2017-06-16 | 2018-01-31
GRT-CC00-P0UGD-145306 | [WTP] Piping Layout Drawing for Water Treatment Area | 2017-02-28 | 2017-03-30
GRT-XB02-P0MAJ-460211 | Foundation Drawing For Water Box Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-CC03-P0UZA-175428 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | 2017-07-20 | 2017-03-30
GRT-DD00-P0BAA-156306 | Type Test Reports for 15.75kV IPBD | 2017-10-09 | 2017-11-08
GRT-YE07-P0UGD-155310 | [WTP] Grounding Wiring Layout | 2017-03-22 | 2017-04-21
GRT-CA01-P0UMA-175254 | [STG BUILDING] Foundation Framing Elevation | 2017-03-07 | 2017-04-06
GRT - YL16 - P0LD - 155848 | Cable Schedule Electrical for WTP | 2018-02-02 | 2018-02-16
GRT-CC03-P0UMA-175599 | Cable Trench and Duct Bank Lay out Area 2 | 2017-11-21 | 2017-12-21
GRT-YS18-P0LB-111111 | [Bypass Valve & PRDS]_Pneumatic Diagram | 2017-07-14 | 2017-10-12
GRT-YF00-P0ZEN-165570 | Instrument Control Logic for Raw Water System | 2017-10-24 | 2017-10-24
GRT-XB02-P0GCK-135835 | FOUNDATION LAYOUT | 2017-07-21 | 2017-08-20
GRT-YD00-P0MAG-410104 | Cathodic Protection System for Condenser_The Location of Anode (Outlet Waterbox) DCR 0008 | 2019-10-14 | 2019-11-13
GRT-DN02-P1ZEN-830026 | [Commissioning Procedure] Reliability Test | 2018-04-30 | 2018-06-30
GRT-DN02-P1ZEN-830022 | [Commissioning Procedure] Capacity Test | 2018-04-30 | 2018-06-30
GRT-YM02-P0UCA-155412 | Electrical Room Section & Detail Cable Tray Layout | 2017-06-14 | 2017-07-14
GRT-FF01-P0SGA-133002 | [Fire Fighting System] Water Spray System Plan for STG Enclosure Inside | 2018-06-15 | 2018-09-14
GRT-YL19-P0MA-200038 | [STG]_Electrical load list | 2017-03-28 | 2017-07-28
GRT-DA06-P0MAJ-460223 | Lubricant List For Water Box Vacuum Pump | 2017-07-14 | 2017-09-08
GRT-YR05-P0BYA-165649 | DCS Outline Drawing of GWC | 2017-11-17 | 2017-12-19
GRT-XG02-P0GCK-135841 | P & ID Mixed BED System | 2017-10-19 | 2017-11-18
GRT-YR02-P0ZEN-155063 | [Electrical General] Datasheet for Emergency Diesel Generator | 2017-03-07 | 2017-04-06
GRT-XW03-P0ZEN-156180 | 150KV GRT Switchgear Calculation Note Protection Setting | 2019-01-15 | 2019-02-14
GRT-YF00-P0ZEN-161302 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Typical Function | 2017-04-14 | 2017-07-31
GRT-XW03-P0SG-115387 | [Fire Fighting System] Process Calculation for Jockey Pump | 2017-03-20 | 2017-04-19
GRT-XG05-P0ZEN-110001 | [Plant Overall]_HEAT BALANCE DIAGRAMS | 2017-02-10 | 2017-07-14
GRT-XK00-P0MAJ-460217 | Coupling Drawing For Water Box Vacuum Pump | 2017-07-21 | 2017-09-08
GRT-US02-P0MJY-156156 | Local Electrical Panel Bom and Drawing | 2018-02-05 | 2018-02-19
GRT-CA03-P0UMA-175268 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SD & SE | 2017-03-07 | 2017-04-06
GRT-YS00-P0ZEN-163305 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Modulating Control Actuator | 2017-03-03 | 2017-05-31
GRT-XG02-P0UGD-115286 | [WTP] Piping and instrumentation Diagram for Auxiliary Service Water System | 2017-02-21 | 2017-03-23
GRT-YK09-P0MA-200026 | [STG]_Line and Neutral Cubicles | 2017-11-11 | 2018-03-10
GRT-DC01-P0GDN-125916 | Data Sheet Acid Cleaning Pump | 2017-09-14 | 2017-10-14
GRT-YS05-P0ZEN-162704 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Instrument Rack and Junction Box | 2017-03-17 | 2017-07-31
GRT-XL00-P0MAG-410003 | Condenser_Connection List | 2017-02-10 | 2017-05-10
GRT-YF00-P0MAJ-161313 | [Condenser Vacuum Pump System _I&C_Loop]_Control Loop Diagram for BOP | 2017-04-28 | 2017-07-31
GRT-YS01-P0BYA-165658 | GTCS-Schematic Diagram of GWC | 2017-12-05 | 2017-12-19
GRT-YL01-P0UGD-165334 | [DCS] I/O List for Raw Water System | 2017-02-28 | 2017-03-30
GRT-YL01-P0UGD-165333 | [DCS] I/O List for Demin Makeup System | 2017-02-28 | 2017-08-16
GRT-YR02-P0AT-156106 | Technical Specification UAT 15kV | 2017-10-06 | 2017-11-05
GRT-YK08-P0PAH-440003 | Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | 2017-04-01 | 2017-10-31
GRT-XW03-P0PAC-156397 | Chatodic Protection System for Intake Screen | 2019-11-29 | 2019-12-29
GRT-XB02-P0QC-130009 | [Chemical Dosing System]_FOUNDATION AND LOADING DATA | 2017-08-10 | 2017-11-22
GRT-YQ01-P0ZEN-155050 | [Electrical General] Lighting and Receptacle Panel Schedule and Connection Diagram for Oufall Area | 2017-06-22 | 2017-07-22
GRT-YV02-P0QC-130017 | [Chemical Dosing System]_INTERCONNECTION WIRING DIAGRAM | 2017-09-09 | 2017-12-22
GRT-DA06-P0ZEN-115001 | [Process General] Line List | 2017-04-25 | 2017-05-25
GRT-YF00-P0ZEN-161202 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Typical Function | 2017-04-14 | 2017-07-31
GRT-XG02-P0PAH-440051 | CCW HEX Tube Cleaning System_P & I Diagram | 2017-04-01 | 2017-10-31
GRT-XS00-P0PG-110405 | [Closed cooling water system]_SYSTEM DESCRIPTION | 2017-02-28 | 2017-07-14
GRT-YT02-P0GD-165929 | Data Sheet Temperatur Transmitter | 2017-07-21 | 2017-08-20
GRT-YS01-P0ZEN-165124 | [Instrument General] CCTV Block Diagram | 2017-04-22 | 2017-05-22
GRT-YL22-P0PGB-113108 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | 2017-08-12 | 2017-11-10
GRT-YD00-P0UGD-120033 | Bottom Plate Arrangement Section & Detail | 2017-11-14 | 2017-11-14
GRT-YK00-P0MA-200034 | [STG]_Hook ups | 2017-05-14 | 2017-08-14
GRT-YK09-P0MA-200051 | [STG]_Operating instructions for the steam turbine and accessories | 2018-02-28 | 2018-05-22
GRT-XN00-P0LDB-130043 | [Condensate Filter System]_VALVE LIST | 2017-06-26 | 2017-10-08
GRT-XK00-P0ZEN-144905 | Outline Drawing for Piping LP Manual Forging Valve | 2017-11-15 | 2017-12-01
GRTBCP-YS01-P0BJF-156065 | Schematic Diagram BOP Essential MCC | 2018-01-26 | 2018-02-25
GRT-DN02-P0PC-830003 | [Commissioning Procedure] Auxiliary Cooling Water System | 2018-01-30 | 2018-03-30
GRT-YD08-P0UMA-164311 | [Steam Turbine Building_INC_ILD]_BOP_Instrument Location Drawing | 2017-07-25 | 2017-11-05
GRT-YU02-P0SCA-120014 | [Air Compressor]_SINGLE LINE DIAGRAM | 2017-05-20 | 2017-09-17
GRT-YS01-P0BYA-165657 | GTCS-Schematic Diagram of GTC | 2017-12-05 | 2017-12-19
GRT-CV03-P0ZEN-163704 | [Control Valves(DHI)]_Technical Specification & Datasheet for Control Valve - BOP | 2017-07-21 | 2017-10-31
GRT-YF00-P0MA-200036 | [STG]_Consumer schemes | 2017-05-14 | 2017-09-13
GRT-YK08-P0LB-111101 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR BYPASS AND PRDS | 2017-07-14 | 2017-10-12
GRT-CV03-P0ZEN-163703 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Flow Element - BOP | 2017-07-31 | 2017-10-31
GRT-MA02-P0ZEN-161121 | [DCS]_LAN Configuration Diagram | 2017-03-31 | 2017-06-30
GRT-DC01-P0GDN-125917 | Data Sheet Dilunation air Blower | 2017-09-14 | 2017-10-14
GRT-YR05-P0BYA-165650 | DCS Outline Drawing of SRS | 2017-10-31 | 2017-11-30
GRT-YK09-P0MA-200030 | [STG]_DC motor starter | 2017-11-11 | 2018-03-10
GRT-YT01-P0MJA-156160 | Diesel Engine Data Sheet | 2017-12-11 | 2018-01-10
GRT-YL00-P0MAJ-460227 | Instrument Data sheet For Water Box Vacuum Pump | 2017-07-14 | 2017-09-08
GRT-CA06-P0UGX-175212 | [Chlorination System] Calculation Sheet for Chlorination System Building | 2017-06-23 | 2017-07-23
GRT-YT01-P0LAC-122505 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | 2017-04-20 | 2017-07-20
GRT-YR02-P0ZEN-155069 | [Electrical General] Datasheet for Cable and Wire | 2017-03-08 | 2017-04-07
GRT-CQ02-P0LDB-130058 | [Condensate Filter System]_O&M MANUAL | 2017-11-23 | 2018-03-07
GRT-YT001-P0ZEN-145548 | General Arrangement Butterfly MOV Valve | 2017-11-20 | 2017-11-20
GRT-DN02-P1ZEN-830024 | [Commissioning Procedure]_Load Rejection | 2020-03-20 | 2020-04-20
GRT-YL25-P0LD-165847 | MODBUS LIST FOR WTP | 2019-02-13 | 2019-03-15
GRT-YD00-P0PAC-125141 | [Circulating Water Pump] GA Drawing Travelling Screen | 2017-07-15 | 2017-08-14
GRT-CN00-P0ZEN-110106 | [Steam drain system]_Flash tank calculation | 2017-03-30 | 2017-07-14
GRT-CC07-P0UGD-175465 | Calculation Sheet for Raw Water Tank Foundation | 2017-09-28 | 2017-09-28
GRT-YF00-P0ZEN-161312 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Miscellaneous System | 2017-04-28 | 2017-07-31
GRT-YF00-P0PAH-440004 | Control Logic for CTCS & Debris Filter | 2017-06-01 | 2017-10-31
GRT-YQ01-P0UAG-155361 | [Transformer] Lighting and Receptale Wiring Layout | 2017-06-23 | 2017-07-23
GRT-YD00-P0AT-156283 | Surge Arrester Drawing of Station Service Transformer 25MVA | 2017-10-19 | 2017-11-18
GRT-XJ00-P0MAA-143013 | Piping ISO (Small Bore) - ST Misc. | 2017-07-28 | 2018-01-31
GRT-YD00-P0ZEN-120003 | General Arrangement Make up Demin Tank Capacity 1000 M3 | 2017-11-09 | 2017-10-10
GRT-XJ00-P0QUA-143017 | Piping ISO (Small Bore) - Sampling | 2017-07-28 | 2018-01-31
GRT-YF00-P0ZEN-165572 | Instrument Control Logic for Demin Make up System | 2017-12-12 | 2017-12-12
GRT-YD00-P0PAC-165158 | [Circulating Water Pump] Instrument Cable Wiring Layout | 2017-03-11 | 2017-04-10
GRT-YR02-P0BCA-165703 | JUNCTION BOX OUTLINE DRAWING | 2019-02-13 | 2019-03-15
GRT-YD00-P0LCB-121001 | [Condensate Extraction Pump]_GENERAL ARRANGEMENT DRAWING | 2017-04-20 | 2017-07-20
GRT-YD00-P0QJA-111000 | [N2 Gas System]_General Arrangement Drawing | 2017-08-08 | 2017-11-06
GRT-CC00-P0UMA-145453-1 | Piping Layout Drawing Steam Turbine Generator Area | 2017-09-13 | 2017-09-13
GRT-YT02-P0LD-165823 | DATA SHEET FLOW TRANSMITTER | 2017-10-18 | 2017-11-17
GRT-YF00-P0ZEN-165574 | INSTRUMENT CONTROL LOGIC FOR AUXILIARY SERVICE WATER SYSTEM | 2017-11-13 | 2017-12-13
GRT-YU04-P0ZEN-161003 | [INC_Plant_Overall_Design]_Plant Control Block Diagram | 2017-03-31 | 2017-07-14
GRT-CC03-P0UGD-175357 | Sum Pit at STG Area Foundation Plan, Section and Detail | 2017-06-23 | 2017-07-23
GRT-YU01-P0BFC-156029 | Single Line Diagram LV Switchgear 3 | 2018-01-26 | 2018-02-25
GRT-DE00-P0ZEN-145031 | [Piping General] Piping Fabrication and Installation | 2017-03-15 | 2017-04-14
GRT-XJ00-P0TEM-140011 | Piping ISO (Large Bore) - Steam blowing & flushing | 2018-03-30 | 2018-06-01
GRT-YK08-P0PAH-440052 | CCW HEX Tube Cleaning System_Outline Drawing | 2017-04-01 | 2017-10-31
GRT-YT01-P1H-300058 | [HRSG]_PERFORMANCE AND OPERATIONAL DATA | 2017-03-23 | 2017-06-20
GRT-DA06-P0MAJ-460222 | Utility Consumption List For Water Box Vacuum Pump | 2017-08-08 | 2017-11-08
GRT-XG02-P0SC-120002 | [Compressed air system]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | 2017-02-06 | 2017-07-14
GRT-YR01-P0ZEN-110107 | [Plant Overall]_STEAM FLUSHING - DIAGRAM | 2018-04-06 | 2018-06-15
GRT-YD00-P0UGD-165328 | [WTP] Instrument Main Cable & JB Layout for Water Treatment System | 2017-03-22 | 2017-04-21
GRT-YS01-P0ZEN-156358 | 150KV GRATI SWITCHGEAR 400/230V AC DISTRIBUTION BOARD | 2019-02-13 | 2019-03-15
GRT-YF01-P0ZEN-161004 | [INC_Plant_Overall_Design]_Plant Protection & Interlock Diagram | 2017-04-07 | 2017-06-30
GRT-YE00-P0QC-130021 | [Chemical Dosing System]_CABLE TRAY LAYOUT DRAWING | 2017-09-09 | 2017-12-22
GRT-XK00-P0LBA-144001 | Support DWG (Large Bore) - HP Steam | 2017-08-15 | 2017-11-30
GRT-DN02-P0LC-830005 | [Commissioning Procedure] Condensate System | 2018-01-30 | 2018-03-30
GRT-YT01-P0BJJ-156081 | Data Sheet Feeder UPS-1 | 2017-11-24 | 2017-12-24
GRT-YD07-P0BYA-165671 | DCS Input / Output Signal List of H/W | 2017-10-26 | 2017-11-25
GRT-XJ00-P0LCM-143004 | Piping ISO (Small Bore) - Steam drain | 2017-07-07 | 2018-01-31
GRT-CC04-P0ZEN-156238 | Common Switchgear Steel Structure Post Insulator Support H=4.5M-IB555 | 2018-02-05 | 2018-02-19
GRT-XW03-P0SC-120006 | [Compressed air system]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | 2017-02-06 | 2017-07-14
GRT-YF00-P0QU-130033 | [Sampling System]_CONTROL LOOP & LOGIC DIAGRAM | 2017-09-18 | 2017-12-31
GRT-DF04-P0MA-200018 | [STG]_Stress analysis of piping | 2017-10-25 | 2018-03-24
GRT-UE00-P1H-300007 | [HRSG]_ARRANGEMENT OF CASING & FIELD ERECTION | 2017-04-20 | 2017-07-20
GRT-YT01-P0UGD-115289 | [WTP] Process data sheet for service water pump | 2017-02-23 | 2017-03-25
GRT-YT01-P0MAJ-460205 | Motor Data sheet and Characteristic Curves and Drawing For WBVP | 2017-07-07 | 2017-09-08
GRT-YM03-P0LD-160040 | Instrumnet Arrangement for WTP (MIXED BED) | 2019-02-13 | 2019-03-15
GRT-CC04-P0ZEN-156245 | Common Switchgear Steel StructureC.T Support-H=2.1M-IB576 | 2018-02-05 | 2018-02-19
GRT-XJ00-P0LCM-140004 | Piping ISO (Large Bore) - Steam drain | 2017-06-09 | 2018-01-31
GRT-YK08-P0MAJ-460200 | General Arrangement Drawing For Water Box Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-YT02-P0GD-165922 | Data Sheet Flow Transmitter | 2017-07-21 | 2017-08-20
GRT-UE00-P0ZEN-100004 | General Arrangement of Steam Turbine Building Mezzanine Floor | 2017-03-17 | 2018-10-01
GRT-YK09-P0MA-200033 | [STG]_Electrical system description | 2017-05-14 | 2017-08-13
GRT-YT01-P0BJK-156086 | Data Sheet Feeder UPS-2 | 2017-11-24 | 2017-12-24
GRT-YE00-P0ZEN-155042 | [Electrical General] General Area Clock System Wiring Layout | 2017-03-15 | 2017-04-14
GRT-YD00-P0AT-156304 | General Arrangement Drawing of 1000 KVA | 2017-10-09 | 2017-11-08
GRTBCP-YS01-P0BJO-156403 | Schematic Diagram HRSG PDB-02 | 2018-01-26 | 2018-02-25
GRT-YE00-P0GAC-145940 | Data Sheet Busduct | 2019-02-04 | 2019-03-06
GRT-XB00-P0MA-200003 | [STG]_Foundation - Static & Dynamic Calculation | 2017-02-28 | 2017-08-08
GRT-YK10-P0BAA-156305 | Standar Sub-assembly Drawing for 15.75kV IPBD | 2017-10-09 | 2017-11-08
GRT-DC01-P0GDN-125914 | Data Sheet Sea Water Strainer | 2017-09-14 | 2017-10-14
GRT-XJ00-P0LBA-140001 | Piping ISO (Large Bore) - HP Steam | 2017-06-09 | 2017-08-31
GRT-YF00-P0ZEN-161310 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Sampling & Chemical Dosing System | 2017-04-28 | 2017-07-31
GRT-CQ02-P0SM-123003 | [Crane & Hoist(DHI)]_HOIST_O&M MANUAL FOR HOIST | 2018-04-20 | 2018-05-31
GRTSCH-YS01-P0BAC-150006 | Electrical Diagram | 2018-02-05 | 2018-02-19
GRT-XK00-P0MAJ-460216 | Name Plate Drawing For Water Box Vacuum Pump | 2017-08-11 | 2017-09-08