## Sheet1
Document No | Title | FA | FC
GRT-YD00-P0ZEN-165105 | [Instrument General] Telephone Cable Wiring Layout | 2017-06-14 | 2017-07-30
GRT-QM03-P0ZEN-141006 | RADIOGRAPHIC EXAMINATION PROCEDURE | 2017-10-11 | 2017-11-13
GRT-XK58-P0GCK-125840 | GENERAL ARRANGEMENT NAME PLATE OF TANK | 2017-09-14 | 2017-10-14
GRT-XW03-P0ZEN-115015 | [Process General] Line Sizing Calculation | 2017-04-14 | 2017-05-14
GRT-YD00-P0ZEN-120010 | Shell Manhole Section & Detail Make Up Demin Tank | 2017-11-09 | 2017-10-10
GRT-CQ02-P0MAG-410011 | Condenser_Instruction Manuals for Erection, Installation, Operation and Maintenance | 2017-09-30 | 2017-11-30
GRT-XK00-P0ZEN-144902 | Outline Drawing for Piping HP Manual Casting Valve | 2017-11-15 | 2017-12-01
GRT-YT01-P0PCC-113004 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP MOTOR | 2017-06-05 | 2017-09-03
GRT-YS00-POGCK-155952 | INSTRUMENT CONNECTION DIAGRAM FOR EC | 2018-10-10 | 2018-11-09
GRT-XJ00-P0PGB-143008 | Piping ISO (Small Bore) - CCW | 2017-07-21 | 2018-01-31
GRT-CC07-P0UAA-175376 | [Switchyard] Calculation Sheet for Foundation | 2017-07-07 | 2017-07-06
GRT-XK00-P0GAC-125950 | General Arrangement Aux Service Water Tank | 2019-02-13 | 2019-03-15
GRT-YS00-P0ZEN-163304 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | 2017-03-03 | 2017-05-31
GRT-DC01-P0BYA-165644 | DCS Hardware Specification | 2017-11-17 | 2017-12-19
GRT-YD00-P0BRA-156358 | General Arrangement AC Distribution Board 400/230V for UPS System | 2017-11-14 | 2017-12-14
GRT-XK00-P0EGB-156154 | General Arrangement Daily Tank Drawing | 2017-10-31 | 2017-11-30
GRT-XH01-P0LDB-130046 | [Condensate Filter System]_PIPING ARRANGEMENT DRAWING | 2017-06-26 | 2017-10-08
GRT-XS00-P0SC-120004 | [Compressed air system]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | 2017-02-20 | 2017-06-20
GRT-YD16-P0UAA-155367 | [Switchyard] Cable Tray and Power Wiring Layout | 2017-06-19 | 2017-07-19
GRT-XK00-P0MAJ-460112 | Outline & Sectional Drawing For Condenser Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-YT01-P0SM-123002 | [Crane & Hoist(DHI)]_HOIST_DATA SHEETS FOR HOISTS | 2017-05-19 | 2017-08-18
GRT-YL00-P0MAG-410010 | Condenser_Instrument list and Datasheet for Condenser | 2017-07-30 | 2017-08-30
GRT-YD00-P0AT-156305 | General Arrangement Drawing of 2000 KVA | 2017-10-09 | 2017-11-08
GRT-YV02-P0AT-156114 | Layout and Schematic Diagram for Remote Tap Charger Control Panel Transformer 25MVA 15.75/6.3kV | 2017-10-18 | 2017-11-17
GRT-CA06-P0UGD-175401 | [Fire Fighting Shelter] Calculation Sheet for Fire Fighting Shelter Stricture and Foundation | 2017-07-14 | 2017-08-13
GRT-YQ01-P0UAA-155369 | [Switchyard] Lighting and Receptale Wiring Layout | 2017-06-19 | 2017-07-19
GRT-XK00-P0TEM-144011 | Support DWG (Large Bore) - Steam blowing | 2018-04-30 | 2018-06-01
GRT-CA06-P0UMA-175271 | [STG BUILDING] Calculation Sheet for Steel Structure and Foundation | 2017-03-07 | 2017-04-06
GRT - YT01 - P0GCK - 126808 | Data Sheet Sea Water Drain Pump | 2018-02-02 | 2018-02-16
GRT-XW03-P0ZEN-156243 | Switchgear Steel Structures SA Support H=2. 1M - IB573 | 2017-11-16 | 2017-12-16
GRT-XG02-P0LBA-110003 | [HP & LP steam system]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-YV02-P0PAH-440005 | Cable Connection/wiring Diagram(for power, control & instrument cable) for CTCS & Debris Filter | 2017-06-01 | 2017-10-31
GRT-CQ02-P0QU-130035 | [Sampling System]_O&M MANUAL | 2017-12-17 | 2018-03-31
GRTBCP-YS01-P0BJB-156045 | Schematic Diagram STG PDB | 2018-01-26 | 2018-02-25
GRT-YT01-P0BJ0-156312 | General Arrangement HRSG PDB-2 | 2017-11-24 | 2017-12-24
GRT-YT02-P0GD-165928 | Data Sheet Level Switch Electrochlorination | 2017-09-15 | 2017-10-15
GRT-DC01-P0GDN-125915 | Data Sheet Electrolyzer | 2017-09-14 | 2017-10-14
GRT-YQ01-P0UGD-155312 | [WTP] Lighting and Receptacle Wiring Layout | 2017-03-22 | 2017-04-21
GRT - YL16 - P0LD - 155945 | Cable Schedule Instrument for EC | 2018-02-02 | 2018-02-16
GRT-YT01-P0QC-130013 | [Chemical Dosing System]_MOTOR DATA SHEET | 2017-08-10 | 2017-11-22
GRT-DC01-P0LDP-125817 | DATA SHEET REGENERATION PUMP | 2017-10-18 | 2017-11-17
GRT-XW03-P0SG-115388 | [Fire Fighting System] Process Calculation for Fire Water Pump | 2017-03-20 | 2017-04-19
GRT-XG02-P0MAJ-460101 | P & ID For Condenser Vacuum Pump | 2017-06-16 | 2017-09-08
GRT-YF00-P0MAJ-161213 | [Condenser Vacuum Pump System _I&C_Logic]_Control Logic Diagram for BOP | 2017-04-28 | 2017-07-31
GRT-YD00-P0PCC-113001 | [Aux. Cooling Water Pump]_GENERAL ARRANGEMENT DRAWING FOR AUXILIARY COOLING WATER PUMP | 2017-06-05 | 2017-09-03
GRT-XW01-P0LC-110203 | [Condensate system]_DESIGN CRITERIA | 2017-02-22 | 2017-07-14
GRT-XG02-P0LAC-122001 | [HP Feed Water Pump]_P&I DIAGRAM | 2017-04-20 | 2017-07-20
GRT-YS05-P0ZEN-162702 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Control Valve | 2017-03-17 | 2017-07-31
GRT-YR05-P0BYA-165648 | DCS Outline Drawing of GTC | 2017-11-17 | 2017-12-19
GRT-CV03-P0ZEN-162301 | [VMS]_Technical Specification & Datasheet for Vibration Monitoring System | 2017-06-09 | 2017-09-15
GRTH-YR01-P0ZEN-115471 | Hazop Study Report | 2017-06-12 | 2017-07-12
GRT-CC07-PIUHA-175610 | Calculation Sheet for Elevator Structure and Foundation | 2018-01-04 | 2018-01-04
GRT-YT01-P0BJ0-156315 | Data Sheet HRSG PDB-2 | 2017-11-24 | 2017-12-24
GRT-XK00-P0PAC-126811 | Piping & Instrumentation Diagram Intake Screen | 2019-02-13 | 2019-03-15
GRT-YD00-P1H-300041 | [HRSG]_SPEC. & DRAWING FOR SILENCER | 2017-07-20 | 2017-10-20
GRT-CC07-P0QC-130004 | [Chemical Dosing System]_CALCULATION SHEET | 2017-07-11 | 2017-10-23
GRT-HM01-P0UMA-125236 | [STG BUILDING] Steam Turbine Building HVAC Elevation, Section & Detail | 2017-03-11 | 2017-04-10
GRT-YT01-P0BJP-156317 | General Arrangement HRSG PDB-3 | 2017-11-24 | 2017-12-24
GRT-YS00-P0ZEN-163308 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Input | 2017-03-03 | 2017-05-31
GRT-YT01-P0UGD-115290 | [WTP] Process data sheet for sump pumps | 2017-04-06 | 2017-05-06
GRT-CC03-P0PAC-175170(7OF7) | [Circulating Water Pump] Circulating Water Pump Pipe Header Pedestal Detail | 2017-02-14 | 2017-03-16
GRT-YS01-P0AT-156122 | Layout and Schematic Diagram for Mashalling Kiosk Transformer 25000KVA 15.75/6.3kV | 2017-10-18 | 2017-11-17
GRT-CC04-P0ZEN-156233 | Common Switchgear Steel Structure Tower Type P1-Top Part | 2018-02-05 | 2018-02-19
GRT-YF00-P0LBG-161304 | [AUX Steam System_I&C_Loop]_Control Loop Diagram for BOP | 2017-04-14 | 2017-07-31
GRT-DN02-P1ZEN-830028 | [Commissioning Procedure] Noise Test | 2018-07-30 | 2018-10-30
GRT-CC03-P0UMA-175601 | Cable Trench and Duct Bank Detail | 2017-11-21 | 2017-12-21
GRT-XW01-P0SG-115386 | [Fire Fighting System] Specification for Fire Protection Equipment | 2017-03-20 | 2017-04-19
GRT-YK08-P0PBB-440102 | Debris Filter_Outline Drawing | 2017-04-01 | 2017-10-31
GRT-DN02-P0QU-830009 | [Commissioning Procedure] Sampling System | 2018-03-30 | 2018-05-30
GRT-XJ00-P0PAB-140007 | Piping ISO (Large Bore) - Aux. cooling water | 2017-06-23 | 2018-01-31
GRT-YT01-P1H-300061 | [HRSG]_DESH. DATASHEET & DRAWINGS | 2017-07-20 | 2017-10-20
GRT-CA01-P0UGD-175348 | [WTP] Concrete Structure Floor Plan, Section & Member Schedule | 2017-03-22 | 2017-04-21
GRT-YL01-P0ZEN-165114 | [Instrument General] Instrument Index for BOP | 2017-03-17 | 2017-04-16
GRT-CA03-P0UMA-175270 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line S11 & S12 | 2017-03-07 | 2017-04-06
GRT-CA01-P0UGX-175208 | [Chlorination System] Foundation Plan | 2017-06-23 | 2017-07-23
GRT-YS00-POGCK-155951 | ELECTRICAL CONNECTION DIAGRAM FOR EC | 2018-09-25 | 2018-10-25
GRT-XW03-P0ZEN-156221 | 150 KV Switchgear Cable List Diameter 1 | 2018-02-05 | 2018-02-19
GRT-YL16-P1H-300052 | [HRSG]_CABLE SCHEDULE | 2017-08-20 | 2017-11-20
GRT-CV03-P0ZEN-165676 | Data Sheet for Raw Water System | 2017-11-17 | 2017-12-17
GRT-XS00-P0LBA-110400 | [HP & LP steam system]_SYSTEM DESCRIPTION | 2017-02-28 | 2017-07-14
GRT-YE00-P0ZEN-155041 | [Electrical General] Standard Installation Drawing for Electrical | 2017-03-01 | 2017-03-31
GRT-CC03-P0UZA-175424(2OF2) | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pile Cap Rebar Arrangement and Section | 2017-02-28 | 2017-03-30
GRT-YL01-P0ZEN-161101 | [INC_DCS_IO]_DCS I/O Database | 2017-04-07 | 2017-06-30
GRT-YD07-P0BYA-165653 | DCS Input / Output Signal List of GTC | 2017-10-26 | 2017-11-25
GRT-YT01-P0ZEN-113401 | [MOV (Butterfly)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | 2017-08-15 | 2017-11-13
GRT - YT01 - P0GCK - 126803 | Data Sheet Service Water Pump | 2018-02-02 | 2018-02-16
GRT-YL22-P0PGB-113109 | [CCWP ]_NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 2017-08-12 | 2017-11-10
GRT-YE00-P1UHA-155214 | [HRSG] Clock System Wiring Layout | 2017-10-31 | 2017-06-20
GRT-CA01-P0PAC-175608 | Intake Electrical Building Architectural Plan, View, Section, & Finishing Schedule | 2017-10-23 | 2017-10-23
GRT-XJ00-P0QJA-143009 | Piping ISO (Small Bore) - N2 | 2017-07-21 | 2018-01-31
GRT-YL01-P0GD-161042 | IO LIST FOR EC | 2019-02-13 | 2019-03-15
GRT-DF04-P0ZEN-144514 | [Piping General]_Stress Analysis Report for Aux.steam system | 2017-06-23 | 2017-09-15
GRT-CC03-P0UMA-175277(2OF2) | [STG ] Concrete structure Insert Plate Plant and Detail | 2017-06-05 | 2017-05-07
GRT-YD00-P0UGD-165324 | [WTP] Instrument Main Cable & JB Layout for Service Water System | 2017-03-22 | 2017-04-21
GRT-YE06-P0ZEN-155047 | [Electrical General] Lightning Protection Layout for General Area | 2017-03-23 | 2017-06-10
GRT-YL00-P0ZEN-163700 | [Field Instruments(DHI)]_Field Instrument List for BOP | 2017-07-19 | 2017-10-31
GRT-XK00-P0PAB-144012 | Support DWG (Large Bore) - Cooling Water | 2017-12-31 | 2018-01-30
GRT-XJ00-P0ZEN-145041 | CALCULATION SHEET FOR FIRE FIGHTING PIPE SUPPORT | 2019-05-24 | 2019-06-23
GRT-YU01-P0ZEN-155078 | [Electrical General] Single Line Diagram for LV System | 2017-02-25 | 2017-03-27
GRT-YF02-P0SCA-120017 | [Air Compressor]_CONTROL DESCRIPTION (PHILOSOPHY) | 2017-05-20 | 2017-09-17
GRT-XK00-P0MAJ-460114 | Baseframe Drawing For Condenser Vacuum Pump | 2017-08-04 | 2017-09-08
GRT-XN00-P0ZEN-144505 | [Piping General]_Manual Valve List (BOP) | 2017-03-31 | 2017-06-30
GRT-YK08-P0PAH-440002 | Condenser Tube Cleaning System_Outline Drawing | 2017-04-01 | 2017-10-31
GRT-XG11-P0AE-156349 | Schematic Line Diagram Cable 150KV | 2018-02-05 | 2018-02-19
GRT-YF00-P0MA-200044 | [STG]_Logic diagrams for control of functional groups | 2017-09-16 | 2017-12-22
GRT-YF00-P0ZEN-161401 | [INC_PMC]_Plant Master Control Diagram | 2017-07-14 | 2017-10-12
GRT-YL22-P0LAC-122507 | [LP Feed Water Pump]_NAME PLATE DRAWING | 2017-06-20 | 2017-09-20
GRT-YQ01-P0UGX-155196 | [Chlorination System] Lighting and Receptale Wiring Layout | 2017-03-11 | 2017-04-10
GRT-YE06-P0ZEN-155046 | [Electrical General] Grounding Wiring Layout for General Area | 2017-03-10 | 2017-04-09
GRT-CA03-P0UMA-175262 | [STG BUILDING] Steam Turbine Building Steel Structure Operating Floor El +17.104 (F.F.L) | 2017-03-07 | 2017-04-06
GRT-YS01-P0QU-130034 | [Sampling System]_SCHEMATIC DIAGRAM | 2017-09-18 | 2017-12-31
GRT-CC03-P0UAA-175372 | [Switchyard] Foundation Layout | 2017-06-23 | 2017-07-23
GRT-XW01-P0SCA-120031 | [Air Compressor]_MAIN MOTOR SPECIFICATION | 2017-08-30 | 2017-10-30
GRT-DC01-P0LDR-125820 | DATA SHEET NEUTRALIZATION DISCHARGE PUMP | 2017-10-18 | 2017-11-17
GRT-CE00-P0SG-115378 | [Fire Fighting System] Escape route lay out | 2017-07-07 | 2017-07-06
GRT-YD00-P0MAG-410103 | Cathodic Protection System for Condenser_The Location of Anode (Inlet Waterbox) DCR 0008 | 2019-10-14 | 2019-11-13
GRT-YU01-P0BJA-156039 | Single Line Diagram STG Unit MCC | 2018-01-26 | 2018-02-25
GRT-XJ00-P0ZEN-145035 | [Piping General] Isometric Drawing | 2017-06-07 | 2017-07-07
GRT-YD00-P0BFA-156126 | General Arrangement NSPB-2 | 2017-11-17 | 2017-12-17
GRT-YT01-P1H-300062 | [HRSG]_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | 2017-10-20 | 2017-12-20
GRT-XG02-P0QU-130024 | [Sampling System]_P&ID | 2017-06-20 | 2017-10-02
GRT-YD00-P1H-300040 | [HRSG]_SPEC. & DRAWING FOR STACK DAMPER | 2017-07-20 | 2017-10-20
GRTBCP-YS01-P0BFC-156030 | Schematic Diagram LV Switch Gear 3 | 2018-01-26 | 2018-02-25
GRT-YD00-P0GAF-126809 | Feed Pump Drawing (Arrangement Drawing) | 2019-02-13 | 2019-03-15
GRTBP-YS00-POGCK-155856 | Instrument Connection Diagram for WTP (Mixed Bed) | 2019-02-13 | 2019-03-15
GRT-YT01-P0PAC-125142 | [Circulating Water Pump] Mech. Data Sheet for CWP Pump | 2017-02-11 | 2017-03-13
GRT-QA00-P0H-040010 | [HRSG]_WPS&PQR for HRSG HP Drum | 2017-08-29 | 2017-11-29
GRT-YT01-P0LCB-121007 | [Condensate Extraction Pump]_SUCTION STRAINER SPECIFICATION | 2017-06-20 | 2017-09-20
GRT-CA01-P0UMA-175257 (2 OF 3) | Steam Turbine Building Deaerator and Battery Room Floor Plan Section and Details | 2019-02-13 | 2019-03-15
GRT-XK00-P0PGB-144008 | Support DWG (Large Bore) - CCW | 2017-12-31 | 2018-01-30
GRT-XH01-P0UMA-144521 | [Steam Turbine Building_Piping]_Piping Arrangement | 2017-06-02 | 2017-09-29
GRT-YT01-P0BFD-156036 | Data Sheet LV Switchgear 4 | 2017-11-24 | 2017-12-24
GRT-XL00-P0ZEN-144504 | [Piping General]_Piping Specialty List (BOP) | 2017-03-31 | 2017-06-30
GRT-YR02-P0ZEN-155065 | [Electrical General] Datasheet for Auxiliary & Service Transformer | 2017-02-18 | 2017-03-20
GRT-CC03-P0UMA-175602 | Cable Trench and Duct Bank Detail | 2017-11-21 | 2017-12-21
GRT-YL01-P0UGD-165558 | DCS IO List for Waste Water Transfer System | 2017-09-08 | 2017-09-08
GRT-CC03-P0UMA-175603 | Cable Pit Foundation Detail | 2017-11-21 | 2017-12-21
GRT-YR02-P0BCA-165707 | Wiring Diagram | 2020-01-30 | 2020-02-29
GRT-YL01-P0SCA-120020 | [Air Compressor]_DATALINK INTERFACE IO LIST | 2017-05-20 | 2017-09-17
GRT-YL00-P0MAJ-460107 | Instrument list For Condenser Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-YF00-P0ZEN-161201 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram - Symbol & Legend | 2017-04-14 | 2017-07-31
GRT-YD07-P0ZEN-161122 | [DCS]_IO & Module Allocation | 2017-04-21 | 2017-07-07
GRT-FF01-P0SGA-125501 | General Arrangement Drawing Fire Pump | 2017-06-10 | 2017-10-16
GRT-YD00-P0ZEN-165109 | [Instrument General] Instrument Panel Arrangement for BOP | 2017-07-19 | 2017-08-18
GRT-YV02-P0PAH-440055 | CCW HEX Tube Cleaning System_Cable Connection/wiring Diagram(for power, control & instrument cable) | 2017-06-01 | 2017-10-31
GRT-YF02-P0SCA-120026 | [Air Compressor]_PLC PANEL DRAWING | 2017-05-20 | 2017-09-17
GRT-XG02-P1H-300020 | [HRSG]_P&I DIAGRAM | 2017-03-23 | 2017-07-14
GRT-XS00-P1H-300032 | [HRSG]_BLOWDOWN SYSTEM SUMMARY | 2017-03-23 | 2017-07-14
GRTSCH-YD00-P0BAC-150003 | Interlocking Diagram | 2018-02-05 | 2018-02-19
GRT-YK08-P0MA-200047 | [STG]_HMI design | 2017-09-16 | 2018-01-21
GRT-YT01-P0BFC-156031 | Data Sheet LV Switchgear 3 | 2017-11-24 | 2017-12-24
GRT-CC00-P0ZEN-145452 | Drawing Index Balance of Plant BOP | 2017-10-09 | 2017-10-09
GRT-DN02-P0LBA-830001 | [Commissioning Procedure] HP & LP Steam System | 2018-02-28 | 2018-04-30
GRT-YR02-P0ZEN-155074 | [Electrical General] Datasheet for Electrical Bulk Material | 2017-03-11 | 2017-06-20
GRT-YK10-P0LAC-122004 | [HP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | 2017-05-20 | 2017-08-20
GRT-YE00-P0UCA-155409 | [Electrical Room] Clock System Wiring Layout | 2017-06-14 | 2017-07-14
GRTBCP-YS01-P0BJK-156085 | Schematic Diagram Feeder UPS-02 | 2018-01-26 | 2018-02-25
GRT-YM02-P0UCA-155411 | [Electrical Room] Electrical Equipment Layout | 2017-07-16 | 2017-08-06
GRT-YD00-P0UGD-165319 | [WTP] Instrument Main Cable & JB Layout for Potable Water System | 2017-03-22 | 2017-04-21
GRT-CC03-P0PAC-175164 | [Circulating Water Pump] Circulating Water Pump Framing Plan | 2017-02-14 | 2017-03-16
GRTBCP-YS01-P0BJN-156398 | Schematic Diagram HRSG PDB-01 | 2018-01-26 | 2018-02-25
GRT-CV03-P0ZEN-165097 | [Instrument General] Data Sheet for CCTV Camera | 2017-06-14 | 2017-07-14
GRT-YE07-P0UGX-155194 | [Chlorination System] Grounding Wiring Layout | 2017-03-11 | 2017-04-10
GRT-HM01-P0UMA-125233 | [STG BUILDING] Steam Turbine Building HVAC Flow Schematic Diagram | 2017-03-11 | 2017-04-10
GRT-CC03-P0UMA-175585 | Steam Turbine Building Condenser Vacuum pump & Air Compressore Foundation Detail | 2017-10-11 | 2017-11-10
GRT-CC00-P1UHA-145454 | Piping Layout Drawing for HRSG Area | 2017-10-19 | 2017-10-19
GRT-YT01-P0BJB-156046 | Data Sheet STG PDB | 2017-11-24 | 2017-12-24
GRT-CC03-P0UAA-175373 | [Switchyard] Type 1 Foundation Plan, Section & Detail | 2017-06-23 | 2017-07-23
GRT-YL15-P0MA-200050 | [STG]_Cable list | 2017-11-20 | 2018-02-19
GRT-YL15-P0PAC-165616 | TCS Cable Schedule | 2020-08-29 | 2020-09-28
GRT-YT01-P0PGB-113104 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | 2017-06-12 | 2017-09-10
GRT-YL01-P0ZEN-165462 | DCS IO List for Electrical Interface System | 2017-10-20 | 2017-08-20
GRT-YD00-P0BFD-156033 | General Arrangement LV Switchgear 4 | 2017-11-24 | 2017-12-24
GRT-CC04-P0ZEN-156232 | Common Switchgear Steel Structure Tower Type P1-Bottom Part | 2018-02-05 | 2018-02-19
GRT-CC03-P0UMA-175588 | Steam Turbine Building Chemical Dosing System Foundation Detail | 2017-10-11 | 2017-11-10
GRT-YD00-P0MA-200017 | [STG]_Layout - piping routing - | 2017-05-21 | 2017-10-25
GRT-DN02-P0MAV-830018 | [Commissioning Procedure] STG | 2018-03-30 | 2018-05-30
GRT-XK00-P0MAJ-460214 | Baseframe Drawing For Water Box Vacuum Pump | 2017-08-04 | 2017-09-08
GRT-YD00-P0LAC-122002 | [HP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | 2017-05-20 | 2017-08-20
GRT-CC07-P0PAD-175178(2OF3) | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Section Slab Schedule and Wall Schedule | 2017-02-11 | 2017-03-13
GRT-YD00-P0BJG-156068 | General Arrangement Space Heater Panel | 2017-11-24 | 2017-12-24
GRT-YK09-P0MA-200062 | [STG]_Commissioning manual for auxiliary equipment | 2018-06-20 | 2018-08-20
GRT-DN02-P1ZEN-830025 | [Commissioning Procedure]_Island operation | 2020-04-24 | 2020-05-22
GRT-YT01-P0UGD-115284 | [WTP] Process data sheet for make up demin for closed cooling system pump | 2017-02-23 | 2017-03-25
GRT-XW03-P1UHA-115456 | [WTP] Process calculation for blowdown transfer pump | 2017-08-18 | 2017-08-18
GRT-YK00-P0ZEN-164307 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Level Transmitter / Switch | 2017-04-21 | 2017-08-31
GRT-DN02-P0LA-830006 | [Commissioning Procedure] Feedwater System | 2018-01-30 | 2018-03-30
GRT-CA03-P0UMA-175269 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line S8, S9 & S10 | 2017-03-07 | 2017-04-06
GRTBCP-YS01-P0BJG-156070 | Schematic Diagram Space Heater Panel | 2018-01-26 | 2018-02-25
GRT-YK01-P1H-300048 | [HRSG]_INSTRUMENT INSTALLATION DETAIL DRAWINGS | 2017-07-20 | 2017-10-20
GRT-DC01-P0BYA-165646 | DCS SRS Specification of GTC | 2017-10-31 | 2017-11-30
GRT-CA03-P0UMA-175267 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SB, SC & SE | 2017-03-07 | 2017-04-06
GRT-DN02-P1ZEN-830023 | [Commissioning Procedure]_Fast cut back | 2020-03-17 | 2020-04-17
GRT-PP-MAR-0000 | Material Approval Painting Raw Tank | 2018-02-02 | 2018-02-16
GRT-MA01-P0ZEN-161002 | [INC_Plant_Overall_Design]_Plant Control System Configuration Diagram | 2017-03-31 | 2017-07-14
GRT-XB02-P1H-300015 | [HRSG]_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | 2017-03-30 | 2017-06-30
GRT-YD00-P0ZEN-120007 | Roof Rafter Assembly Section & Detail Make up Demin Tank | 2017-11-09 | 2017-10-10
GRT-YV02-P0MAJ-460102 | Wiring Diargam For Condenser Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-DN02-P1H-830012 | [Commissioning Procedure] HRSG | 2018-03-30 | 2018-05-30
GRT-YT01-P0BJG-156071 | Data Sheet Space Heater Panel | 2017-11-24 | 2017-12-24
GRT-YD16-P0UCA-155408 | [Control Building] Cable Tray and Power Wiring Layout | 2017-06-14 | 2017-07-14
GRT-YT01-P0BJL-156091 | Data Sheet Feeder Normal Lighting | 2017-11-24 | 2017-12-24
GRT-CC03-P0PAC-175166 | [Circulating Water Pump] Circulating Water Pump Sections | 2017-02-14 | 2017-03-16
GRT-YD00-P0BJA-156038 | General Arrangement STG Unit MCC | 2017-11-24 | 2017-12-24
GRT-YF00-P0ZEN-161311 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram for Interface with other Control System | 2017-04-28 | 2017-07-31
GRT-YD16-P0PAC-155151 | [Circulating Water Pump] Cable Tray and Power Wiring Layout | 2017-02-03 | 2017-03-05
GRT-YV02-P0SCA-120015 | [Air Compressor]_ELECTRICAL WIRING DIAGRAMS | 2017-05-20 | 2017-10-17
GRT-XS00-P0QC-130003 | [Chemical Dosing System]_SYSTEM DESCRIPTION | 2017-07-11 | 2017-10-23
GRT-DE00-P0ZEN-144500 | [Piping General]_Piping material specification (BOP) | 2017-03-03 | 2017-06-09
GRT-CA01-P0UMA-175256 (2 OF 2) | Steam Turbine Building Operating Local Platform Foundation Detail | 2019-01-07 | 2019-02-06
GRT-YT01-P0BJA-156041 | Data Sheet STG Unit MCC | 2017-11-24 | 2017-12-24
GRT-DF04-P0ZEN-144512 | [Piping General]_Stress Analysis Report for HP steam system | 2017-06-23 | 2017-09-15
GRT-YR05-P0ZEN-161133 | [DCS]_Outline & Detail Drawing for Power Distribution Cabinet | 2017-04-07 | 2017-07-07
GRT-YT10-P0LCM-430110 | Strength Calculation for Atmospheric Flash Tank | 2017-10-20 | 2017-12-22
GRT-YQ01-P0UMA-155243 | [STG BUILDING] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-07-12 | 2017-08-11
GRT-YT01-P0BJE-156061 | Data Sheet Valve PDB | 2017-11-24 | 2017-12-24
GRT-CC03-P0UMA-175606 | Culvert, Detail & Section | 2017-11-21 | 2017-12-21
GRT-FF05-P0SGA-133005 | [Fire Fighting System] Water Spray System Hydraulic Calculation | 2018-06-15 | 2018-09-14
GRT-YD00-P0PCC-113007 | [Aux. Cooling Water Pump]_MAIN TERMINAL BOX DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 2017-08-12 | 2017-11-10
GRT-YT01-P0SG-115381 | [Fire Fighting System] Datasheet for Fire Protection Equipment | 2017-03-20 | 2017-04-19
GRT-YT02-P0GD-165927 | Data Sheet Flow Indicator | 2017-07-21 | 2017-08-20
GRT-YT01-P0MAJ-460104 | Technical Data Sheet for Condenser Vacuum Pump | 2017-07-21 | 2017-09-08
GRT-XG08-P0ZEN-115007 | [Process General] Water Balance Calculation | 2017-03-28 | 2017-04-27
GRT-XW03-P0ZEN-156226 | 150 KV Switchgear Connection Diagram Diameter 1 | 2018-02-05 | 2018-02-19
GRT-CC09-P0UZA-175449(2OF5) | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 10.604 (T.O.S) | 2017-07-30 | 2017-08-29
GRT-YD00-P0UGD-165323 | [WTP] Instrument Main Cable & JB Layout for Raw Water System | 2017-03-22 | 2017-04-21
GRT-XL00-P0ZEN-144503 | [Piping General]_Piping Line List (BOP) | 2017-03-31 | 2017-06-30
GRT-YS01-POLDY-155853 | Schematic Diagram for WTP (Mixed Bed) | 2018-10-10 | 2018-11-09
GRT-CV03-P0ZEN-165679 | Data Sheet for Circulating Water Pump | 2017-11-17 | 2017-12-17
GRT-YF00-P0LC-161306 | [Condensate system_I&C_Loop]_Control Loop Diagram for BOP | 2017-04-21 | 2017-07-31
GRT-XG02-P0PBB-440101 | Debris Filter_P & I Diagram | 2017-04-01 | 2017-10-31
GRT-CA07-P0ZEN-179036 | CALCULATION REPORT CABLE TRENCH | 2018-04-18 | 2018-05-18
GRT-CA00-P0UMA-175246 | [STG BUILDING] Architectural Door & Window Schedule | 2017-06-05 | 2017-07-05
GRT-YV02-P0MAJ-460202 | Wiring Diargam For Water Box Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-VN03-P1H-300012 | [HRSG]_TYPICAL LADDER DETAIL FOR STEEL STRUCTURE | 2017-05-20 | 2017-08-20
GRT-CV03-P0ZEN-165674 | Data Sheet for Waste Water Transfer System | 2017-11-17 | 2017-12-17
GRT-YF00-P1LBA-161203 | [HP & LP steam system_I&C_Logic]_Control Logic Diagram for BOP | 2017-04-14 | 2017-07-31
GRT-XW03-P0ZEN-156191 | 150KV GRATI SWITCHGEAR CALCULATION NOTE STEEL STRUCTURE – EQUIPMENT SUPPORT | 2018-10-22 | 2018-11-21
GRT-CC04-P1UHA-175615 | Elevator HRSG Architectural Plan, Detail, & Finishing Schedule | 2017-12-06 | 2017-12-06
GRT-YD00-P0ZEN-165690 | Panel Arrangement Intake Electrical Building | 2019-05-27 | 2019-06-26
GRT-XW03-P0ZEN-156248 | 150 KV Switchgear Earthing And Mounting Principle Drawing | 2018-02-05 | 2018-02-19
GRT-YR05-P0ZEN-161134 | [DCS]_Outline & Detail Drawing for System & Marshalling Cabinet | 2017-04-07 | 2017-07-07
GRT-YE03-P0ZEN-161114 | [DCS]_Grounding Concept & Drawing | 2017-03-31 | 2017-06-30
GRT-YR02-P0ZEN-156253 | 150KV Grati Switchgear Disconnector Switch Tecnical Particular & Guarantee | 2017-10-05 | 2017-10-05
GRT-YL01-P0UGD-165335 | [DCS] I/O List for Service Water System | 2017-02-28 | 2017-03-30
GRT-QA00-P0H-040012 | [HRSG]_WPS&PQR for HRSG LP Drum | 2017-08-29 | 2017-11-29
GRT-YD00-P0LAC-122508 | [LP Feed Water Pump]_VFD OUTLINE AND DATA SHEET | 2017-08-25 | 2017-10-25
GRT-XJ00-P0LBG-143003 | Piping ISO (Small Bore) - Aux. Steam | 2017-07-14 | 2018-01-31
GRT-CA01-P0UMA-175255 (2 OF 2) | Steam Turbine Building Lube Oil and Mezzanine Local Platform Foundation Detail | 2019-01-07 | 2019-02-06
GRT-CC03-P1UHA-175222 | [HRSG] Foundation Detail (2/2) | 2017-03-25 | 2017-04-24
GRT-YD00-P0PAC-165156 | [Circulating Water Pump] Instrument Main Cable & JB Layout | 2017-03-11 | 2017-04-10
GRT-XW01-P0SCA-120029 | [Air Compressor]_VALVE SPECIFICATION | 2017-05-20 | 2017-10-17
GRT-DB00-P0MAJ-460218 | Performance Curves For Water Box Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-XA00-P0LCQ-106800 | GA Drawing Sump Pump | 2018-02-07 | 2018-02-21
GRT-HM05-P0UGX-125191 | [Chlorination System] HVAC Calculation for Chlorination Plant Building | 2017-07-07 | 2017-08-06
GRT-CQ02-P0SCA-120030 | [Air Compressor]_O & M MANUAL | 2017-07-20 | 2017-11-17
GRT-YU01-P0BJH-156074 | Single Line Diagram BOP Essensial PDB | 2018-01-26 | 2018-02-25
GRT-CA03-P0UMA-175263 | [STG BUILDING] Steam Turbine Building Steel Structure Roof Plan #1 | 2017-03-07 | 2017-04-06
GRT-YT01-P0LDB-130051 | [Condensate Filter System]_INSTRUMENT DATA SHEET | 2017-07-25 | 2017-11-07
GRT-YT01-P0MAJ-460115 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For CVP | 2017-07-07 | 2017-09-08
GRT-US02-P0MA-200014 | [STG]_Detail drawings - piping, components and BOM | 2018-01-22 | 2018-05-22
GRT-YR05-P0ZEN-161131 | [DCS]_Outline & Detail Drawing for Console desk & Computer desk & Printer desk | 2017-04-07 | 2017-07-07
GRT-XH01-P0UZT-144522 | [Pipe Rack_Piping]_Piping Arrangement | 2017-06-02 | 2017-09-29
GRT-YT01-P0UZA-156407 | Layout Cathodic Protection for Thermal Barrier | 2019-01-15 | 2019-02-14
GRT-XW03-P0ZEN-155090 | [Electrical General] Lightning Protection System Calculation | 2017-03-16 | 2017-04-15
GRT-DP00-P0ZEN-125019 | [Mechanical General] Specification for Storage Tank | 2017-02-25 | 2017-03-27
GRT-YS01-P0ZEN-156197 | 150KV GRATI. Switchgear Schematic Diagram Diameter X | 2018-02-05 | 2018-02-19
GRT-YD00-P0UGD-165326 | [WTP] Instrument Cable Wiring Layout for Water Treatment System | 2017-03-29 | 2017-04-28
GRT-YR02-P0ZEN-156258 | 150KV GRATI SWITCHGEAR SYSTEM FUNCTION SPEFICATION | 2019-04-24 | 2019-05-24
GRT-CQ02-P0PGB-400070 | Operation and Maintenance Manual for CCW Heat Exchanger | 2018-04-20 | 2018-06-30
GRT-CA05-P0UGX-125186 | [Chlorination System] Chlorination Plant Building Grey, Black Water Layout & Isometric | 2017-03-11 | 2017-04-10
GRT-QA00-P0H-040003 | [HRSG]_NDE Procedure for HRSG LP Drum | 2017-06-20 | 2017-09-20
GRT-XW03-P0ZEN-155096 | [Electrical General] Electrical Load List | 2017-02-20 | 2017-03-22
GRT-XJ00-P1H-300024 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR PIPNG FABRICATION STANDARD | 2017-09-20 | 2017-12-20
GRT-CV03-P0ZEN-161117 | [DCS]_Functional Design Specification for Performance Monitoring System | 2017-04-21 | 2017-06-30
GRT-QA00-P0H-040005 | [HRSG]_NDE Procedure for HRSG Heat Exchanger | 2017-06-20 | 2017-09-20
GRT-YE06-P0UAG-155360 | [Transformer] Lightning Protection Layout | 2017-06-23 | 2017-07-23
GRT-CC09-P0UZA-175449(5OF5) | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 17.304 (T.O.S) | 2017-07-30 | 2017-08-29
GRT-CC00-P0PAC-145145 | [Circulating Water Pump] Piping Layout Drawing for Sea Water Intake System | 2017-02-03 | 2017-03-05
GRT-CN00-P0ZEN-110102 | [Plant Overall]_PLANT START - UP AND SHUT - DOWN PROCEDURE | 2017-08-18 | 2017-11-16
GRT-CQ02-P0PAH-440059 | CCW HEX Tube Cleaning system_Operation & Maintenance Manual | 2018-06-30 | 2018-07-31
GRT-XJ00-P0LCA-140006 | Piping ISO (Large Bore) - Condensate | 2017-06-16 | 2018-01-31
GRT-XF00-P0SCA-120027 | [Air Compressor]_NAME PLATE DRAWING | 2017-06-20 | 2017-10-18
GRT-YT01-P0MAJ-460206 | Heat Exchanger Drawing and Data Sheet For Water Box Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-YQ01-P1UHA-155217 | [HRSG] Lighting and Receptale Wiring Layout | 2017-06-15 | 2017-07-15
GRT-CC00-P0ZEN-145024 | [Piping General] Information Drawing for Loading Data & Local Foundation Water Treatment Area | 2017-06-07 | 2017-07-07
GRT-YT02-P0GD-165926 | Data Sheet Pressure Diffrential | 2017-07-21 | 2017-08-20
GRTSCH-YD00-P0BAC-150005 | SF6 Pressure Scale | 2018-02-05 | 2018-02-19
GRT-CC03-P0UMA-175586 | Steam Turbine Building Air Dryer & Air Reciver Tank Foundation Detail | 2017-10-11 | 2017-11-10
GRT-CA03-P0UGD-175349 | [WTP] Steel Structure Framing Plan | 2017-03-22 | 2017-04-21
GRT-XW03-P0ZEV-156227 | 150 KV Switchgear Connection Diagram Diameter X | 2018-02-05 | 2018-02-19
GRT-YS00-P0ZEN-163310 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Electrical System | 2017-07-21 | 2017-09-30
GRT-CV03-P0ZEN-161110 | [DCS]_Functional Design Specification for Hardware | 2017-03-31 | 2017-06-30
GRT-YK10-P0MA-200056 | [STG]_Initial specification for TG installation | 2018-02-28 | 2018-05-22
GRT-YD06-P0ZEN-161115 | [DCS]_Equipment Power Distribution Diagram | 2017-03-31 | 2017-06-30
GRT-CC03-P0PAC-175167 | [Circulating Water Pump] Circulating Water Pump Detail 1 & 2 | 2017-02-14 | 2017-03-16
GRT-YQ01-P0PAC-155153 | [Circulating Water Pump] Lighting and Receptacle Wiring Layout | 2017-02-03 | 2017-03-05
GRT-YK09-P0MA-200035 | [STG]_Instrumentation data sheets | 2017-11-22 | 2018-03-24
GRT-YT01-P0MAJ-460106 | Heat Exchanger Drawing and Data Sheet For Condenser Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-CC03-P0UMA-175273 | [STG BUILDING] Concrete Structure Framing Elevation | 2017-04-08 | 2017-05-08
GRT-CC03-P0UGH-175353 (2 OF 2) | Shelter for Make Up Demin Water Pump | 2020-02-28 | 2020-03-29
GRT-YD00-P0BJC-156048 | General Arrangement HRSG Unit MCC | 2017-11-24 | 2017-12-24
GRT-YD16-P0UBN-155413 | [Engine Diesel Generator] Cable Tray and Power Wiring Layout | 2017-06-14 | 2017-07-14
GRT-YF00-P0LDB-130054 | [Condensate Filter System]_CONTROL LOOP & LOGIC DIAGRAM | 2017-08-24 | 2017-12-07
GRT-YR02-P0ZEN-155064 | [Electrical General] Datasheet for Main Transformer | 2017-02-18 | 2017-03-20
GRT-YT01-P0GAF-126810 | Feed Pump Data Sheet | 2019-02-13 | 2019-03-15
GRT-CC03-P0UAG-175365 | [Transformer] Foundation Detail | 2017-06-20 | 2017-07-20
GRT-CV03-P0UGD-165314 | [WTP] Instrument Data sheet for Potable Water System | 2017-03-02 | 2017-04-01
GRT-YT01-P0LB-111100 | [Bypass Valve & PRDS]_DATA SHEET FOR BYPASS AND PRDS | 2017-07-14 | 2017-10-12
GRT-YT02-P0LD-165829 | DATA SHEET PRESSURE DIFFERENTIAL SWITCH | 2017-10-18 | 2017-11-17
GRT-XK00-P0MAJ-460212 | Outline & Sectional Drawing For Water Box Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-CE00-P0SG-115377 | [Fire Fighting System] Lay out fire protection equipment | 2017-07-07 | 2017-07-06
GRT-XG02-P0LDB-130036 | [Condensate Filter System]_P&ID | 2017-05-26 | 2017-09-08
GRT-CC09-P0UZA-175449(4OF5) | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 15.604 (T.O.S) | 2017-07-30 | 2017-08-29
GRT-YD00-P0PAC-125140 | [Circulating Water Pump] GA Drawing Bar Screen | 2017-07-15 | 2017-08-14
GRT-YK08-P0PAH-440053 | CCW HEX Tube Cleaning System_Outline Drawing for Ball Recirculation unit | 2017-04-01 | 2017-10-31
GRT-CV03-P0ZEN-165677 | Data Sheet for Portable Water System | 2017-11-17 | 2017-12-17
GRT-XS03-P0ZEN-115009 | [Process General] Process Control Philosophy for BOP | 2017-06-12 | 2017-07-12
GRT-YK10-P0PCC-113003 | [Aux. Cooling Water Pump]_Pump Sectional Drawing | 2017-06-05 | 2017-09-03
GRT - YL16 - P0LD - 155949 | Cable Schedule Instrument for WTP | 2018-02-02 | 2018-02-16
GRT-YF02-P0BYA-165673 | GTCS-System Configuration for GTC | 2017-12-18 | 2018-01-17
GRT-YR02-P0ZEN-156189 | Common Switchgear Technical Specification Connector | 2018-02-05 | 2018-02-19
GRT-XS03-P0ZEN-115008 | [Process General] Process Description for BOP | 2017-03-21 | 2017-04-20
GRT - YT01 - P0GCK - 126801 | Data Sheet Make Up Demin Water Pump | 2018-02-02 | 2018-02-16
GRT-YR00-P0BYA-165645 | DCS Software Specification og GTC | 2017-10-31 | 2017-11-30
GRT-XA00-P0GKB-106804 | GA Drawing Auxiliary Water Pump | 2018-02-07 | 2018-02-21
GRT-XW01-P0SG-115384 | [Fire Fighting System] Fire Protection Design Basis | 2017-03-20 | 2017-04-19
GRT-XJ00-P0QC-143016 | Piping ISO (Small Bore) - Chemical dosing | 2017-07-14 | 2018-01-31
GRT-YS01-P0ZEN-165687 | LDC SYSTEM ARCHITECTURE | 2019-02-13 | 2019-03-15
GRT-YS05-P0ZEN-162701 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Field Instrument | 2017-03-17 | 2017-07-31
GRT-QA00-P0H-040002 | [HRSG]_NDE Procedure for HRSG HP Drum | 2017-06-20 | 2017-09-20
GRT-QA00-P0H-040006 | [HRSG]_Shop Quality Manual for HRSG | 2017-06-23 | 2017-09-23
GRT-MA02-P0ZEN-161006 | [INC_Interface]_3rd Party Data-link Interface Concept Diagram | 2017-03-31 | 2017-07-14
GRT-XW01-P0ZEN-115010 | [Process General] Process Design Basis | 2017-02-18 | 2017-03-20
GRT-YD00-P0UGD-165318 | [WTP] Instrument Location Plan Layout for Potable Water System | 2017-03-16 | 2017-04-15
GRT-YR05-P0ZEN-165691 | Data Sheet for Fire Alarm System | 2019-02-13 | 2019-03-15
GRT-YD00-P0LDB-130040 | [Condensate Filter System]_CONTROL PANEL ARRANGEMENT DRAWING | 2017-06-26 | 2017-10-08
GRT-DE00-P0ZEN-145032 | [Piping General] Specification for Wrapping Tape Material | 2017-03-02 | 2017-04-01
GRT-UE00-P0ZEN-100008 | General Arrangement of Steam Turbine Building Section A-A | 2017-03-17 | 2018-10-01
GRT-DC01-P0LDN-125819 | DATA SHEET CAUSTIC DOSING PUMP FOR NUTRALIZING SYSTEM | 2017-10-13 | 2017-11-12
GRT-CC04-P0ZEN-156234 | Common Switchgear Steel Structure Tower Type P1- Tower Head | 2018-02-05 | 2018-02-19
GRT-CA03-P0UGD-175350 | [WTP] Steel Structure Framing Elevation and Detail | 2017-06-23 | 2017-07-23
GRT-YD00-P0ZEN-165100 | [Instrument General] Instrument Layout Keyplan | 2017-09-14 | 2017-06-20
GRT-CC07-P0PAD-175179(1OF2) | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Details | 2017-02-11 | 2017-03-13
GRT-DA06-P0ZEN-115003 | [Process General] Tie-In List | 2017-05-02 | 2017-06-01
GRT-YR02-P0ZEN-165691 | Data Sheet Equipment for Clock System | 2019-02-13 | 2019-03-15
GRT-QM03-P0ZEN-141008 | MAGNETIC PARTICLE EXAMINATION PROCEDURE | 2017-10-11 | 2017-11-13
GRT-UE00-P0ZEN-100006 | General Arrangement of Steam Turbine Building Deaerator Floor | 2017-03-17 | 2018-10-01
GRT-YF00-P0LC-161206 | [Condensate system_I&C_Logic]_Control Logic Diagram for BOP | 2017-04-21 | 2017-07-31
GRT-XG02-P0MAJ-460201 | P & ID For Water Box Vacuum Pump | 2017-06-16 | 2017-09-08
GRT-XW01-P0LA-110202 | [Feedwater system]_DESIGN CRITERIA | 2017-02-22 | 2017-07-14
GRT-YK10-P0ZEN-113300 | [MOV (Gate & Globe)(DHI)]_OUTLINE DRAWING FOR MOV (G&G) | 2017-08-15 | 2017-11-13
GRT-YF00-P0PA-161307 | [Aux. Cooling Water System_I&C_Loop]_Control Loop Diagram for BOP | 2017-04-21 | 2017-07-31
GRT-XS00-P0LBG-110401 | [AUX Steam System]_SYSTEM DESCRIPTION | 2017-02-28 | 2017-07-14
GRT-CC03-P0PAC-175169 | [Circulating Water Pump] Circulating Water Pump Detail 4,5 and Suction Chamber | 2017-02-14 | 2017-03-16
GRT-XS00-P0LDB-130038 | [Condensate Filter System]_SYSTEM DESCRIPTION | 2017-05-26 | 2017-09-08
GRT-XW01-P0SCA-120011 | [Air Compressor]_AIR RECEIVER SPECIFICATION | 2017-04-20 | 2017-07-19
GRT-PP-KSB-P1702024-ME-002 | Mechanical Data Sheet for CWP Pump | 2017-06-10 | 2017-06-10
GRT-XW03-P0ZEN-155083 | [Electrical General] Short Circuit Calculation | 2017-03-14 | 2017-04-13
GRT-YS18-P0LB-111107 | [Bypass Valve & PRDS]_P&ID for HPU | 2017-07-28 | 2017-10-26
GRT-YT01-P0PAC-115137 | [Circulating Water Pump] Sea Water Intake Basin Process Data Sheet | 2017-02-10 | 2017-03-12
GRT-YD00-P0AT-156119 | Termination drawing of Station Service Transformer 25MVA | 2017-10-18 | 2017-11-17
GRT-XW01-P0LBA-110200 | [HP & LP steam system]_DESIGN CRITERIA | 2017-02-22 | 2017-07-14
GRT-CC03-P0UMA-175597 | Cable Trench and Duct Bank General Layout | 2017-11-21 | 2017-12-21
GRT-YT10-P0PGB-430120 | Strength Calculation for CCW Chemical Additive Tank | 2017-10-20 | 2017-12-22
GRT-YE07-P0UMA-155241 | [STG BUILDING] Lightning Protection Layout | 2017-04-08 | 2017-05-08
GRT-XG02-P0UGX-115183 | [Chlorination System] Piping and instrument diagram (PID) Chlorination System | 2017-06-07 | 2017-07-07
GRT-HM01-P0UMA-125235 | [STG BUILDING] Steam Turbine Building HVAC Equipment Layout | 2017-03-11 | 2017-04-10
GRT-YQ01-P0PAC-155154 | [Circulating Water Pump] Lighting and Receptacle Connection Diagram | 2017-02-03 | 2017-03-05
GRT-CQ02-P0PAH-440009 | Condenser Tube Cleaning system_Operation & Maintenance Manual | 2018-05-04 | 2018-06-29
GRT-DN02-P0LBD-830010 | [Commissioning Procedure] Condesate Filter System | 2018-02-28 | 2018-04-30
GRT-XH01-P1H-300021 | [HRSG]_PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | 2017-09-20 | 2017-12-20
GRT-YD07-P0BYA-165654 | DCS Input / Output Signal List of GWC | 2017-10-26 | 2017-11-25
GRT-CC04-P1UHA-175617 | HRSG Foundation Plan and Section | 2017-12-06 | 2017-12-06
GRT-YD07-P0BYA-165652 | DCS Input / Output Signal List of DAS | 2017-10-26 | 2017-11-25
GRT-YT001-P0ZEN-145626 | Data Sheet for Check Valve | 2017-10-16 | 2017-10-16
GRT-XS00-P0QJA-110406 | [N2 Gas system]_system description | 2017-02-28 | 2017-07-14
GRT-YL22-P0PCC-113017 | [ACWP]_OPERATION & MAINTENANCE MANUAL | 2018-04-20 | 2018-05-31
GRT-YL16-P0ZEN-155048 | [Electrical General] Power and Control Cable Schedule | 2017-07-14 | 2017-08-13
GRT-CA03-P0UMA-175265 | [STG BUILDING] Steam Turbine Building Steel Structure Roof Plan #2 | 2017-03-07 | 2017-04-06
GRT-YF00-P0QC-130019 | [Chemical Dosing System]_CONTROL LOOP & LOGIC DIAGRAM | 2017-09-09 | 2017-12-22
GRT-XK00-P0LCA-144006 | Support DWG (Large Bore) - Condensate | 2017-12-31 | 2018-01-30
GRT-YF00-P0ZEN-161405 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Hot Start-up | 2017-08-18 | 2017-11-16
GRT-YD00-P0LCM-430010 | Outline Drawing for Atmospheric Flash Tank | 2017-03-08 | 2017-08-05
GRT-CC03-P0PAC-175170(4OF7) | [Circulating Water Pump] Circulating Water Pump Screen Wash Pumps and Sea Water Feed Pumps Detail | 2017-02-14 | 2017-03-16
GRT-YK00-P0ZEN-165117 | [Instrument General] CCTV Typical Drawing for Installation | 2017-04-22 | 2017-05-22
GRT-YL00-P0QC-130007 | [Chemical Dosing System]_INSTRUMENT LIST | 2017-07-11 | 2017-10-23
GRT-CC09-P0UZA-175449(1OF5) | PIPERACK STEEL STRUCTURE COLUMN ARRANGEMENT & MEMBER SCHEDULE | 2017-07-30 | 2017-08-29
GRT-XG02-P0SC-120001 | [Compressed air system]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | 2017-02-06 | 2017-07-14
GRT-YR01-P0ZEN-110105 | [HP & LP steam system]_Pressure drop calculation | 2017-03-30 | 2017-07-14
GRT-XW01-P0UGD-115294 | [WTP] Process idividual specification for Water treatment system | 2017-02-21 | 2017-03-23
GRT-XN00-P0QU-130029 | [Sampling System]_VALVE LIST | 2017-07-20 | 2017-11-01
GRT-CC00-P0PAD-145176 | [Circulating Water Pump Outfall] Piping Layout Drawing for Sea Water Outfall | 2017-07-15 | 2017-08-14
GRT-XG07-P0LBA-110300 | [Steam, Feedwater & Condensate system]_PROCESS FLOW DIAGRAM | 2017-03-15 | 2017-07-14
GRT-YT01-P0PBB-440103 | Debris Filter_Technical Data Sheet | 2017-04-01 | 2017-10-31
GRT-YT01-P0SG-115380 | [Fire Fighting System] Process data sheet for Fire Water Pump | 2017-07-07 | 2017-07-06
GRT-XW01-P0SG-115385 | [Fire Fighting System] Fire Design Basis | 2017-03-20 | 2017-04-19
GRT-YQ01-P1UHA-155218 | [HRSG] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-07-12 | 2017-07-12
GRT-YK08-P0SMM-146555 | Detail Installation Rail A75 Overhead Crane | 2018-07-24 | 2018-08-23
GRT-XN00-P0QC-130008 | [Chemical Dosing System]_VALVE LIST | 2017-07-11 | 2017-10-23
GRT-XN00-P0SCA-120028 | [Air Compressor]_VALVE LIST | 2017-05-20 | 2017-10-17
GRT-YD16-P0UAG-155358 | [Transformer] Cable Tray and Power Wiring Layout | 2017-06-23 | 2017-07-23
GRT-CT00-P0LB-111210 | [Bypass]_O&M Manual | 2018-04-20 | 2018-05-31
GRT-YD00-P0BFB-156023 | General Arrangement LV Switchgear 2 | 2017-11-24 | 2017-12-24
GRT-YD00-P0PGB-113205 | [Blowdown Cooler]_INSTALLATION, OPERATION AND MAINTENANCE MANUAL | 2018-04-20 | 2018-05-31
GRT-YT01-P0PAH-440058 | CCW HEX Tube Cleaning System_Technical Data Sheet | 2017-04-01 | 2017-10-31
GRT-XW03-P0ZEN-155087 | [Electrical General] UPS, Battery & Battery Charger Capacity | 2017-03-15 | 2017-04-14
GRT-YD04-P1H-300042 | [HRSG]_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | 2017-07-20 | 2017-10-20
GRT-YD00-P0LAC-122502 | [LP Feed Water Pump]_GENERAL ARRANGEMENT DRAWING | 2017-05-20 | 2017-08-20
GRT-XJ00-P0PAB-140012 | Piping ISO (Large Bore) - Cooling water | 2017-08-11 | 2018-01-31
GRT-XW01-P0ZEN-161001 | [INC_Plant_Overall_Design]_I&C General Design Criteria | 2017-03-03 | 2017-07-14
GRT-YK10-P0MA-200061 | [STG]_Assembly manual for auxiliary equipment | 2018-05-18 | 2018-07-17
GRT-XW03-P0ZEN-155095 | [Electrical General] Busduct Sizing Calculation | 2017-03-16 | 2017-04-15
GRT-YF00-P0LBG-161204 | [AUX Steam System_I&C_Logic]_Control Logic Diagram for BOP | 2017-04-14 | 2017-07-31
GRT-YD00-P0PGB-113105 | [CCWP ]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 2017-06-12 | 2017-09-10
GRT-YD00-P0ZEN-165107 | [Instrument General] Paging Cable Wiring Layout | 2017-07-19 | 2017-08-18
GRT-HM01-P0UGX-125190 | [Chlorination System] Chlorination Plant Building HVAC, Elevation, Section & Detail | 2017-03-11 | 2017-04-10
GRT-CC09-P0UZA-175452 | Calculation Sheet for Foundation Support NSPB | 2019-01-20 | 2019-02-19
GRT-YL22-P0PGB-113117 | [CCWP]_OPERATION & MAINTENANCE MANUAL | 2018-04-20 | 2018-05-31
GRT-YL21-P0MA-200046 | [STG]_Trips & Alarms settings | 2017-09-16 | 2018-01-21
GRT-CC03-P0UMA-175591 | Steam Turbine Building Foundation Detail | 2017-10-11 | 2017-11-10
GRT-YD00-P0UGD-120037 | Shell Manhole Section & Detail | 2017-11-14 | 2017-11-14
GRT-CV03-P0UGD-165317 | [WTP] Instrument Data Sheet for Service Water System | 2017-06-02 | 2017-07-02
GRT-XW03-P0ZEN-156273 | 150 kV Grati Switchgear Calculation Note High Voltage | 2018-02-05 | 2018-02-19
GRT-XK00-P0ZEN-144901 | Outline Drawing for Piping Manual Butterfly Valve | 2017-11-15 | 2017-12-01
GRT-CC03-P0UMA-175596 | Calculation Sheet for Underground Facility | 2017-11-21 | 2017-12-21
GRT-YD00-P0BJJ-156078 | General Arrangement Feeder UPS-01 | 2017-11-24 | 2017-12-24
GRT-YK00-P0ZEN-164305 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Diff. Press. Transmitter / Switch | 2017-04-21 | 2017-08-31
GRT-FF02-P0SGA-133004 | [Fire Fighting System] Detection and Alarm System Equipment Location Plan for STG Enclosure Inside | 2018-06-15 | 2018-09-14
GRT-YT01-P0BFA-156021 | Data Sheet LV Switchgear 1 | 2017-11-24 | 2017-12-24
GRT-XJ00-P0SCA-143010 | Piping ISO (Small Bore) - Compressed air | 2017-07-28 | 2018-01-31
GRT-XK00-P0ZEN-144904 | Outline Drawing for Piping HP Manual Forging Valve | 2017-11-15 | 2017-12-01
GRT-XG02-P0SCA-120008 | [Air Compressor]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | 2017-04-20 | 2017-07-19
GRT-YD00-P0BFA-156018 | General Arrangement LV Switchgear 1 | 2017-11-24 | 2017-12-24
GRT-YR02-P0ZEN-155070 | [Electrical General] Datasheet for UPS, Battery & Battery Charger | 2017-03-11 | 2017-04-10
GRT-DP00-P0ZEN-141001 | WPS&PQR for BOP Piping | 2017-09-15 | 2017-12-15
GRT-YS01-P0ZEN-156277 | 150KV GRATI SWITCHGEAR FRONT AND INTERNAL VIEW ENERGY METER PANEL | 2019-02-13 | 2019-03-15
GRT-DC01-P0LDH-125816 | DATA SHEET AIR BLOWER | 2017-10-18 | 2017-11-17
GRT-YK09-P0LB-111106 | [Bypass Valve & PRDS]_Sectional drawing | 2017-07-14 | 2017-10-12
GRT-YT01-P0PGB-113102 | [CCWP ]_DATA SHEET FOR CLOSED COOLING WATER PUMP | 2017-06-12 | 2017-09-10
GRT-YQ05-P0BYA-165651 | DCS System Alarm Diagram | 2017-10-26 | 2017-11-25
GRT-XG02-P0LCM-110005 | [Steam drain system]_P&ID DIAGRAM | 2017-02-22 | 2017-07-14
GRT-YD00-P0BFA-156376 | General Arrangement NSPB-A | 2017-11-14 | 2017-12-14
GRT-YK09-P0MA-200063 | [STG]_ Elec. Heater panel | 2018-12-10 | 2019-03-11
GRT-YK09-P0MA-200059 | [STG]_First commissioning and start-up TG | 2018-02-28 | 2018-05-22
GRT-YD00-P0ZEN-165101 | [Instrument General] Instrument Main Cable Way Layout | 2017-07-19 | 2017-08-18
GRT-CC03-P0UGD-175352 | [WTP] Make Up Closed Cooling Foundation | 2017-06-23 | 2017-07-23
GRT-YD00-P0UGD-120038 | Roof Plate Arrangement Section & Detail | 2017-11-14 | 2017-11-14
GRT-YM03-P0GD-161036 | Instrument Arrangement for Electro Chlorination | 2019-02-13 | 2019-03-15
GRT-CC03-P0UGD-175581 | Sump Pit at HRSG Area Foundation Plan, Section and Detail | 2017-10-23 | 2017-10-23
GRT-YS00-P0LB-111112 | [Bypass Valve & PRDS]_Wiring Diagram | 2017-07-14 | 2017-10-12
GRT-YT01-P0PCC-113002 | [Aux. Cooling Water Pump]_DATA SHEET FOR AUXILIARY COOLING WATER PUMP | 2017-06-05 | 2017-09-03
GRT-YD00-P0UGD-165560 | Instrument Loscation Plant Layout for Waste Water Transfer System | 2017-09-28 | 2017-09-28
GRT-YT01-P0LBG-111301 | [Silencer]_DATA SHEET FOR SILENCER | 2017-10-24 | 2018-01-22
GRT-VN03-P1H-300011 | [HRSG]_TYPICAL HANDRAIL DETAIL FOR STEEL STRUCTURE | 2017-05-20 | 2017-08-20
GRT-XW03-P0UGD-115298 | [WTP] Process calculation for auxiliary service water pump | 2017-02-23 | 2017-03-25
GRT-YR02-P0ZEN-155067 | [Electrical General] Datasheet for Low Voltage Switchgear and MCC | 2017-03-07 | 2017-04-06
GRT-YF00-P0ZEN-165576 | Instrument Control Loop for Waste water Transfer System | 2017-10-24 | 2017-10-24
GRT-XG02-P0GAC-135937 | P & ID | 2017-10-13 | 2017-11-12
GRT-YL00-P0MA-200048 | [STG]_I/O list | 2017-11-22 | 2018-03-10
GRT-CC00-P0ZEN-145025 | [Piping General] Layout Crossing Road & Electrical Underground | 2017-02-24 | 2017-09-07
GRT-CC00-P0PAD-145177 | [Circulating Water Pump Outfall] Detail & Section Drawing for Sea Water Outfall | 2017-07-07 | 2017-08-06
GRT-XA00-P0LCQ-106802 | GA Drawing Blow Down Transfer Water Pump | 2018-02-07 | 2018-02-21
GRT-YD00-P0BJK-156083 | General Arrangement Feeder UPS-02 | 2017-11-24 | 2017-12-24
GRT-XB00-P0MA-200009 | [STG]_Lay down plan | 2017-05-21 | 2017-09-20
GRT-YD00-P0UGD-120039 | Roof Handril Detail | 2017-11-14 | 2017-11-14
GRT-YQ01-P0UGD-155313 | [WTP] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-03-22 | 2017-04-21
GRT-YT01-P0SG-115379 | [Fire Fighting System] Process data sheet for Jockey Pump | 2017-07-07 | 2017-07-06
GRT-YD00-P0PGB-113201 | [Blowdown Cooler]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | 2017-07-24 | 2017-10-22
GRT-DN02-P1H-830017 | [Commissioning Procedure]_Bypass Damper | 2019-07-15 | 2019-09-15
GRT-CA05-P0UGX-125185 | [Chlorination System] Chlorination Plant Building Cold Water Layout & Isometric | 2017-03-11 | 2017-04-10
GRT-CC09-P0UZA-175450(2OF3) | PIPE RACK STEEL STRUCTURE ELEVATION LINE SAD -5 & SAD-6 | 2017-05-01 | 2017-05-31
GRT-YE07-P0UGD-155311 | [WTP] Lightning Protection Layout | 2017-03-22 | 2017-04-21
GRT-XW03-P0LC-110501 | [CEP_Design]_sizing Calculation | 2017-03-15 | 2017-06-13
GRT-XK00-P0PAB-144007 | Support DWG (Large Bore) - Aux. cooling water | 2017-12-31 | 2018-01-30
GRT-YT01-P0BJC-156051 | Data Sheet HRSG Unit MCC | 2017-11-24 | 2017-12-24
GRT-XJ00-P0LBA-140002 | Piping ISO (Large Bore) - LP Steam | 2017-06-09 | 2017-08-31
GRT-YT01-P0LDB-130050 | [Condensate Filter System]_VALVE DATA SHEET | 2017-07-25 | 2017-11-07
GRT-YT01-P0LCB-121005 | [Condensate Extraction Pump]_MECHANICAL SEAL SPECIFICATION | 2017-06-20 | 2017-09-20
GRT-XA00-P0GCK-106801 | GA Drawing Make Up Demin Water Pump | 2018-02-07 | 2018-02-21
GRT-YS00-P0ZEN-163307 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Output | 2017-03-03 | 2017-05-31
GRT-XW01-P0SCA-120009 | [Air Compressor]_AIR COMPRESSOR SPECIFICATION | 2017-04-20 | 2017-07-19
GRT-YD07-P0BYA-165655 | DCS Input / Output Signal List of SRS | 2017-10-26 | 2017-11-25
GRT-DP00-P0ZEN-141002 | Heat treatment procedure for BOP Piping | 2017-09-15 | 2017-12-15
GRT-CA01-P0UMA-175256 (1 OF 2) | Steam Turbine Building Operating Plan El. +17.054 (T.O.C) Slab Schedule, Section and Details | 2019-01-07 | 2019-02-06
GRT-QA00-P0H-040009 | [HRSG]_Welders List for HRSG HP Drum | 2017-08-29 | 2017-11-29
GRT-CQ02-P1H-300001 | [HRSG]_INSTALLATION, OPERATION AND MAINTENANCE INSTRUCTION MANUAL | 2018-02-28 | 2018-05-28
GRT-XW03-P0ZEN-155091 | [Electrical General] Cable Size Calculation | 2017-03-30 | 2017-04-29
GRT-QM03-P0ZEN-141007 | ULTRASONIC EXAMINATION PROCEDURE | 2017-10-11 | 2017-11-13
GRT-DN02-P0ZEN-830000 | General Commissioning Procedure | 2018-07-23 | 2018-09-25
GRT-YK00-P0ZEN-164306 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Flow Transmitter / Switch | 2017-04-21 | 2017-08-31
GRT-YT02-P0LD-165822 | DATA SHEET PRESSURE INDICATOR | 2017-10-18 | 2017-11-17
GRT-XW03-P0ZEN-156190 | 150kV Grati, Switchgear Calculation Steel Structures - Gantries | 2017-11-16 | 2017-12-16
GRT-XB02-P0MAJ-460111 | Foundation Drawing For Condenser Vacuum Pump | 2017-07-07 | 2017-09-08
GRTBCP-YS01-P0BJE-156060 | Schematic Diagram Valve PDB | 2018-01-26 | 2018-02-25
GRT-XW03-P0SG-115390 | [Fire Fighting System] Fire Water Hydraulic Calculation | 2017-03-20 | 2017-04-19
GRT-XB02-P1H-300014 | [HRSG]_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | 2017-03-30 | 2017-06-30
GRT-YD00-P0ZEN-165108 | [Instrument General] Instrument Grounding Layout | 2017-06-14 | 2017-07-14
GRT-XW03-P0ZEN-156184 | 150kV Grati Switchgear Technical Specification Low Voltage Cable | 2018-02-05 | 2018-02-19
GRT-YK09-P0LCB-121004 | [Condensate Extraction Pump]_PUMP SECTIONAL DRAWING | 2017-05-20 | 2017-08-20
GRT-YT10-P0PGB-400050 | Thermal Calculation for CCW Heat Exchanger | 2017-10-16 | 2017-12-22
GRT-CC07-P0LD-135842 | MASS BALANCE Mixed BED System | 2017-10-18 | 2017-11-17
GRT-CA07-P0ZEN-175127 | [Civil General] Design Specification for Civil and Structural | 2017-02-23 | 2017-03-25
GRT-XW03-P0ZEN-156195 | 150 KV Switchgear Principle Diagram | 2018-02-05 | 2018-02-19
GRT-YK00-P0ZEN-165118 | [Instrument General] Telephone Typical Drawing for Installation | 2017-04-25 | 2017-05-25
GRT-YB03-P0PAH-440056 | CCW HEX Tube Cleaning System_Configuration Diagram of Package System | 2017-06-01 | 2017-10-31
GRT-XA00-P0QC-130002 | [Chemical Dosing System]_GENERAL ARRANGEMENT DRAWING | 2017-07-11 | 2017-10-23
GRT-YM02-P0UCA-175452 | Arrangement Support NSPB (include calculation) | 2019-03-10 | 2019-04-09
GRT-YU01-P0ZEN-155080 | [Electrical General] Single Line Diagram for Protection & Metering System | 2017-03-02 | 2017-04-01
GRT-DC01-P0GDN-125919 | Data Sheet Shock DosingPump | 2017-09-14 | 2017-10-14
GRT-YB10-P0BAA-156314 | Terminationn Details of 15.75kV IPBD | 2017-12-13 | 2018-01-12
GRT-YL25-P0GD-165943 | MODBUS LIST FOR EC | 2019-02-13 | 2019-03-15
GRT-YU01-P0BJP-156054 | Single Line Diagram HRSG PDB | 2018-01-26 | 2018-02-25
GRT-YD00-P0PUR-156395 | ICCP (IMPRESSED CURRENT CATHODIC PROTECTION) FOR AUXILIARY COOLING WATER PUMP | 2019-11-29 | 2019-12-29
GRT-QA00-P0H-040007 | [HRSG]_Welders List for HRSG Heat Exchanger | 2017-08-29 | 2017-11-29
GRT-HM01-P0UMA-125234 | [STG BUILDING] Steam Turbine Building HVAC Ducting Layout | 2017-03-11 | 2017-04-10
GRT-YQ01-P0ZEN-155049 | [Electrical General] Flood Light Wiring Layout for Outfall Area | 2017-07-14 | 2017-08-13
GRT-YS01-P0AT-156130 | Rating & Schematic Plate 150/15.75 kV – 250 MVA Power Transformer | 2017-10-06 | 2017-11-05
GRT-YF00-P0ZEN-161403 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Cold Start-up | 2017-08-18 | 2017-11-16
GRT-CC07-P0PAD-175179(2OF2) | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Details | 2017-02-11 | 2017-03-13
GRT-CC09-P0UZA-175448(1OF2) | [Structure for Transport, Trafic & Other Purpose] Pipe Rack Foundation Plan & Grade Beam Schedule | 2017-07-30 | 2017-08-29
GRT-YR05-P0ZEN-161135 | [DCS]_Outline & Detail Drawing for Relay Cabinet | 2017-04-07 | 2017-07-07
GRT-YD00-YM02-156410 | GENERAL ARRANGEMENT DIFFERENTIAL PROTECTION OVERALL & UAT SWITCHBOARD | 2018-12-17 | 2019-01-16
GRT-YS01-P0BYA-165659 | GTCS-Schematic Diagram of SRS | 2017-12-05 | 2017-12-19
GRT-YF00-P0ZEN-165575 | Instrument Control Logic for Service Water System | 2017-11-03 | 2017-12-03
GRT-XJ00-P0LBA-143001 | Piping ISO (Small Bore) - HP Steam | 2017-07-07 | 2018-01-31
GRT-YS01-P0AT-156111 | Layout and Schematic Diagram for Mashalling Kiosk Transformer 25000KVA 15.75/6.3kV | 2017-10-18 | 2017-11-17
GRT-YS00-P0ZEN-163306 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Analog Input | 2017-03-03 | 2017-05-31
GRT-XW03-P0ZEN-156179 | 150kV Grati, Switchgear Calculation Note Compatibility CT / Protection (exclude GSUT & SST Area) | 2017-11-16 | 2017-12-16
GRT-CC03-P0UZA-175421 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pilling Plan and List | 2017-07-14 | 2017-08-13
GRT-XG02-P0LCB-121002 | [Condensate Extraction Pump]_P&I DIAGRAM | 2017-04-20 | 2017-07-20
GRT-XG02-P0PAH-440001 | Condenser Tube Cleaning System_P & I Diagram | 2017-04-01 | 2017-10-31
GRT-YU01-P0BJK-156084 | Single Line Diagram Feeder UPS-02 | 2018-01-26 | 2018-02-25
GRT-YT02-P0LD-165825 | DATA SHEET CONDUCTIVITY TRANSMITTER | 2017-10-18 | 2017-11-17
GRT-YF00-P0ZEN-165580 | Instrument Control Loop for Condenser Circulating Sea Water Cooling System | 2017-12-12 | 2017-12-12
GRT-YS00-P0GCK-155855 | ELECTRICAL CONNECTION DIAGRAM FOR MIXED BED | 2019-02-13 | 2019-03-15
GRT-YK09-P0MA-200052 | [STG]_Maintenance instructions for the steam turbine and accessories | 2018-02-28 | 2018-05-22
GRT-YK08-P0PAH-440007 | Outline Drawing for Control Panel of CTCS & Debris Filter | 2017-06-01 | 2017-10-31
GRT-YT01-P0BAA-156304 | Technical Data Sheet for 15.75kV IPBD | 2017-10-09 | 2017-11-08
GRT-YL22-P0LDB-130053 | [Condensate Filter System]_NAME PLATE DRAWING | 2017-08-24 | 2017-12-07
GRT-CC03-P0UMA-175584 | Steam Turbine Building ACW & CCW Foundation Detail | 2017-10-11 | 2017-11-10
GRT-YS01-P0LDB-130055 | [Condensate Filter System]_SCHEMATIC DIAGRAM | 2017-08-24 | 2017-12-07
GRTBCP-YS01-P0BJP-156020 | Schematic Diagram LV Switch Gear 1 | 2018-01-26 | 2018-02-25
GRTBCP-YS01-P0BJP-156408 | Schematic Diagram HRSG PDB-03 | 2018-01-26 | 2018-02-25
GRT-XA00-P0LDB-130037 | [Condensate Filter System]_GENERAL ARRANGEMENT DRAWING | 2017-05-26 | 2017-09-08
GRT-YT01-P0ZEN-111201 | [Safety Relief Valve(DHI)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | 2017-09-26 | 2017-12-25
GRT-YD00-P0LCB-121008 | [Condensate Extraction Pump]_FOUNDATION DRAWINGS | 2017-04-20 | 2017-07-20
GRT-CC03-P1UHA-175220 | [HRSG] Foundation Plan | 2017-03-25 | 2017-04-24
GRT-YT01-P0UGD-115283 | [WTP] Process data sheet for make-up demin water tank | 2017-02-23 | 2017-03-25
GRT-XW03-P0UGD-115292 | [WTP] Process calculation for service water pump | 2017-02-23 | 2017-03-25
GRT-YR02-P0ZEN-155072 | [Electrical General] Datasheet for Lighting Fixture & Accessories | 2017-03-11 | 2017-04-10
GRT-YR02-P0ZEN-156255 | 150 KV Grati Switchgear Disconnector Swich Tecnical Particular & Guarantee | 2017-10-05 | 2017-10-05
GRT-CQ02-P0MAJ-460108 | Operation and Maintenance Manuals for Condenser & Water box vacuum pump | 2017-11-10 | 2018-01-20
GRT-XG02-P0UGD-115287 | [WTP] Piping and instrument diagram (PID) Service Water System | 2017-02-21 | 2017-03-23
GRT-CV03-P0SCA-120024 | [Air Compressor]_INSTRUMENT SPECIFICATION | 2017-05-20 | 2017-09-17
GRT-YR02-P0BCA-165708 | Site Acceptance Test (SAT) LDC Panel | 2020-01-30 | 2020-02-29
GRT-YE07-P0UMA-155240 | [STG BUILDING] Grounding Wiring Layout | 2017-04-08 | 2017-05-08
GRT-XB00-P0MA-200013 | [STG]_Allowable loadings and displacements | 2017-03-10 | 2017-10-25
GRT-CC07-P0UZA-175429 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Calculation Sheet | 2017-07-30 | 2017-08-19
GRT-XL00-P0MAG-410004 | Condenser_Connection Detail | 2017-02-10 | 2017-05-10
GRTBCP-YD00-P0BBA-156003 | General Arrangement MV Switchgear 6,3kV | 2017-10-31 | 2017-11-30
GRT-YK08-P0MAG-410001 | Condenser_General Layout | 2017-02-10 | 2017-05-10
GRT-CC09-P0UZA-175448(2OF2) | [Structure for Transport, Trafic & Other Purpose] Pipe Rack Foundation Detail | 2017-07-30 | 2017-08-29
GRT-YF00-P0LA-161305 | [Feedwater system_I&C_Loop]_Control Loop Diagram for BOP | 2017-04-28 | 2017-07-31
GRT-YK00-P0ZEN-164303 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Material List | 2017-04-21 | 2017-08-31
GRT-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | 2017-01-10 | 2017-04-10
GRT-YF00-P0ZEN-161406 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram for Shutdown | 2017-08-18 | 2017-11-16
GRT-CA00-P0UMA-175245 | [STG BUILDING] Floor Plan, Roof Plan & Finishing Schedule | 2017-03-04 | 2017-04-03
GRT-XW03-P0ZEN-156352 | SURGE ARRESTER OUTLINE DRAWING PACKAGE | 2018-12-31 | 2019-01-30
GRT-YD00-P1H-300036 | [HRSG]_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | 2017-06-20 | 2017-09-20
GRTBCP-YS01-P0BFB-156025 | Schematic Diagram LV Switch Gear 2 | 2018-01-26 | 2018-02-25
GRT-XS00-P0LC-110403 | [Condensate system]_SYSTEM DESCRIPTION | 2017-02-28 | 2017-07-14
GRT-XW03-P0ZEN-115016 | [Process General] Hydraulic Calculation | 2017-05-13 | 2017-06-12
GRT-YU01-P0BJE-156059 | Single Line Diagram Valve PDB | 2018-01-26 | 2018-02-25
GRT-XG02-P0UGD-115469-2 | P & ID For Waste Water Transfer System ( 2 of 2 ) | 2017-06-12 | 2017-07-12
GRT-YL01-P0UGD-165336 | [DCS] I/O List for Auxiliary Service Water System | 2017-02-28 | 2017-03-30
GRT-CQ02-P0LAC-122522 | [LP Feed Water Pump]_Operational & Maintenance Manual | 2018-04-20 | 2018-05-31
GRT-DF04-P1H-300002 | [HRSG]_STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | 2017-04-20 | 2017-07-20
GRT-YU03-P0SCA-120016 | [Air Compressor]_ELECTRICAL SCHEMATIC DIAGRAM | 2017-05-20 | 2017-10-17
GRT-CC07-P0UAG-175366 | [Transformer] Calculation Sheet for Foundation | 2017-06-20 | 2017-07-20
GRT-YB03-P0PAH-440006 | Configuration Diagram of Package System for CTCS & Debris Filter | 2017-06-01 | 2017-10-31
GRT-YT01-P0UGD-115282 | [WTP] Process data sheet for raw water tank | 2017-02-23 | 2017-03-25
GRT-CV03-P0ZEN-165098 | [Instrument General] Data Sheet for Telephone System | 2017-06-14 | 2017-07-14
GRT-YL22-P0PCC-113009 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 2017-08-12 | 2017-11-10
GRT-YS01-P0ZEN-156198 | 150KV GRT General Arrangement Protection Diameter X & 1 Switchboard | 2019-02-13 | 2019-03-15
GRT-YF02-P0QC-130006 | [Chemical Dosing System]_CONTROL CONFIGURATION DIAGRAM | 2017-07-11 | 2017-10-23
GRT-YT01-P0UGD-125300 | [WTP] Mech. Data Sheet for Make-up Demin Water Tank | 2017-06-23 | 2017-07-23
GRT-YQ01-P0UGD-155396 | [Fire Fighting Shelter] Lighting and Receptale Wiring Layout | 2017-07-14 | 2017-08-13
GRT-XW01-P0UGX-115184 | [Chlorination System] Process specification for Chlorination system | 2017-06-07 | 2017-07-07
GRT-YD00-P0MA-200024 | [STG]_Generator Specification | 2017-05-14 | 2017-09-13
GRT-QA00-P0ZEN-141003 | Welder qualificatoin list for BOP Piping | 2017-09-15 | 2017-12-15
GRT-YS18-P0LB-111103 | [Bypass Valve & PRDS]_CIRCUIT DIAGRAM FOR HYDRAULIC POWER UNIT | 2017-07-28 | 2017-10-26
GRT-CA01-P0UGX-175209 | [Chlorination System] Foundation Detail | 2017-06-23 | 2017-07-23
GRT-YV02-P0SCA-120022 | [Air Compressor]_I&C WIRING DIAGRAMS | 2017-05-20 | 2017-10-17
GRT-XH01-P0UTG-144523 | [N2 Gas Shelter_Piping]_Piping Arrangement | 2017-06-02 | 2017-09-29
GRT-YD00-P0GAD-125625 | CW PUMP AUXILIARY UNIT PACKAGE | 2019-02-13 | 2019-03-15
GRT-YR05-P0ZEN-161132 | [DCS]_Outline & Detail Drawing for LAN Cabinet | 2017-04-07 | 2017-07-07
GRT-HM01-P0UGD-125453 | [WTP] WTP Building HVAC Equipment Layout | 2019-02-13 | 2019-03-15
GRT-YF00-P0ZEN-165571 | Instrument Control loop for Raw Water System | 2017-10-24 | 2017-10-24
GRT-YD00-P1H-300070 | [HRSG]_ERECTION ISOMETRIC DRAWING FOR SMALL BORE PIPING | 2018-06-29 | 2018-07-27
GRT-YE07-P0UCA-155410 | [Electrical Room] Grounding Wiring Layout | 2017-06-14 | 2017-07-14
GRT-CA01-P0UMA-175252 | [STG BUILDING] Basement Floor Plan, El +3.104,EL+2.604, EL.+0.544, EL-0.496, & El-1.150 ( T.O.C ) | 2017-03-07 | 2017-04-06
GRT-YS05-P0ZEN-162703 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for MOV | 2017-03-17 | 2017-07-31
GRT-YT02-P1H-300065 | [HRSG]_REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | 2017-09-20 | 2017-11-20
GRT-CC04-P0ZEN-156236 | Common Switchgear Steel Structure Beam Type B1 | 2018-02-05 | 2018-02-19
GRT-YF00-P0PG-161208 | [Closed cooling water system_I&C_Logic]_Control Logic Diagram for BOP | 2017-04-21 | 2017-07-31
GRT-YK09-P0MA-200032 | [STG]_Cabling system | 2017-11-11 | 2018-03-10
GRT-XG02-P0LAC-122501 | [LP Feed Water Pump]_P&I DIAGRAM | 2017-04-20 | 2017-07-20
GRT-UE00-P0ZEN-100009 | General Arrangement of Steam Turbine Building Section B-B | 2017-03-17 | 2018-10-01
GRT-YK08-P0LAA-420001 | Outline Drawing for Deaerator & Feedwater Storage Tank | 2017-04-28 | 2017-06-29
GRT-YL22-P0QC-130018 | [Chemical Dosing System]_NAME PLATE DRAWING | 2017-09-09 | 2017-12-22
GRT-YE06-P0UAG-155359 | [Transformer] Grounding Wiring Layout | 2017-06-23 | 2017-07-23
GRT-YR02-P0ZEN-156187 | Common Switchgear Technical Specification Conductor | 2018-02-05 | 2018-02-19
GRT-XW03-P0ZEN-156274 | 150 kV Grati Switchgear Calculation Note lightning Arrester Checking | 2018-02-05 | 2018-02-19
GRT-YT02-P0LAC-122506 | [LP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | 2017-06-20 | 2017-10-20
GRT-YK10-P0LAC-122504 | [LP Feed Water Pump]_SECTIONAL DRAWING FOR PUMP | 2017-05-20 | 2017-08-20
GRT-DE00-P0ZEN-145033 | [Piping General] Piping Material Specification | 2017-02-11 | 2017-03-13
GRT-YD00-P0SM-123001 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING FOR HOISTS | 2017-05-19 | 2017-08-18
GRT-CQ02-P0LAA-420003 | OPERATING AND MAINTENANCE MANUAL FOR DEAERATOR & FEEDWATER STORAGE TANK | 2018-04-20 | 2018-06-30
GRT-YD00-P0BFC-156028 | General Arrangement LV Switchgear 3 | 2017-11-24 | 2017-12-24
GRT-YD00-P0AT-156284 | NGR Drawing SST & UAT | 2017-10-19 | 2017-11-18
GRT-YT01-P1H-300059 | [HRSG]_MOV DATASHEET & DRAWINGS | 2017-07-20 | 2017-10-20
GRT-YL22-P0LB-111108 | [Bypass Valve & PRDS]_Name Plate Drawing | 2017-09-14 | 2017-12-13
GRT-YK00-P0PAC-165689 | Hook Up for BOP Area | 2019-02-13 | 2019-03-15
GRT-PL03-P0MAJ-460220 | Terminal Point List For Water Box Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-XW03-P0PAC-155149 | [Circulating Water Pump] Cable Size Calculation for Sea Water Intake | 2017-02-03 | 2017-03-05
GRT-YT01-P0ZEN-145038 | [Piping General] Data Sheet for Valve | 2017-03-18 | 2017-04-17
GRT-CA03-P0UMA-175266 | [STG BUILDING] Steam Turbine Building Steel Structure Framing Elevation Line SA0 & SA | 2017-03-07 | 2017-04-06
GRT-XG11-P0SGA-133003 | [Fire Fighting System] Single Line Diagram for STG Enclosure Inside | 2018-06-15 | 2018-09-14
GRT-YK00-P0ZEN-165119 | [Instrument General] Paging Typical Drawing for Installation | 2017-04-26 | 2017-05-26
GRT-CC07-P0LDB-130039 | [Condensate Filter System]_CALCULATION SHEET | 2017-05-26 | 2017-09-08
GRT-YL22-P0LAC-122008 | [HP Feed Water Pump]_Hydraulic Coupling Data Sheet | 2017-10-31 | 2017-11-30
GRT-YL00-P0SCA-120023 | [Air Compressor]_INSTRUMENT LIST | 2017-05-20 | 2017-09-17
GRT-CV03-P0UGD-165559 | Instrument Data Sheet for Waste Water Transfer System | 2017-08-07 | 2017-08-07
GRT-YT01-P0LDB-130047 | [Condensate Filter System]_TECHNICAL DATASHEET | 2017-07-25 | 2017-11-07
GRT-YD00-P0BJN-156093 | General Arrangement HVAC | 2017-11-24 | 2017-12-24
GRT-YK10-P0QC-130010 | [Chemical Dosing System]_EQUIPMENT ASSEMBLY DRAWING | 2017-08-10 | 2017-11-22
GRT-CN00-P0ZEN-110104 | [Plant Overall]_Hazardous Area Classification | 2017-05-30 | 2017-08-28
GRT-YS02-P0ZEN-155075 | [Electrical General] Connection Diagram For Power and Control Cable | 2017-06-14 | 2017-07-14
GRT-YK10-P0ZEN-113400 | [MOV (Butterfly)(DHI)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | 2017-08-15 | 2017-11-13
GRT-XG02-P0QJA-110010 | [N2 Gas system]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-DA06-P0MAJ-460122 | Utility Consumption List For Condenser Vacuum Pump | 2017-08-08 | 2017-11-08
GRT-XG02-P0SG-115382 | [Fire Fighting System] Piping & Instrument Diagram for firewater system | 2017-03-20 | 2017-04-19
GRT-CC03-P0UMA-175600 | Cable Trench and Duct Bank Lay out Area 3 | 2017-11-21 | 2017-12-21
GRT-CC03-POUMA-175592 | Steam Turbine Building Condensate Pump Foundation Detail (include attachment calculation) | 2018-12-25 | 2019-01-24
GRT-YK09-P1H-300049 | [HRSG]_SPECIALTY DRAWING FOR EXTERNAL PIPING | 2017-09-20 | 2017-12-20
GRT-XL00-P1H-300028 | [HRSG]_LINE LIST | 2017-05-20 | 2017-08-20
GRT-CV03-P0UGD-165315 | [WTP] Instrument Data Sheet for Raw Water System | 2017-03-02 | 2017-04-01
GRT-UE00-P0ZEN-100005 | General Arrangement of Steam Turbine Building Operating Floor | 2017-03-17 | 2018-10-01
GRT-YD00-P0BFA-156123 | General Arrangement NSPB-1 | 2017-11-17 | 2017-12-17
GRT-CC09-P0UZA-175450(1OF3) | PIPE RACK STEEL STRUCTURE PLAN EL. +19.004(T.O.S) & FRAMING ELEVATION LINE | 2017-05-01 | 2017-05-31
GRT-YK08-P0LB-111102 | [Bypass Valve & PRDS]_OUTLINE DRAWING FOR HYDRAULIC POWER UNIT | 2017-07-28 | 2017-10-26
GRT-YD16-P0UGD-155309 | [WTP] Cable Tray and Power Wiring Layout | 2017-03-22 | 2017-04-21
GRT-CC03-P0UMA-175598 | Cable Trench and Duct Bank Lay out Area 1 | 2017-11-21 | 2017-12-21
GRT-YS05-P0ZEN-162705 | [INC_Design_Criteria_Cable]_Typical I&C Cable Installation Drawing for Conduit Support | 2017-03-17 | 2017-07-31
GRT-YK08-P0MAG-410002 | Condenser_General Arrangement | 2017-02-10 | 2017-05-10
GRT-CC03-P0UMA-175274 | [STG BUILDING] Foundation Elevation, Section and Detail (2/2) | 2017-03-07 | 2017-04-06
GRT-YU01-P0BJM-156099 | Single Line Diagram Feeder PDB-01 | 2017-12-07 | 2018-01-06
GRT-CV03-P0ZEN-163706 | [Local Boxes(DHI)]_Technical Specification for Junction Box & Racks | 2017-07-25 | 2017-11-05
GRT-YR04-P0ZEN-165121 | [Instrument General] Instrument General Symbol & Index | 2017-02-18 | 2017-03-20
GRT-YD00-P0ZEN-165102 | [Instrument General] CCTV Location Plan Layout | 2017-09-14 | 2017-07-30
GRT-YD00-P0UGD-120034 | Roof Manhole Scetion and Detail | 2017-03-11 | 2017-03-11
GRT-UE00-P1H-300008 | [HRSG]_ARRANGEMENT OF INLET DUCT | 2017-04-20 | 2017-07-20
GRT-XJ00-P0PAB-143007 | Piping ISO (Small Bore) - Aux. cooling water | 2017-07-21 | 2018-01-31
GRT-YT01-P0LB-111110 | [Bypass Valve & PRDS]_Data Sheet for HPU | 2017-07-28 | 2017-10-26
GRT-CA01-P0UGD-175347 | [WTP] Foundation Plan | 2017-03-22 | 2017-04-21
GRT-FF03-P0SGA-133001 | [Fire Fighting System] Water Spray System P&ID for STG Enclosure Inside | 2018-06-05 | 2018-09-07
GRT-YK10-P0MA-200058 | [STG]_Main assembly manual | 2018-02-28 | 2018-05-22
GRT-YK00-P0ZEN-164312 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Temp.Transmitter/ Guage/ Test Well | 2017-04-21 | 2017-08-31
GRT-DN02-P1ZEN-830019 | [Commissioning Procedure] Disturbance Test | 2018-04-30 | 2018-06-30
GRT-XG02-P0QC-130001 | [Chemical Dosing System]_P&ID | 2017-07-11 | 2017-10-23
GRT-QA00-P0H-040018 | [HRSG]_Welding Consumable Control Procedure for HRSG Piping | 2017-09-28 | 2017-12-28
GRT-YU01-P0BJJ-156079 | Single Line Diagram Feeder UPS-01 | 2018-01-26 | 2018-02-25
GRTH-YR01-P0ZEN-115017 | Procedure for Hazop Study | 2017-06-09 | 2017-07-09
GRT-YF00-P0ZEN-161212 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Miscellaneous System | 2017-04-28 | 2017-07-31
GRT-CC03-P0UMA-175587 | Steam Turbine Building HP Feedwater Pump & LP feedwater Pump Foundation Detail | 2017-10-11 | 2017-11-10
GRT-YT01-P0UGD-125304 | [WTP] Mech. Data Sheet for Service Water Pump | 2017-03-02 | 2017-04-01
GRT-DN02-P0LBG-830002 | [Commissioning Procedure] Auxiliary Steam System | 2018-01-30 | 2018-03-30
GRT-XW03-P0LA-110500 | [BFP_Design]_sizing Calculation | 2017-03-03 | 2017-07-14
GRT-CC03-P0UBN-175568 | Emergency Diesel Generator Concrete Structure Foundation Plan & Detail | 2017-09-13 | 2017-09-13
GRT-XJ00-P0PAB-143015 | Piping ISO (Small Bore) - Cooling water | 2017-07-07 | 2018-01-31
GRT-VS02-P0BTL-156359 | Battery Rack 2000AH for UPS System | 2017-11-24 | 2017-12-24
GRT-XW03-P0UGD-115297 | [WTP] Process calculation for make up demin system pump | 2017-02-23 | 2017-03-25
GRT-YF00-P0ZEN-165578 | Instrument Control Loop for Electrical | 2017-11-03 | 2017-11-03
GRT-XW03-P0ZEN-156275 | 150kV Grati Switchgear Calculation Note Compatibility CVT | 2019-10-30 | 2019-11-29
GRT-XK00-P0LCM-144004 | Support DWG (Large Bore) - Steam drain | 2017-12-31 | 2018-01-30
GRT-XB02-P0AT-156129 | Foundation Drawing 150/15.75 kV – 250 MVA Power Transformer | 2017-10-06 | 2017-11-05
GRT-YU01-P0ZEN-155077 | [Electrical General] Single Line Diagram for MV System | 2017-02-25 | 2017-03-27
GRT-YS00-P0ZEN-163302 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | 2017-03-03 | 2017-05-31
GRT-XW03-P0ZEN-156183 | 150kV Grati Switchgear Technical Specification Protective Relays | 2018-02-05 | 2018-02-19
GRT-XG02-P0PA-110008 | [Aux. Cooling Water System]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-YR05-P0ZEN-165123 | [Instrument General] General Specification for CCTV | 2017-04-16 | 2017-05-16
GRT-YD00-P0ZEN-120006 | Roof Plate Arrangement Section & Detail Make up Demin Tank | 2017-11-09 | 2017-10-10
GRT-YE00-P0ZEN-155043 | [Electrical General] General Area Clock System Wiring Layout | 2017-03-15 | 2017-04-14
GRT-CC03-P1UHA-175611 | Elevation HRSG Foundation Plan, detail & Section | 2018-01-04 | 2018-01-04
GRT - YT01 - P0GCK - 126802 | Data Sheet Blow Down Transfer Pump | 2018-02-02 | 2018-02-16
GRT-CC03-P0UZA-175427 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | 2017-07-20 | 2017-03-30
GRT-YK08-P0MAJ-460100 | General Arrangement Drawing For Condenser Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-YD00-P0BTL-156363 | General Arrangement DC System | 2017-11-14 | 2017-12-14
GRT-YR02-P0ZEN-155054 | [Electrical General] Specification for Auxiliary & Service Transformer | 2017-02-18 | 2017-03-20
GRT-YS01-P0ZEN-165126 | [Instrument General] Paging System Block Diagram | 2017-06-14 | 2017-07-14
GRT-YT01-P0QC-130016 | [Chemical Dosing System]_INSTRUMENT DATA SHEET | 2017-08-10 | 2017-11-22
GRT-CC03-P0UGD-175353 | [WTP] Make Up Demin for Deaerator Pump Foundation | 2017-06-23 | 2017-07-23
GRT-VN03-P1H-300010 | [HRSG]_TYPICAL PLATFORM DETAIL FOR STEEL STRUCTURE | 2017-05-20 | 2017-08-20
GRT-XW03-P0UGD-115293 | [WTP] Process calculation for sump pumps | 2017-04-06 | 2017-05-06
GRT-YK00-P0ZEN-164310 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Stanchion & Rack | 2017-04-21 | 2017-08-31
GRT-YR02-P0ZEN-155068 | [Electrical General] Datasheet for Distribution & Lighting Panel | 2017-03-08 | 2017-04-07
GRT-YL01-P0PAC-165160 | [Circulating Water Pump] I/O List | 2017-03-11 | 2017-04-10
GRT-XG02-P0PAC-115131 | Piping & Instrument Diagram for Sea Water Intake | 2019-02-13 | 2019-03-15
GRT-YL15-P0ZEN-165115 | [Instrument General] Instrument Cable Drum Schedule for BOP | 2017-04-29 | 2017-05-29
GRT-YK09-P0MA-200029 | [STG]_Frequency converter for turning gear | 2017-11-11 | 2018-03-10
GRT-YS00-P0ZEN-163309 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Binary Output | 2017-03-03 | 2017-05-31
GRT-YK09-P0MA-200020 | [STG]_Functional description | 2017-05-21 | 2017-08-28
GRT-XL35-P0LB-111109 | [Bypass Valve & PRDS]_Instrument List & Database Sheet | 2017-07-14 | 2017-10-12
GRT-XA00-P0PCC-106803 | GA Drawing Service Water Pump | 2018-02-07 | 2018-02-21
GRT-YD00-P0AT-156118 | General Arrangement Drawing of Unit Station Service Transformer 25MVA | 2017-10-18 | 2017-11-17
GRT-YD00-P0PGB-400040 | Outline Drawing for CCW Heat Exchanger | 2017-03-08 | 2017-08-05
GRT-YQ01-P0UMA-155242 | [STG BUILDING] Lighting and Receptacle Wiring Layout | 2017-04-08 | 2017-05-08
GRT-YS01-P0QC-130020 | [Chemical Dosing System]_SCHEMATIC DIAGRAM | 2017-09-09 | 2017-12-22
GRT-YT01-P0MKA-156159 | Generator Data Sheets | 2017-12-11 | 2018-01-10
GRT-DN02-P1ZEN-830027 | [Commissioning Procedure] Performance Test | 2018-07-30 | 2018-10-30
GRT-XS00-P0SC-120005 | [Compressed air system]_DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | 2017-02-06 | 2017-06-06
GRT-YK09-P0MA-200027 | [STG]_Electrical Protections | 2017-11-11 | 2018-03-10
GRT-DN02-P0QC-830008 | [Commissioning Procedure] Chemical Dosing System | 2018-03-30 | 2018-05-30
GRT-CC07-P0UZA-175420 | [Structure for Transport, Trafic & Other Purpose] Calculation for Sheet Pile and Concrete Batter Pile for Thermal Barier | 2017-07-14 | 2017-08-13
GRT-CC03-P0UGD-175355 | [WTP] Raw Water Tank Pump Foundation | 2017-06-23 | 2017-07-23
GRT-DN02-P0MAJ-830011 | [Commissioning Procedure] Condenser Vacuum System | 2018-02-28 | 2018-04-30
GRTBP-YD00-P0GD-155935 | PANEL ARRANGEMENT OF ELECTROCHLORINATION | 2019-02-13 | 2019-03-15
GRT-YL22-P0PCC-113008 | [Aux. Cooling Water Pump]_NAMEPLATE DRAWING FOR AUXILIARY COOLING WATER PUMP | 2017-08-12 | 2017-11-10
GRT-CC03-P0UMA-175272 | [STG ] Concrete Structure Foundation Plan & Section | 2017-04-08 | 2017-05-08
GRT-YS01-P0BYA-165668 | GTCS-Spare Part List | 2017-12-05 | 2017-12-19
GRT-YD00-P0ZEN-165683 | GENERAL ARRANGEMENT LOCAL PANEL FIRE FIGTHING | 2019-02-13 | 2019-03-15
GRT-YE03-P0PAC-155152 | [Circulating Water Pump] Grounding and Lightning Protection Layout | 2017-02-03 | 2017-03-05
GRT-YT01-P1H-300069 | [HRSG]_ SPEC. & DRAWING FOR PREHEATER RECIRCULATION PUMP | 2017-08-29 | 2017-11-29
GRT-QA00-P0H-040011 | [HRSG]_Welders List for HRSG LP Drum | 2017-08-29 | 2017-11-29
GRT-XB00-P0MA-200001 | [STG]_Foundation - Shape & Anchoring | 2017-02-28 | 2017-07-14
GRT-XK00-P0MAA-144010 | Support DWG (Large Bore) - ST Misc. | 2017-12-31 | 2018-01-30
GRT-YR02-P0ZEN-155052 | [Electrical General] Specification for Emergency Diesel Generator | 2017-03-07 | 2017-04-06
GRT-YT01-P0BJN-156310 | Data Sheet HRSG PDB-1 | 2017-11-24 | 2017-12-24
GRT-CC09-P0UZA-175451 | Foundation Support NSPB | 2019-01-20 | 2019-02-19
GRT-YR02-P0ZEN-155053 | [Electrical General] Specification for Main Transformer | 2017-02-18 | 2017-03-20
GRT-CC03-P0UMA-175277(1OF2) | [STG ] Concrete structure Insert Plate Plant and Detail | 2017-06-05 | 2017-05-07
GRT-YT01-P0LAC-122005 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | 2017-04-20 | 2017-07-20
GRT-YD00-P0UGD-165320 | [WTP] Instrument Cable Wiring Layout for Raw Water System | 2017-03-29 | 2017-04-28
GRT-YT01-P0BJN-156307 | General Arrangement HRSG PDB-1 | 2017-11-24 | 2017-12-24
GRT-QM03-P0ZEN-141009 | LIQUID PENETRANT EXAMINATION PROCEDURE | 2017-10-11 | 2017-11-13
GRT-YF00-P0LA-161205 | [Feedwater system_I&C_Logic]_Control Logic Diagram for BOP | 2017-04-28 | 2017-07-31
GRT-XW03-P0ZEN-156212 | 150kV Grati Switchgear Outdoor Installation Busbar-Section | 2018-04-02 | 2018-05-02
GRT-YT02-P0GD-165925 | Data Sheet Pressure Switch | 2017-07-21 | 2017-08-20
GRT-YK08-P0MAG-410012 | Transition Piece Assembly between LP TBN and Condenser | 2017-10-13 | 2017-12-30
GRT-HM05-P0UGD-125452 | HVAC Calculation for Water Treatment Building | 2017-10-04 | 2017-10-04
GRT-CC03-P0PAC-175170(1OF7) | [Circulating Water Pump] Circulating Water Pump Stop Log Detail and Section | 2017-02-14 | 2017-03-16
GRT-YU01-P0BJO-156104 | Single Line Diagram Feeder PDB-02 | 2018-01-26 | 2018-02-25
GRT-YS02-P0PAC-165162 | [Circulating Water Pump] Instrument Termination Diagram for Circulating Water Pump | 2017-03-11 | 2017-04-10
GRT-CC04-P0ZEN-156247 | Common Switchgear Steel Structure CSE SUPPORT - IB583 | 2018-02-05 | 2018-02-19
GRT-YD00-P0PGB-430030 | Outline Drawing for CCW Expansion Head Tank | 2017-03-08 | 2017-08-05
GRT-UE00-P0ZEN-100003 | General Arrangement of Steam Turbine Building Ground Floor | 2017-03-17 | 2018-10-01
GRT-YF00-P0ZEN-161402 | [INC_Start&Shutdown Diagram]_Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | 2017-08-18 | 2017-11-16
GRT-CC03-P0UMA-175605 | Culvert Detail, Section & Schedule (2/2) | 2017-11-21 | 2017-12-21
GRT-YF00-P0ZEN-161211 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Interface with other Control System | 2017-04-28 | 2017-07-31
GRT-YU03-P0MA-200043 | [STG]_Control system. Hardware specification | 2017-07-22 | 2017-11-21
GRT-YD00-P1H-300034 | [HRSG]_PRESSURE PART ARRANGEMENT | 2017-03-20 | 2017-07-20
GRT-YL00-P0LDB-130042 | [Condensate Filter System]_INSTRUMENT LIST | 2017-06-26 | 2017-10-08
GRT-YS02-P0UGD-165344 | [WTP] Instrument Termination Diagram for Service Water System | 2017-07-07 | 2017-08-06
GRT-YK08-P0BAA-156316 | GA & Wiring Diagram of Pressurisation Cubicle for 15.75kV IPBD | 2017-12-13 | 2018-01-12
GRT-YT001-P0ZEN-145427 | General Arrangement for Check Valve | 2017-10-16 | 2017-10-16
GRT-CA01-P0UMA-175257 (1 OF 3) | Steam Turbine Building Electrical Room Floor Plan Slab Schedule, Sections and Detail | 2019-01-07 | 2019-02-06
GRT-YD00-P0PGB-113101 | [CCWP ]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | 2017-06-12 | 2017-09-10
GRT-CC00-P0UMA-145453-2 | Piping Layout Drawing Steam Turbine Generator Area | 2017-09-13 | 2017-09-13
GRT-YU01-P0ZEN-155079 | [Electrical General] Single Line Diagram for UPS & DC System | 2017-02-28 | 2017-03-30
GRT-CC07-P0UMA-175583 | Calculation Sheet for Equipment Foundation on STG Building Grounding Floor | 2017-10-11 | 2017-11-10
GRT-CQ02-P0LCB-121013 | [Condensate Extraction Pump]_O&M MANUAL | 2018-01-22 | 2018-04-22
GRT-YU01-P0BFB-156024 | Single Line Diagram LV Switchgear 2 | 2018-01-26 | 2018-02-25
GRT-CA01-P0PAC-175183 | Toilet STG | 2020-10-13 | 2020-11-12
GRT-HM01-P0UGX-125187 | [Chlorination System] Chlorination Plant Building HVAC Flow Schematic Diagram | 2017-03-11 | 2017-04-10
GRT-XK00-P0MAJ-460213 | Tank Drawing For Water Box Vacuum Pump | 2017-08-04 | 2017-09-08
GRT-XW03-P0ZEN-155086 | [Electrical General] Transformer Sizing Calculation | 2017-02-18 | 2017-03-20
GRT-CA01-P0UGD-175563 | Water Treatment Plant Concrete Structure Section and Detail | 2017-09-04 | 2017-09-04
GRT-YR01-P1H-300055 | [HRSG]_CONSERVATION PROCEDURE | 2017-09-20 | 2017-12-20
GRT-XK00-P0MAJ-460113 | Tank Drawing For Condenser Vacuum Pump | 2017-08-04 | 2017-09-08
GRT-CA00-P0UGX-175207 | [Chlorination System] Section, Detail & Finishing Schedule | 2017-06-23 | 2017-07-23
GRT-YT01-P0MAG-410009 | Condenser_Performance Curves | 2017-02-10 | 2017-05-10
GRT-XW01-P0ZEN-115012 | [Process General] Overpressure study | 2017-06-15 | 2017-07-15
GRT-XW03-P0UGD-120002 | Mechanical Calculation & Orentation | 2017-03-11 | 2017-03-11
GRT-HM01-P0UGX-125188 | [Chlorination System] Chlorination Plant Building HVAC Ducting Layout | 2017-03-11 | 2017-04-10
GRT-YD00-P0SCA-120007 | [Air Compressor]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | 2017-04-20 | 2017-07-19
GRT-YT01-P0PAC-115136 | Sea Water Intake Pump Process Data Sheet | 2017-02-03 | 2017-03-05
GRT-CA01-P0UMA-175250 | [STG BUILDING] Foundation Plan (1/2) | 2017-03-07 | 2017-04-06
GRT-XW01-P0SCA-120010 | [Air Compressor]_AIR DRYER SPECIFICATION | 2017-04-20 | 2017-07-19
GRT-XN00-P0ZEN-145037 | [Piping General] Valve List | 2017-03-11 | 2017-04-10
GRT-XW03-P0ZEN-115014 | [Process General] Process Calculation for IA & PA consumption | 2017-06-15 | 2017-07-15
GRT-YS00-P0ZEN-163303 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | 2017-03-03 | 2017-05-31
GRT-XJ00-P0SCB-143011 | Piping ISO (Small Bore) - Service air | 2017-07-28 | 2018-01-31
GRT-XV00-P0ZEN-145036 | [Piping General] Pipe Support List | 2017-06-07 | 2017-07-07
GRT-YW06-P0UAA-155371 | [Switchyard] Grounding Wiring Layout | 2017-06-23 | 2017-07-23
GRT-YD16-P0UMA-155238 | [STG BUILDING] Cable Tray & Power Wiring Layout | 2017-06-14 | 2017-07-14
GRT-XG02-P0UGD-115291 | [WTP] Piping and Instrumentation Diagram for Interconnecting System | 2017-02-21 | 2017-06-05
GRT-XW01-P0LBG-110201 | [AUX Steam System]_DESIGN CRITERIA | 2017-02-22 | 2017-07-14
GRTBCP-YS01-P0BJH-156075 | Schematic Diagram BOP Essential PDB | 2018-01-26 | 2018-02-25
GRT-CC09-P0UZA-175450(3OF3) | PIPE RACK STEEL STRUCTURE ELEVATION LINE S8-A & S8-B | 2017-05-01 | 2017-05-31
GRT-YT01-P0UGD-125301 | [WTP] Mech. Data Sheet for Make up Demin for Closed Cooling System Pump | 2017-03-02 | 2017-04-01
GRT-CC03-P0PAC-175170(6OF7) | [Circulating Water Pump] Circulating Water Pump Gantry Crane Rail-2 Detail | 2017-02-14 | 2017-03-16
GRT-QA00-P0H-040004 | [HRSG]_Heat Treatment Procedure for HRSG Heat Exchanger | 2017-06-20 | 2017-09-20
GRT-CC03-P0UMA-175590 | Steam Turbine Building Foundation Detail | 2017-10-11 | 2017-11-10
GRT - YT01 - P0GCK - 126805 | Data Sheet Accumulation Sump Pit Pump | 2018-02-02 | 2018-02-16
GRT-XJ00-P0LCA-143006 | Piping ISO (Small Bore) - Condensate | 2017-07-14 | 2018-01-31
GRT-DP00-P0MJY-156158 | Diesel Genset Specification Sheet | 2017-10-31 | 2017-11-30
GRT-YS18-P0BTL-156176 | Battery Charger Circuit | 2018-02-05 | 2018-02-19
GRT-YK10-P0MA-200057 | [STG]_Instructions for steam turbine assembly | 2018-02-28 | 2018-05-22
GRT-CC03-P0UMA-175589 | Steam Turbine Building Foundation Detail | 2017-10-11 | 2017-11-10
GRT-YF00-P0ZEN-165568 | Instrument Control Loop for Sea Water Intake System | 2017-09-20 | 2017-09-20
GRT-CA03-P0UMA-175261 | [STG BUILDING] Steam Turbine Building Steel Structure Mezzanine Floor El +11.604 (F.F.L) | 2017-03-07 | 2017-04-06
GRT-YD00-P0UGD-120036 | Stairway Arrangement | 2017-11-14 | 2017-11-14
GRT-XK00-P0ZEN-144903 | Outline Drawing for Piping LP Manual Casting Valve | 2017-11-15 | 2017-12-01
GRTBCP-YS01-P0BJA-156040 | Schematic Diagram STG Unit MCC | 2018-01-26 | 2018-02-25
GRT-YL01-P0ZEN-161102 | [INC_DCS_IO]_3rd Party Data-link Interface Signal Database | 2017-09-15 | 2017-11-03
GRT-YM01-P0LCB-121009 | [Condensate Extraction Pump]_MOTOR DATA SHEET & CHARACTERISTIC CURVE | 2017-05-20 | 2017-09-20
GRT-YB10-P0MAJ-460203 | Terminal Box For Water Box Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-XW01-P0PG-110205 | [Closed cooling water system]_DESIGN CRITERIA | 2017-02-22 | 2017-07-14
GRT-YU01-P0BJM-156094 | Single Line Diagram Feeder HVAC | 2018-01-26 | 2018-02-25
GRT-YF00-P0ZEN-165112 | [Instrument General] Instrument Control Logic for Sea Water Intake System | 2017-07-07 | 2017-08-06
GRT-CA01-P0UMA-175253 | [STG BUILDING] Floor Plan EL. +.104 (T.O.C) | 2017-06-05 | 2017-07-05
GRT-XS00-P1H-300031 | [HRSG]_SYSTEM DESCRIPTION | 2017-04-20 | 2017-05-20
GRT-CC03-P0UZA-175422 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Layout | 2017-07-14 | 2017-08-13
GRT-DE00-P0ZEN-145034 | [Piping General] Specification for Cement Lined for Carbon Stell pipe | 2017-02-23 | 2017-03-25
GRT-CA03-P0MA-200004 | [STG]_Steel structures | 2017-10-25 | 2018-02-24
GRT-YT01-P0MAG-410008 | Condenser_Nozzle Force and Moment | 2017-02-10 | 2017-05-10
GRT-CV03-P0ZEN-161116 | [DCS]_Functional Design Specification for Safety Related System | 2017-04-21 | 2017-06-30
GRT-DP00-P0ZEN-070001 | Painting specification | 2017-06-21 | 2017-09-21
GRT-YR02-P0ZEN-155058 | [Electrical General] Specification for Cable and Wire | 2017-03-08 | 2017-04-07
GRT-XG02-P0LC-110007 | [Condensate system]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-YD00-P0UGD-165327 | [WTP] Instrument Location Plan Layout for Water Treatment System | 2017-03-16 | 2017-04-15
GRT-YD00-P0UMA-165244 | [STG BUILDING] Instrument Main Cable & JB Layout | 2017-07-06 | 2017-08-05
GRT-UE00-P0ZEN-145571 | General Arrangement for Rubber Expansion Joint | 2017-10-20 | 2017-10-20
GRT-XV00-P0MA-200012 | [STG]_List of equipments | 2017-05-21 | 2017-10-25
GRT-CC03-P0UGD-175354 | [WTP] Service Water Pump Foundation | 2017-06-23 | 2017-07-23
GRT-YF00-P0PAH-440054 | CCW HEX Tube Cleaning System_Control Logic | 2017-06-01 | 2017-10-31
GRT-YD00-P0PAC-165157 | [Circulating Water Pump] Instrument Location Plan Layout | 2017-03-11 | 2017-04-10
GRT-XK58-P0GCK-125830 | GENERAL ARRANGEMENT ACID METERING TANK | 2017-09-14 | 2017-10-14
GRT-XJ00-P0SCA-140009 | Piping ISO (Large Bore) - Compressed air | 2017-06-30 | 2018-01-31
GRT-YS01-P0AT-156132 | Schematic Diagram of Contorl Cubicle 150/15.75 kV-250 MVA Power Transformer | 2017-10-19 | 2017-11-18
GRT-CC07-P0PAD-175180 | [Circulating Water Pump Outfall] Calculation Sheet for Circulating Water Pump Outfall | 2017-02-11 | 2017-03-13
GRT-YT01-P1H-300057 | [HRSG]_DATA & BOM OF INSULATION FOR INTERNAL PIPING | 2017-08-20 | 2017-11-20
GRT-YD00-P0LCB-121014 | [Condensate Extraction Pump]_VFD OUTLINE AND DATA SHEET | 2017-08-25 | 2017-10-25
GRT-CA03-P0UGD-175400 | [Fire Fighting Shelter] Steel Structure Framing Plan & Elevation | 2017-07-14 | 2017-08-13
GRT-CC07-P0UMA-175278 | [STG BUILDING] Calculation Sheet for Foundation | 2017-04-08 | 2017-05-08
GRT-XG02-P0ZEN-115004 | [Process General] Piping and Instrument Diagram (PID) Legends | 2017-02-17 | 2017-03-19
GRT-YR02-P0ZEN-155057 | [Electrical General] Specification for Distribution & Lighting Panel | 2017-03-08 | 2017-04-07
GRT-DA06-P0MAJ-460123 | Lubricant List For Condenser Vacuum Pump | 2017-07-14 | 2017-09-08
GRT-YS01-P0ZEN-156278 | 150KV GRATI SWITCHGEAR SCHEMATIC DIAGRAM ENERGY METER PANEL | 2019-02-13 | 2019-03-15
GRT-QA00-P0H-040017 | [HRSG]_Welding Consumable Control Procedure for HRSG Pressure Part | 2017-09-06 | 2017-12-06
GRT-YD05-P0SCA-120018 | [Air Compressor]_PLC HMI GRAPHICS | 2017-06-20 | 2017-10-18
GRT-YQ01-P0UAG-155362 | [Transformer] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-06-20 | 2017-07-20
GRT-CC07-P0UZA-175430 | [Structure for Transport, Trafic & Other Purpose] CALCULATION SHEET FOR LOCAL FOUNDATION AND PIPE SLEEPER | 2017-07-30 | 2017-08-19
GRT-CV03-P0PAC-165695 | INSTRUMENT DATA SHEET FOR CLAW SCREEN | 2019-02-13 | 2019-03-15
GRT-YT01-P0QC-130015 | [Chemical Dosing System]_VALVE DATA SHEET | 2017-08-10 | 2017-11-22
GRT-YT01-P0AT-156121 | Rating Plate SST | 2017-10-18 | 2017-11-17
GRT-CA06-P0UGD-175351 | Calculation Sheet for Water Treatment Plant Building Structure and Foundation | 2017-06-05 | 2017-07-05
GRT-YT01-P0UGD-115853 | Process Data Sheet for Aux Service Water Tank | 2019-02-13 | 2019-03-15
GRT-YB10-P0UBL-156315 | Support Structure Detail of 15.75kV IPBD | 2017-11-24 | 2017-12-24
GRT-DN02-P1LBF-830013 | [Commissioning Procedure] HRSG Safety Valve Popping Test | 2018-03-30 | 2018-05-30
GRT-YD00-P0QC-130005 | [Chemical Dosing System]_CONTROL PANEL ARRANGEMENT DRAWING | 2017-07-11 | 2017-10-23
GRT-XK00-P0ZEN-144900 | Outline Drawing for Piping Manual Ball Valve | 2017-11-15 | 2017-12-01
GRT-YU02-P1H-300066 | [HRSG]_ELECTRICAL SINGLE LINE DIAGRAMS | 2017-05-20 | 2017-08-20
GRT-XW03-P0ZEN-156354 | CURRENT TRANSFORMER OUTLINE DRAWING PACKAGE | 2018-12-31 | 2019-01-30
GRT-CC07-P0UGD-175467 | Calculation Sheet for Make –up Demin Water Tank Foundation | 2017-09-05 | 2017-09-05
GRT-YT01-P0BJF-156066 | Data Sheet BOP Essential MCC | 2017-11-24 | 2017-12-24
GRT-CV03-P0LAA-420002 | Datasheet for Deaerator & Feedwater Storage Tank | 2017-04-28 | 2017-06-29
GRT-DC01-P0GD-125920 | Data Sheet Rectifier | 2017-11-27 | 2017-12-27
GRT-YD00-P1H-300037 | [HRSG]_POWER DISTRIBUTION PANEL DRAWINGS | 2017-09-20 | 2017-12-20
GRT-YT01-P0LAC-122003 | [HP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | 2017-04-20 | 2017-07-20
GRT-QA00-P0H-040016 | WPS&PQR for HRSG Piping | 2017-08-29 | 2017-11-29
GRT-YL01-P0ZEN-165203 | IO List for Package Equipment | 2017-11-21 | 2017-11-21
GRT-CQ02-P0PAH-440104 | Debris Filter_Operation & Maintenance Manual | 2018-05-04 | 2018-06-29
GRT-YT01-P0ZEN-145039 | [Piping General] Data Sheet for Special Item | 2017-03-18 | 2017-04-17
GRT-YD00-P0BJL-156088 | General Arrangement Feeder Normal Lighting | 2017-11-24 | 2017-12-24
GRT-FF04-P0SGM-125443 | Fire Suppression/FM/200 Isometric | 2017-11-28 | 2017-12-28
GRT-CC06-P0UMA-175272 | Calculation Sheet for Steam Turbine Building Foundation | 2017-04-08 | 2017-05-08
GRT-YQ01-P0UGD-155397 | [Fire Fighting Shelter] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-07-07 | 2017-08-13
GRT-CA01-P0UMA-175255 (1 OF 2) | Steam Turbine Building Mezzanine Floor Plan El. +11.604 (T.O.C) Slab Schedule and Sections | 2019-01-07 | 2019-02-06
GRT-XK00-P0SCA-144009 | Support DWG (Large Bore) - Compressed air | 2017-12-31 | 2018-01-30
GRT-YE07-P0UGX-155195 | [Chlorination System] Lightning Protection Layout | 2017-03-11 | 2017-04-10
GRT-YV02-P0LDB-130052 | [Condensate Filter System]_INTERCONNECTION WIRING DIAGRAM | 2017-08-24 | 2017-12-07
GRT-UE00-P0ZEN-100007 | General Arrangement of Steam Turbine Building Basement Floor | 2017-03-17 | 2018-10-01
GRT-YU03-P0MA-200049 | [STG]_Wiring diagrams, Loop diagrams | 2017-11-22 | 2018-03-10
GRT-YD05-P0LD-135841 | HMI GRAPHICS WTP | 2019-02-13 | 2019-03-15
GRT-YE00-P0LDB-130056 | [Condensate Filter System]_CABLE TRAY LAYOUT DRAWING | 2017-08-24 | 2017-12-07
GRT-XG02-P0PG-110009 | [Closed cooling water system]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-XW03-P0PAC-155148 | [Circulating Water Pump] Grounding System Calculation for Sea Water Intake | 2017-02-03 | 2017-03-05
GRT-XB02-P0GAC-135931 | Foundation Layout ELECTROCHLORINATION | 2017-07-21 | 2017-08-20
GRT-XN00-P1H-300029 | [HRSG]_VALVE LIST | 2017-04-20 | 2017-07-20
GRTSCH-YD00-P0BAC-150004 | Name Plate | 2018-02-05 | 2018-02-19
GRT-YR05-P0ZEN-165692 | OUTLINE DRAWING FIRE FIGHTING SYSTEM | 2019-02-13 | 2019-03-15
GRT-YR02-P0ZEN-155055 | [Electrical General] Specification for Medium Voltage Switchgear and MCC | 2017-03-07 | 2017-04-06
GRT-CC04-P0ZEN-156249 | Common Switchgear Steel Structure SA SUPPORT H=4M - IB574 | 2018-02-05 | 2018-02-19
GRT-DP00-P0ZEN-125020 | [Mechanical General] Specification for Centrifugal Pump | 2017-02-25 | 2017-03-27
GRT-CC04-P1UHA-175613 | Elevation HRSG Steel Structure Framing Elevation | 2018-01-04 | 2018-01-04
GRT-YD00-P0BVC-156364 | General Arrangement DC Distribution Board 220V for DC System | 2017-11-14 | 2017-12-14
GRT-DN03-P0BAA-156308 | Site Inspection &Test Plan for 15.75kV IPBD | 2017-12-07 | 2018-01-06
GRT-YS01-P0ZEN-156196 | 150 kV Grati Switchgear Schematic Diagram Diameter 1 | 2018-02-05 | 2018-02-19
GRT-CA00-P0UGX-175206 | [Chlorination System] Chlorination System Architectural Plan, View, Section & Finishing Schedule | 2017-03-04 | 2017-04-03
GRT-YT02-P0LAC-122006 | [HP Feed Water Pump]_LIST AND DATA SHEET FOR INSTRUMENT | 2017-06-20 | 2017-10-20
GRT-YE07-P0UGD-155394 | [Fire Fighting Shelter] Grounding Wiring Layout | 2017-07-14 | 2017-08-13
GRT-YD00-P0BJG-156073 | General Arrangement BOP Essential PDB | 2017-11-24 | 2017-12-24
GRT-HM05-P0UMA-125237 | [STG BUILDING] HVAC Calculation for Steam Turbine Generator Building | 2017-06-20 | 2017-07-20
GRT-CC03-P0UMA-175604 | Culvert Detail, Section & Schedule (1/2) | 2017-11-21 | 2017-12-21
GRT-YT01-P0UGD-125451 | [WTP] Mech. Data Sheet for Portable Water Pump | 2017-02-28 | 2017-03-30
GRT-CA00-P0UGD-175346 | [WTP] Architectural door & Window key Plant and Schedule | 2017-06-12 | 2017-07-12
GRT-YL22-P0LCB-121012 | [Condensate Extraction Pump]_NAME PLATE DRAWING | 2017-06-20 | 2017-10-20
GRT-CC04-P0ZEN-156244 | Common Switchgear Steel Structure C.V.T. SUPPORT H=2.1m - IB575 | 2018-02-05 | 2018-02-19
GRT-VL00-P0MAG-410006 | Condenser_Foundation Detail | 2017-02-10 | 2017-05-10
GRT-YD00-P0AT-156108 | Termination Drawing of Auxiliary Transformer 25MVA | 2017-10-18 | 2017-11-17
GRT-CC00-P0UGD-175395 | Fire Fighting Shelter Architectural Plan, View, Section & Finishing Schedule | 2017-08-09 | 2017-08-09
GRT-YT01-P0PGB-113200 | [Blowdown Cooler]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | 2017-07-24 | 2017-10-22
GRT-XN00-P0MAJ-460219 | Valve and Specialty List For Water Box Vacuum Pump | 2017-07-21 | 2017-09-08
GRT-YD00-P0ZEN-120018 | Anchor Bolt Arrangemnt Section & Detail Make Up Demin Tank | 2017-11-09 | 2017-10-10
GRT-YV02-P0AT-156125 | Layout and Schematic Diagram for Remote Tap Charger Control Panel Transformer 25MVA 15.75/6.3kV | 2017-10-18 | 2017-11-17
GRT-XG07-P0PA-110304 | [Aux. & Closed Cooling Water System]_PROCESS FLOW DIAGRAM | 2017-03-15 | 2017-07-14
GRT-YK00-P0LCB-121011 | [Condensate Extraction Pump]_INSTRUMENTATION HOOK - UP DRAWING | 2017-06-20 | 2017-10-20
GRT-XB00-P0MA-200008 | [STG]_Loads plan - Levels | 2017-06-19 | 2017-11-24
GRT-YL01-P0LD-165846 | IO LIST FOR WTP | 2019-02-13 | 2019-03-15
GRT-YV02-P0QU-130032 | [Sampling System]_INTERCONNECTION WIRING DIAGRAM | 2017-09-18 | 2017-12-31
GRT-HM03-P0EBM-135647 | HVAC PACKAGE | 2019-03-26 | 2019-04-25
GRT-YR02-P0AT-156117 | Technical Specification SST 15kV | 2017-10-06 | 2017-11-05
GRT-QA00-P0H-040008 | [HRSG]_WPS&PQR for HRSG Heat Exchanger | 2017-08-29 | 2017-11-29
GRT-YT001-P0ZEN-145547 | Valve Closing Time Calculation Sheet | 2017-10-16 | 2017-10-16
GRT-YT01-P0ZEN-145568 | Data Sheet for rubber Expansion Join | 2017-10-20 | 2017-10-20
GRT-YT02-P0LD-165828 | DATA SHEET FLOW INDICATOR | 2017-10-18 | 2017-11-17
GRT-UE00-P1H-300006 | [HRSG]_GENERAL ARRANGEMENT | 2017-03-30 | 2017-06-30
GRT-QA00-P0ZEN-141005 | Welder consumable control procedure for BOP Piping | 2017-09-15 | 2017-12-15
GRT-YD00-P0UGD-165321 | [WTP] Instrument Location Plan Layout for Raw Water System | 2017-07-07 | 2017-08-06
GRT-YU01-P0BJG-156069 | Single Line Diagram Space Heater Panel | 2018-01-26 | 2018-02-25
GRT-YT01-P0UGD-125305 | [WTP] Mech. Data Sheet for Sump Pumps | 2017-04-13 | 2017-05-13
GRT-YK08-P0SMM-146538 | General Arrangement Rail A75 Overhead Crane | 2018-07-24 | 2018-08-23
GRT-DA06-P0ZEN-115002 | [Process General] Equipment list | 2017-04-27 | 2017-05-27
GRT-YF00-P1LBA-161303 | [HP & LP steam system_I&C_Loop]_Control Loop Diagram for BOP | 2017-04-14 | 2017-07-31
GRTBCP-YS01-P0BJD-156055 | Schematic Diagram HRSG PDB | 2018-01-26 | 2018-02-25
GRT-XJ00-P0LAB-143005 | Piping ISO (Small Bore) - Feedwater | 2017-07-14 | 2018-01-31
GRT-YL00-P0LCB-121010 | [Condensate Extraction Pump]_INSTRUMENT LIST | 2017-06-20 | 2017-10-20
GRT-YB03-P1H-300033 | [HRSG]_CABLE CONNECTION DIAGRAM | 2017-08-20 | 2017-11-21
GRT-DP00-P0ZEN-125021 | [Mechanical General] Specification & Design Criteria for HVAC | 2017-02-25 | 2017-03-27
GRT-YT01-P0ZEN-165127 | Process Data Sheet for Pressure Regulating Valve | 2019-02-13 | 2019-03-15
GRT-CA07-P0ZEN-179033 | ADDITIONAL WINGWALL INTAKE BLOCK 2 STABILITY | 2018-04-02 | 2018-05-02
GRT-YB10-P0MAJ-460103 | Terminal Box For Condenser Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-CC03-P0UAG-175363 | [Transformer] FOUNDATION PLAN, PLAN EL. +5.672 (T.O.S) SECTION, DETAIL & MEMBER SCHEDULE | 2017-06-20 | 2017-07-20
GRT-YT01-P1H-300056 | [HRSG]_DATA & BOM OF INSULATION FOR DRUM AND BLOWDOWN TANK | 2017-06-20 | 2017-09-20
GRT - YT01 - P0GCK - 126807 | Data Sheet CEP Sump Pit Pump | 2018-02-02 | 2018-02-16
GRT-XW03-P0ZEN-156192 | 150kV Grati Switchgear Single Line Diagram Diameter | 2017-11-14 | 2017-12-14
GRT-YT01-P0LCB-121006 | [Condensate Extraction Pump]_COUPLING SPECIFICATION | 2017-05-20 | 2017-08-20
GRT-XB00-P0MA-200007 | [STG]_Foundation load plan | 2017-03-10 | 2017-07-14
GRT-YT01-P0SG-125392 | [Fire Fighting System] Mech. Data Sheet for Fire Water Pump | 2017-03-27 | 2017-04-26
GRT-XW03-YD00-156395 | Cathodic Protection System ACWP | 2019-10-30 | 2019-11-29
GRT-YE00-P0ZEN-155040 | [Electrical General] General Electrical Symbol List | 2017-03-01 | 2017-03-31
GRT-XB02-P1H-300018 | [HRSG]_FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | 2017-03-23 | 2017-07-14
GRT-XH01-P0QC-130011 | [Chemical Dosing System]_PIPING ARRANGEMENT DRAWING | 2017-08-10 | 2017-11-22
GRTBCP-YD00-P0BBA-156006 | Data Sheet MV Switchgear 6,3 kV | 2017-10-31 | 2017-11-30
GRT-CC07-P0UBN-175569 | Calculation Sheet for EDG Foundation | 2017-09-04 | 2017-09-04
GRT-DN02-P0PAH-830015 | [Commissioning Procedure] CTCS / Debris filter | 2018-02-28 | 2018-04-30
GRT-YT01-P0LCB-121003 | [Condensate Extraction Pump]_DATA SHEET & CHARACTERISTIC CURVE | 2017-04-20 | 2017-07-20
GRT-XW03-P0PAC-155001 | [Circulating Water Pump] Lighting Illumination Level Calculation for Sea Water Intake | 2017-02-03 | 2017-03-05
GRT-CC09-P0UZA-175447 | [Structure for Transport, Trafic & Other Purpose] Calculation Sheet for Piperack Structure | 2017-07-30 | 2017-08-29
GRT-YK00-P0QC-130022 | [Chemical Dosing System]_HOOK UP DRAWING | 2017-09-09 | 2017-12-22
GRT-CC00-P0UGD-145308 | [WTP] Piping Layout Drawing Demin to HRSG Area | 2017-03-02 | 2017-04-01
GRT-XK00-P0LAB-144005 | Support DWG (Large Bore) - Feedwater | 2017-08-15 | 2017-11-30
GRT-XK00-P0ZEN-144511 | [Piping General]_Typical Installation Drawing for Pipe Support | 2017-06-15 | 2017-08-18
GRTBCP-YS01-P0BBA-156005 | Schematic Diagram MV Switchgear 6,3kV | 2018-02-05 | 2018-02-19
GRT-XG08-P0MA-200005 | [STG]_P&I Diagrams | 2017-03-10 | 2017-07-09
GRT-XB00-P0SCA-120013 | [Air Compressor]_FOUNDATION DRAWINGS | 2017-04-20 | 2017-07-19
GRT-YT01-P0BFB-156026 | Data Sheet LV Switchgear 2 | 2017-11-24 | 2017-12-24
GRT-YF02-P0QU-130027 | [Sampling System]_CONTROL CONFIGURATION DIAGRAM | 2017-07-20 | 2017-11-01
GRT-CA01-P0UMA-175259 | [STG BUILDING] Location Foundation Plant and Detail | 2017-06-05 | 2017-07-05
GRT-XJ00-P0MAA-140010 | Piping ISO (Large Bore) - ST Misc. | 2017-06-30 | 2018-01-31
GRT-YS01-POGDY-155949 | SCHEMATIC DIAGRAM FOR EC | 2018-10-10 | 2018-11-09
GRT-YM02-P0ZEN-156207 | 150kV Grati Switchgear Indoor Installation Control BLDG Equipment Layout | 2019-02-13 | 2019-03-15
GRT-YD00-P0BAC-156286 | GCB General Arrangement Drawing for FKG 1X | 2017-10-31 | 2017-11-30
GRT-YK00-P0ZEN-164301 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - General Notes | 2017-04-21 | 2017-08-31
GRT-CC04-P1UHA-175614 | Elevation HRSG Steel Structure Stairway Detail & Section | 2018-01-04 | 2018-01-04
GRT-XG02-P0UGD-115279 | [WTP] Piping and instrument diagram (PID) Raw Water System | 2017-02-23 | 2017-03-25
GRT-XB02-P0LDB-130044 | [Condensate Filter System]_FOUNDATION AND LOADING DATA | 2017-06-26 | 2017-10-08
GRT-YL19-P0ZEN-125022 | [Mechanical General] Power Consumption List | 2017-07-10 | 2017-08-09
GRT-QM01-P0ZEN-040001 | Shop Inspection and Test Plan for Manufacturing | 2017-03-10 | 2017-06-10
GRT-XG02-P0SC-120003 | [Compressed air system]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | 2017-02-06 | 2017-07-14
GRT-XW03-P0ZEN-155081 | [Electrical General] Electrical Load Data Calculation | 2017-02-23 | 2017-03-25
GRT-MA01-P0ZEN-165582 | SYSTEM CONFIGURATION OF CLOCK SYSTEM | 2019-02-13 | 2019-03-15
GRT-XW03-P0SG-115389 | [Fire Fighting System] Process Calculation for Fire Water Consumption | 2017-03-20 | 2017-04-19
GRT-YU01-P0BJP-156109 | Single Line Diagram Feeder PDB-03 | 2018-01-26 | 2018-02-25
GRT - YT01 - P0GCK - 126804 | Data Sheet Auxiliary Service Water Pump | 2018-02-02 | 2018-02-16
GRT-YK09-P0MA-200053 | [STG]_Summary Operation and Maintenance instructions | 2018-02-28 | 2018-05-22
GRT-YT01-P0AT-156110 | Rating Plate UAT | 2017-10-18 | 2017-11-17
GRTBCP-YS01-P0BJL-156090 | Schematic Diagram Feeder Normal Lighting | 2018-01-26 | 2018-02-25
GRT-YE00-P0ZEN-155045 | [Electrical General] Cable Tray, Trench and Power Wiring Layout for General Area | 2017-06-10 | 2017-07-10
GRT-YF01-P0MJ-156169 | Termination Diagram for EDG | 2018-02-05 | 2018-02-19
GRTBCP-YS01-P0BJM-156095 | Schematic Diagram Feeder HVAC | 2018-01-26 | 2018-02-25
GRT-YD00-P0ZEN-120005 | Bottom Plate Arrangement Section & Detail Make Up Demin Tank | 2017-11-09 | 2017-10-10
GRT-YD06-P0ZEN-161113 | [INC_Plant_Overall_Design]_DCS Power Distribution Concept Diagram | 2017-03-31 | 2017-06-30
GRT-CC07-P0ZEN-145029 | [Piping General] Piping Wall Thickness Calculation | 2017-02-10 | 2017-03-12
GRT-XW03-P0ZEN-155092 | [Electrical General] MOTOR STARTING ANALYSIS | 2017-04-01 | 2017-05-01
GRT-CC04-P1UHA-175612 | Elevation HRSG Steel Structure Column Arrangement & Member Schedule | 2018-01-04 | 2018-01-04
GRT-CC03-P0UZA-175423 | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Cross Section | 2017-07-14 | 2017-08-13
GRT-XG08-P0ZEN-115006 | [Process General] Utility Flow Diagram for Raw Water System | 2017-03-30 | 2017-04-29
GRT-XW01-P0ZEN-115011 | [Process General] BEDD | 2017-02-18 | 2017-03-20
GRTBCP-YS01-P0BJC-156050 | Schematic Diagram HRSG Unit MCC | 2018-01-26 | 2018-02-25
GRT-YS18-P0PAC-156398 | CIRCUIT AND WIRING DIAGRAM MCC & PLC FOR INTAKE SCREEN | 2019-02-13 | 2019-03-15
GRTBCP-YS01-P0BJJ-156080 | Schematic Diagram Feeder UPS-01 | 2018-01-26 | 2018-02-25
GRT-XW03-P0ZEN-156209 | 150KV Grati Switchgear Outdoor Installation Switchyard Layout | 2018-02-05 | 2018-02-19
GRT-YD16-P0UGX-155193 | [Chlorination System] Cable Tray and Power Wiring Layout | 2017-03-11 | 2017-04-10
GRT-CC00-P0ZEN-145026 | [Piping General] Detail Crossing Road & Electrical Underground | 2017-02-24 | 2017-03-26
GRT-YT001-P0ZEN-145628 | Data Sheet for Butterfly MOV Valve | 2017-10-16 | 2017-10-16
GRT-XS00-P0MAJ-460109 | Vacuum Pump System Description & Control Philosophy | 2017-07-21 | 2017-09-08
GRT-YR02-P0ZEN-155061 | [Electrical General] Specification for Busduct | 2017-03-11 | 2017-04-10
GRT-YL00-P0MAJ-460207 | Instrument list For Water Box Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-YS01-P0BYA-165656 | GTCS-Schematic Diagram of DAS | 2017-12-05 | 2017-12-19
GRT-YU01-P0BJA-156044 | Single Line Diagram STG PDB | 2018-01-26 | 2018-02-25
GRT-YD00-P0BJE-156058 | General Arrangement Valve PDB | 2017-11-24 | 2017-12-24
GRT-YT10-P0PGB-430130 | Strength Calculation for CCW Expansion Head Tank | 2017-10-20 | 2017-12-22
GRT-YT02-P0LD-165827 | DATA SHEET PRESSURE SWITCH | 2017-10-18 | 2017-11-17
GRT-YK08-P0PAH-440057 | CCW HEX Tube Cleaning System_Outline Drawing for Control Panel | 2017-06-01 | 2017-10-31
GRT-YT01-P0BJN-156096 | Data Sheet Feeder HVAC | 2017-11-24 | 2017-12-24
GRT-XW03-P0PAC-155147 | [Circulating Water Pump] Electrical Load Data Calculation for Sea Water Intake | 2017-02-03 | 2017-03-05
GRT-XW03-P0ZEN-156222 | 150 KV Switchgear Cable List Diameter X | 2018-02-05 | 2018-02-19
GRT-YK10-P1H-300050 | [HRSG]_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | 2017-09-20 | 2017-12-20
GRT-YK10-P0PGB-113103 | [CCWP ]_Pump Sectional Drawing | 2017-06-12 | 2017-09-10
GRT-FF04-P0SGM-125445 | Technical Data Sheet FM200 | 2017-11-28 | 2017-12-28
GRT-XK00-P0MAJ-460117 | Coupling Drawing For Condenser Vacuum Pump | 2017-07-21 | 2017-09-08
GRT-YU01-P0BFD-156034 | Single Line Diagram LV Switchgear 4 | 2018-01-26 | 2018-02-25
GRT-YD00-P0PAC-125139 | [Circulating Water Pump] GA Drawing Stop Log Screen | 2017-07-15 | 2017-08-14
GRT-YT01-P0UGD-115288 | [WTP] Process data sheet for raw water pump | 2017-02-21 | 2017-03-23
GRT-CV03-P0UGD-165316 | [WTP] Instrument Data Sheet for Demin Make up System | 2017-03-03 | 2017-04-02
GRT-YT02-P0GD-165924 | Data sheet Clorination Analyzer | 2017-07-21 | 2017-08-20
GRT-YT01-P0QU-130031 | [Sampling System]_INSTRUMENT DATA SHEET | 2017-08-19 | 2017-12-01
GRT-YK00-P0ZEN-164309 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Control Valve | 2017-04-21 | 2017-08-31
GRT-CC00-P0UGX-145192 | [Chlorination System] Piping Layout Drawing for Chlorination | 2017-07-15 | 2017-08-14
GRT-XW03-P0UGD-115295 | [WTP] Process calculation for raw water tank | 2017-06-10 | 2017-07-10
GRT-XB00-P0MA-200002 | [STG]_Foundation - Embedded Elements | 2017-02-28 | 2017-07-14
GRT-CC03-P0PAC-175168 | [Circulating Water Pump] Circulating Water Pump Detail 3 | 2017-02-14 | 2017-03-16
GRT-YR02-P0BCA-165702 | MOV OUTLINE DRAWING | 2019-02-13 | 2019-03-15
GRT-CC04-P1UHA-175616 | HRSG Concrete Layout | 2017-12-06 | 2017-12-06
GRT-DC01-P0GDN-125913 | Data Sheet Sea Water Booster Pump | 2017-09-14 | 2017-10-14
GRT-CC00-P0ZEN-145023 | [Piping General] Plot Plan for BOP | 2017-02-04 | 2017-03-06
GRT-DN02-P1ZEN-830021 | [Commissioning Procedure] Load Change Test | 2018-04-30 | 2018-06-30
GRT-CA01-P0UGD-175399 | [Fire Fighting Shelter] Foundation, Foundation Plan & Detail | 2017-07-14 | 2017-08-13
GRT-YD00-P0ZEN-165110 | [Instrument General] Instrument Panel Base Frame & Hole Opening | 2017-07-19 | 2017-08-18
GRT-YR02-P0ZEN-155059 | [Electrical General] Specification for Induction Motor | 2017-03-02 | 2017-04-01
GRT-YD00-P0PGB-113107 | [CCWP ]_MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | 2017-08-12 | 2017-11-10
GRT-CA01-P0UGX-175210 | [Chlorination System] Steel Structure Framing Plan | 2017-06-23 | 2017-07-23
GRT-XN00-P0MA-200011 | [STG]_List of valves | 2017-05-21 | 2017-08-08
GRT-YT10-P0PGB-400060 | Strength Calculation for CCW Heat Exchanger | 2017-10-16 | 2017-12-22
GRT-YL01-P0ZEN-165463 | DCS IO List for LDC Interface | 2017-10-20 | 2017-08-20
GRT-YT02-P0LD-165824 | DATA SHEET PH TRANSMITTER | 2017-10-18 | 2017-11-17
GRT-CC03-P0UAG-175364 | [Transformer] Section Detail | 2017-06-20 | 2017-07-20
GRT-CC07-P0PAD-175178(1OF3) | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Plan | 2017-02-11 | 2017-03-13
GRT-XA00-P0QU-130025 | [Sampling System]_GENERAL ARRANGEMENT DRAWING | 2017-06-20 | 2017-10-02
GRT-YK00-P0SCA-120025 | [Air Compressor]_INSTRUMENTATION HOOK - UP DRAWING | 2017-05-20 | 2017-09-17
GRT-DC01-P0LDN-125818 | DATA SHEET ACID DOSING PUMP FOR NEUTRALIZING SYSTEM | 2017-10-13 | 2017-11-12
GRT-YR01-P0ZEN-110103 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE | 2018-02-26 | 2018-05-27
GRT-FF01-P0SGC-125440 | Water Spray Layout for Transformer | 2017-11-28 | 2017-12-28
GRT-YK00-P0LDB-130057 | [Condensate Filter System]_HOOK UP DRAWING | 2017-08-24 | 2017-12-07
GRT-CV03-P0ZEN-163701 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Process Transmitter - BOP | 2017-07-31 | 2017-10-31
GRT-DE00-P0ZEN-144501 | [Piping General]_Piping Insulation Specification (BOP) | 2017-04-07 | 2017-07-07
GRT-YK09-P0MA-200028 | [STG]_Measuring and Synchronization | 2017-11-11 | 2018-03-10
GRT-YK00-P0ZEN-164308 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Gauge | 2017-04-21 | 2017-08-31
GRT-DN02-P0ZEN-820001 | [Commissioning Program]_Steam Blowing-Out Emergency Response Plan | 2019-12-03 | 2020-03-20
GRT-XW03-P0ZEN-156240 | Switchgear Steel Structures CB Support IB562 ( GL314 – TYPE F1 ) | 2017-11-16 | 2017-12-16
GRT-YF00-P0ZEN-165577 | Instrument Control Loop for Waste water Transfer System | 2017-10-24 | 2017-10-24
GRT-CC05-P0ZEN-145028 | [Piping General] Support Standard Drawing | 2017-03-18 | 2017-04-17
GRT-YD00-P0BAC-156285 | GCB General Arrangement Drawing for FKG 1X | 2017-10-31 | 2017-11-30
GRT-YD00-P0PGB-430020 | Outline Drawing for CCW Chemical Additive Tank | 2017-03-08 | 2017-08-05
GRT-XW03-P0QJA-111001 | [N2 Gas System_Design]_sizing Calculation | 2017-04-07 | 2017-07-14
GRT-QA00-P0H-040014 | Heat Treatment Procedure for HRSG Piping | 2017-08-29 | 2017-11-29
GRT-YD00-P0BJA-156043 | General Arrangement STG PDB | 2017-11-24 | 2017-12-24
GRT-CC08-P0GCK-135834 | EQUIPMENT LAYOUT | 2017-10-18 | 2017-11-17
GRT-YT01-P1H-300060 | [HRSG]_CV DATASHEET & DRAWINGS | 2017-07-20 | 2017-10-20
GRT-CV03-P0ZEN-163702 | [Field Instruments(DHI)]_Technical Specification & Datasheet for Local Instrument - BOP | 2017-07-31 | 2017-10-31
GRT-YT01-P0QC-130012 | [Chemical Dosing System]_TECHNICAL DATASHEET | 2017-08-10 | 2017-11-22
GRT-CC03-P0PAC-175165 | [Circulating Water Pump] Circulating Water Pump Section, Slab Schedule and Wall Schedule | 2017-02-14 | 2017-03-16
GRT-YF02-P0LDB-130041 | [Condensate Filter System]_CONTROL CONFIGURATION DIAGRAM | 2017-06-26 | 2017-10-08
GRT-HM01-P0UGX-125189 | [Chlorination System] Chlorination Plant Building HVAC Elevation, Equipment Layout | 2017-03-11 | 2017-04-10
GRT-YS02-P0ZEN-165568 | Instrument Termination Dagaram for Waste Water Transfer System | 2017-09-20 | 2017-09-20
GRT-YT01-P0UGD-125303 | [WTP] Mech. Data Sheet for Raw Water Tank | 2017-06-12 | 2017-07-12
GRT-YF00-P0PA-161207 | [Aux. Cooling Water System_I&C_Logic]_Control Logic Diagram for BOP | 2017-04-21 | 2017-07-31
GRT-YD00-P0ZEN-165104 | [Instrument General] Telephone Location Plan Layout | 2017-08-08 | 2017-06-20
GRT-DF04-P0ZEN-144513 | [Piping General]_Stress Analysis Report for LP steam system | 2017-06-23 | 2017-09-15
GRT-YD00-P0GAD-125624 | General Arrangement Circulating Water Pump | 2017-11-20 | 2017-11-20
GRT-YU01-P0BJL-156089 | Single Line Diagram Feeder Normal Lighting | 2018-01-26 | 2018-02-25
GRT-UE00-P1H-300009 | [HRSG]_ARRANGEMENT OF MAIN STACK& FIELD ERECTION | 2017-05-20 | 2017-08-20
GRT-CA01-P0PAC-175182 | Architectural Waste Disposal Building Plan, Elevation & Section, Finishing Schedule | 2020-10-15 | 2020-11-14
GRT-CC03-P1UHA-175221 | [HRSG] Foundation Detail (1/2) | 2017-03-25 | 2017-04-24
GRT-XJ00-P0QFB-143012 | Piping ISO (Small Bore) - Instrument air | 2017-07-28 | 2018-01-31
GRT-CC07-P0ZEN-175582 | Calculation Sheet for Sump Pit | 2017-10-23 | 2017-10-23
GRT-XS00-P0QU-130026 | [Sampling System]_SYSTEM DESCRIPTION | 2017-06-20 | 2017-10-02
GRT-YL22-P0LAC-122007 | [HP Feed Water Pump]_NAME PLATE DRAWING | 2017-06-20 | 2017-09-20
GRT-YK00-P0ZEN-165116 | [Instrument General] Instrument Typical Drawing for Installation | 2017-06-14 | 2017-07-14
GRT-YD00-P0MA-200006 | [STG]_General Arrangement Drawing | 2017-03-10 | 2017-09-25
GRT-XW03-P0ZEN-155085 | [Electrical General] Emergency Diesel Capacity Calculation | 2017-03-15 | 2017-04-14
GRT-XM00-P0AT-156134 | Heaviest Part for Transformer Drawing Plate 150/15.75 kV – 250 MVA Power Transformer | 2017-10-06 | 2017-11-05
GRT-XN00-P0MAJ-460119 | Valve and Specialty List For Condenser Vacuum Pump | 2017-07-21 | 2017-09-08
GRT-XW03-P0PAC-115135 | [Circulating Water Pump] Process calculation for sea water for closed cooling system booster pump | 2017-02-07 | 2017-03-09
GRT-YT01-P1UHA-115457 | [WTP] Process data sheet for blowdown transfer pump | 2017-08-18 | 2017-08-18
GRT-CV03-P0ZEN-165678 | Data Sheet for Demin Make up Sysytem | 2017-11-17 | 2017-12-17
GRT-YT01-P0QU-130030 | [Sampling System]_TECHNICAL DATASHEET | 2017-08-19 | 2017-12-01
GRT-XG02-P0LA-110006 | [Feedwater system]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-CC03-P0PAC-175170 | [Circulating Water Pump] Circulating Water Pump Pipe Header Pedestal Detail | 2017-02-14 | 2017-03-16
GRT-VL00-P0MAG-410005 | Condenser_Foundation Assembly | 2017-02-10 | 2017-05-10
GRT-XG02-P0PAC-115132 | Piping & Instrumentation Diagram for Circulating Sea Water Cooling System | 2019-02-13 | 2019-03-15
GRT-YS02-P0ZEN-165581 | [Instrument General] INSTRUMENT TERMINATION DIAGRAM FOR ALL AREA | 2019-02-13 | 2019-03-15
GRT-XW03-P0PCC-113010 | [Aux. Cooling Water Pump_Design]_SIZING CALCULATION FOR AUXILIARY COOLING WATER PUMP | 2017-04-14 | 2017-09-03
GRT-XW03-P0PCH-156393 | TECHNICAL INFORMATION ACWP IMPRESS CURRENT CATHODIC PROTECTION | 2019-10-30 | 2019-11-29
GRT-YD00-P0UGD-165322 | [WTP] Instrument Location Plan Layout for Service Water System | 2017-03-16 | 2017-04-15
GRT-DB00-P0MAJ-460118 | Performance Curves For Condenser Vacuum Pump | 2017-06-30 | 2017-09-08
GRT-CA07-P0ZEN-179031 | U-Ditch Precast Cable Trench Stability | 2018-04-02 | 2018-05-02
GRT-CC07-P0PAC-175174 | [Circulating Water Pump] Calculation Sheet for Cooling Water Intake Basin | 2017-02-14 | 2017-03-16
GRT-XJ00-P0LAB-140005 | Piping ISO (Large Bore) - Feedwater | 2017-06-16 | 2017-08-31
GRT-QA00-P0H-040013 | NDE Procedure for HRSG Piping | 2017-08-29 | 2017-11-29
GRT-CV03-P0ZEN-161111 | [DCS]_Functional Design Specification for Software | 2017-03-31 | 2017-06-30
GRT-DN02-P0SCA-830007 | [Commissioning Procedure] Compressed Air System | 2018-02-28 | 2018-04-30
GRT-YK00-P0ZEN-164304 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Pressure Transmitter / Switch | 2017-04-21 | 2017-08-31
GRT-YD00-P0UGD-120035 | Roof Structure Assembling Section & Detail | 2017-03-11 | 2017-03-11
GRT-YT01-P0LAC-122503 | [LP Feed Water Pump]_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | 2017-04-20 | 2017-07-20
GRT-CA03-P0UMA-175264 | [STG BUILDING] Steam Turbine Building Steel Structure Runway Girder El +28.604 (T.O.R) | 2017-03-07 | 2017-04-06
GRT-UC07-P0ZEN-100001 | PLOT PLAN | 2017-02-10 | 2017-06-06
GRT-CC00-P0ZEN-145027 | [Piping General] Piping Layout Drawing for Sea Water System | 2017-02-04 | 2017-03-06
GRTBCP-YD00-P0BBA-156004 | Single Line Diagram MV Switchgear 6,3 kV | 2017-10-31 | 2017-11-30
GRT-CA01-P0UMA-175251 | [STG BUILDING] Condenser Foundation Detail | 2017-03-07 | 2017-04-06
GRT-YU01-P0BJC-156049 | Single Line Diagram HRSG Unit MCC | 2018-01-26 | 2018-02-25
GRT-XK00-P0MAJ-460116 | Name Plate Drawing For Condenser Vacuum Pump | 2017-08-11 | 2017-09-08
GRT-CA01-P0UMA-175257 (3 OF 3) | Steam Turbine Building Deaerator Local Platform Foundation Detail | 2019-01-07 | 2019-02-06
GRT-YR02-P0ZEN-155056 | [Electrical General] Specification for Low Voltage Switchgear and MCC | 2017-03-07 | 2017-04-06
GRT-YE07-P0UGD-155395 | [Fire Fighting Shelter] Lightning Protection Layout | 2017-07-14 | 2017-08-13
GRT-YT01-P0QC-130014 | [Chemical Dosing System]_PUMP DATA SHEET | 2017-08-10 | 2017-11-22
GRT-CC03-P0UZA-175425 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan and Detail (1/8) | 2017-07-20 | 2017-03-30
GRT-XW03-P0ZEN-155082 | [Electrical General] Voltage Drop and Power Flow Study | 2017-03-14 | 2017-04-13
GRT-YT01-P0MAG-410007 | Condenser_Data Sheet | 2017-02-10 | 2017-05-10
GRT-YF00-P0ZEN-165573 | Instrument Control Loop for Demin Make up System | 2017-12-12 | 2017-12-12
GRT-YD00-P1H-300035 | [HRSG]_SPEC. & DRAWING FOR STEAM DRUM | 2017-08-20 | 2017-10-20
GRT-XG02-P0UGD-115281 | [WTP] Piping and instrument diagram (PID) Water Treatment System | 2017-02-21 | 2017-03-23
GRT-CC00-P0PAC-145146 | [Circulating Water Pump] Detail & Section Drawing for Sea Water Intake System | 2017-02-03 | 2017-03-05
GRT-DP00-P0ZEN-141004 | Repair welding procedure for BOP Piping | 2017-09-15 | 2017-12-15
GRT-UC08-P0ZEN-100002 | General Arrangement of Power Block | 2017-03-17 | 2018-10-01
GRT-CC04-P0ZEN-156242 | Common Switchgear Steel Structure Disconnector Support - IB572 (S2DAT) | 2018-02-05 | 2018-02-19
GRT-VN03-P1H-300013 | [HRSG]_ARRANGEMENT FOR PLATFORM STRUCTURE | 2017-05-20 | 2017-08-20
GRT-YD00-P0BJF-156063 | General Arrangement BOP Essential MCC | 2017-11-24 | 2017-12-24
GRT-XK00-P0LBA-144002 | Support DWG (Large Bore) - LP Steam | 2017-08-15 | 2017-11-30
GRT-YD16-P0UGD-155393 | [Fire Fighting Shelter] Cable Tray and Power Wiring Layout | 2017-07-14 | 2017-08-13
GRT-CC03-P0UGD-175466 | Raw Water Tank Concrete Structure Foundation Plan, Detail & Schedule | 2017-09-28 | 2017-09-28
GRT-YK00-P0ZEN-164302 | [INC_IID(DHI)]_BOP_Instrument Installation Detail Drawing - Symbol & Legend | 2017-04-21 | 2017-08-31
GRT-CA01-P0UGX-175211 | [Chlorination System] Steel Structure Framing Elevation and Detail | 2017-06-23 | 2017-07-23
GRT-YF00-P0ZEN-161301 | [INC_Other_Sys_Logic&Loop]_Control Loop Diagram - Symbol & Legend | 2017-04-14 | 2017-07-31
GRT-CC03-P0PAC-175170(2OF7) | [Circulating Water Pump] Circulating Water Pump Gantry Crane and Traveling Screen Detail | 2017-02-14 | 2017-03-16
GRT-MA01-P0AY-156172 | IO List Communication to DCS | 2018-02-05 | 2018-02-19
GRT-YF00-P0SCA-120021 | [Air Compressor]_CONTROL LOGIC & LOOP DIAGRAM | 2017-05-20 | 2017-09-17
GRT-XW03-P0UGD-115296 | [WTP] Process calculation for make-up demin water tank | 2017-02-23 | 2017-03-25
GRT-YD00-P0AT-156128 | General Arrangement Drawing 150/15.75 kV – 250 MVA | 2017-10-06 | 2017-11-05
GRT-CC03-P0PAD-175181 | Outfall Stop Log (include calculation) | 2019-03-10 | 2019-04-09
GRT-YD00-P0PCC-113005 | [Aux. Cooling Water Pump]_OUTLINE DRAWING FOR AUXILIARY COOLING WATER PUMP MOTOR | 2017-06-05 | 2017-09-03
GRT-YR05-P0ZEN-161136 | [DCS]_Outline & Detail Drawing for Safety Related System Panel | 2017-04-07 | 2017-07-07
GRT-CA01-P0PAC-175609 | Intake Electrical Building Foundation, Floor, & Roof Plant, Section, Detail Grade Beam, Slab, & Column Schedule | 2017-10-23 | 2017-10-23
GRT-XH01-P1H-300023 | [HRSG]_PIPE SUPPORT DRAWINGS | 2017-08-20 | 2017-12-20
GRT-XW01-P0SCA-120012 | [Air Compressor]_AIR FILTER SPECIFICATION | 2017-04-20 | 2017-07-19
GRT-CC08-P0GAC-135930 | Equipment Lay out | 2017-09-14 | 2017-10-14
GRT-YS02-P0BYA-165643 | DCS Lan Configuration | 2017-10-31 | 2017-11-30
GRT-YT01-P0AT-156135 | Tecnical Specification (TPG) 150/15.75 kV – 250 MVA Power Transformer | 2017-10-06 | 2017-11-05
GRT-YD00-P0ZEN-120017 | Roof Manhole Section & Detail Make up Demin Tank | 2017-11-09 | 2017-10-10
GRT-YT01-P0UGD-115285 | [WTP] Process data sheet for Portable Water Pump | 2017-02-23 | 2017-03-25
GRT-CC01-P0AT-156131 | Oil Piping & Valve Location Plate 150/15.75 kV – 250 MVA Power Transformer | 2017-10-06 | 2017-11-05