## Sheet1
Document No | Title | FA | FC
GRT-XG05-P0ZEN-110002 | [Symbol & Legend]_P&I DIAGRAM | 2017-02-10 | 2017-06-10
GRT-YT02-P0LD-165826 | DATA SHEET LEVEL SWITCH WTP MIXED BED | 2017-10-18 | 2017-11-17
GRT-YR02-P0ZEN-155071 | [Electrical General] Datasheet for Busduct | 2017-03-11 | 2017-04-10
GRT-YD00-P0UGD-120032 | General Arrangement Drawing | 2017-03-11 | 2017-03-11
GRT-XW03-P0PGB-113110 | [CCWP_Design]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | 2017-04-14 | 2017-07-14
GRT-HM01-P0UGD-125454 | [WTP] WTP Building HVAC Ducting Layout | 2019-02-13 | 2019-03-15
GRT - YT01 - P0GCK - 126806 | Data Sheet HRSG Sump Pit Pump | 2018-02-02 | 2018-02-16
GRT-YE07-P0PAC-156415 | [Intake Electrical Building] Lightning Protection Layout | 2019-09-19 | 2019-10-19
GRT-YD00-P0AT-156107 | General Arrangement Drawing of Unit Auxiliary Transformer 25MVA | 2017-10-18 | 2017-11-17
GRT-CA07-P0ZEN-179029 | Study Thermal Barrier and Sedimentation | 2017-06-05 | 2017-07-05
GRT - YL16 - P0LD - 155944 | Cable Schedule Electrical for EC | 2018-02-02 | 2018-02-16
GRT-YS01-P0ZEN-156359 | 150KV GRT DC DISTRIBUTION BOARD | 2019-02-13 | 2019-03-15
GRT-XJ00-P0PGB-140008 | Piping ISO (Large Bore) - CCW | 2017-06-23 | 2018-01-31
GRT-YQ01-P0UAA-155370 | [Switchyard] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-06-19 | 2017-07-19
GRT-DN02-P0PG-830004 | [Commissioning Procedure] Closed Cooling Water system | 2018-01-30 | 2018-03-30
GRT-YK09-P0MA-200025 | [STG]_Excitation system | 2017-11-11 | 2018-03-10
GRT-YD00-P0MA-200022 | [STG]_Steam Turbine Auxiliaries outline drawing | 2017-11-03 | 2018-02-02
GRT-YD00-P0ZEN-165103 | [Instrument General] CCTV Cable Wiring Layout | 2017-10-05 | 2017-07-30
GRT-CV03-P0ZEN-165675 | Data Sheet for Service Water System | 2017-11-17 | 2017-12-17
GRT-YK00-P0MA-200040 | [STG]_I&C Lay-outs | 2017-05-22 | 2017-09-21
GRT-DE00-P1H-300067 | [HRSG]_PIPING MATERIAL CLASSIFICATION | 2017-06-20 | 2017-09-20
GRT-YR02-P0ZEN-155073 | [Electrical General] Datasheet for Cable Tray & Accessories | 2017-03-11 | 2017-04-10
GRT-YU03-P0MA-200039 | [STG]_Control system architecture | 2017-03-28 | 2017-07-21
GRT-YS01-P0ZEN-165125 | [Instrument General] Telephone System Block Diagram | 2017-04-25 | 2017-05-25
GRT-YL00-P0MA-200037 | [STG]_Measurement list | 2017-05-14 | 2017-09-13
GRT-YD00-P0BVC-156357 | General Arrangement UPS System | 2017-11-14 | 2017-12-14
GRT-YK10-P0LDB-130045 | [Condensate Filter System]_EQUIPMENT ASSEMBLY DRAWING | 2017-06-26 | 2017-10-08
GRT-YR02-P0ZEN-155060 | [Electrical General] Specification for UPS, Battery & Battery Charger | 2017-03-11 | 2017-04-10
GRT-YD00-P0GD-155839 | PANEL ARRANGEMENT (LAYOUT DRAWING) | 2019-02-13 | 2019-03-15
GRT-YE00-P1UHA-155213 | [HRSG] Cable Tray and Power Wiring Layout | 2017-06-15 | 2017-07-15
GRT-YE06-P1UHA-155215 | [HRSG] Grounding Wiring Layout | 2017-06-06 | 2017-06-20
GRT-YR02-P0ZEN-156250 | 150KV Grati Switchgear Surge Arrester Technical Particular & Guarantee | 2017-10-05 | 2017-10-05
GRT-CV03-P0PAC-165155 | [Circulating Water Pump] Instrument Data Sheet for Circulating Water Pump | 2017-03-11 | 2017-04-10
GRT-DN02-P0MAJ-830014 | [Commissioning Procedure] Water box vacuum | 2018-02-28 | 2018-04-30
GRT-YD00-P1H-300039 | [HRSG]_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | 2017-07-20 | 2017-10-20
GRT-CC03-P0PAC-175170(5OF7) | [Circulating Water Pump] Circulating Water Pump CWP Pedestal Detail | 2017-02-14 | 2017-03-16
GRT-XK00-P0LBG-144003 | Support DWG (Large Bore) - Aux. Steam | 2017-12-31 | 2018-01-30
GRT-YT02-P0GD-165921 | Data sheet Pressure Indicator | 2017-07-21 | 2017-08-20
GRT-DC01-P0GDN-125918 | Data Sheet Continuos Dosing Pump | 2017-09-14 | 2017-10-14
GRT-YS02-P0PAC-165709 | Instrument Interconnection Diagram for TCS System | 2020-08-29 | 2020-09-28
GRT-YS02-P0UGD-165343 | [WTP] Instrument Termination Diagram for Water Treatment System | 2017-07-07 | 2017-08-06
GRT-XG08-P0ZEN-115005 | [Process General] Utility Flow Diagram for Sea Water Intake & Circulating Sea Water Cooling System | 2017-04-01 | 2017-05-01
GRT-YL10-P0MAJ-460221 | Spare Part List For Water Box Vacuum Pump | 2017-07-14 | 2017-09-08
GRT-YD00-P1UHA-165219 | [HRSG] Instrument Main Cable & JB Layout | 2017-06-15 | 2017-07-15
GRT-YT01-P0PAH-440008 | Condenser Tube Cleaning System_Technical Data Sheet | 2017-04-01 | 2017-10-31
GRT-XG02-P0UGD-115280 | [WTP] Piping and instrument diagram (PID) Demin Make-up System | 2017-02-23 | 2017-03-25
GRT-CT00-P0QJA-111011 | [N2 GAS SYSTEM]_OPERATION & MAINTENANCE MANUAL | 2018-04-20 | 2018-05-31
GRT-CV03-P0ZEN-165099 | [Instrument General] Data Sheet for Paging System | 2017-07-19 | 2017-08-18
GRT-CA03-P0UMA-175260 | [STG BUILDING] Steam Turbine Building Steel Structure Column Layout Plan | 2017-03-07 | 2017-04-06
GRT-XW03-P0ZEN-156351 | 150KV SWITCHGEAR CABLE TRAY AND WIRING LAYOUT | 2019-02-19 | 2019-03-21
GRT-YS01-P0AT-156133 | Schematic Diagram of Remote Control Panel 150/15.75 kV – 250 MVA Power Transformer | 2017-10-06 | 2017-11-05
GRT-YF00-P0ZEN-165569 | Instrument Control Logic for Circulating Sea Water Cooling System | 2017-11-20 | 2017-11-20
GRT-YL10-P0MAJ-460121 | Spare Part List For Condenser Vacuum Pump | 2017-07-14 | 2017-09-08
GRT-XW03-P0ZEN-156193 | 150kV Grati Switchgear 110V DC Single Line Diagram | 2018-02-05 | 2018-02-19
GRT-YR02-P0ZEN-155066 | [Electrical General] Datasheet for Medium Voltage Switchgear and MCC | 2017-03-07 | 2017-04-06
GRT-YL25-P0LD-165852 | MODBUST LIST | 2017-10-18 | 2017-11-17
GRT-CC03-P0UGD-175468 | Make up Demin Water Tank Concrete Structure Foundation Plant, Detail & Schedule | 2017-09-05 | 2017-09-05
GRT-XW01-P0QJA-110206 | [N2 Gas system]_Design Criteria | 2017-02-22 | 2017-07-14
GRT-YD05-P0GD-165937 | HMI GRAPHICS ELECTROCLORINATION | 2019-02-13 | 2019-03-15
GRT-XG08-P0SG-115383 | [Fire Fighting System] Utility Flow Diagram Fire water system | 2017-03-20 | 2017-04-19
GRT-YS02-P0UGD-165341 | [WTP] Instrument Termination Diagram for Potable Water System | 2017-07-07 | 2017-08-06
GRT-XW03-P0UGD-115299 | [WTP] Process calculation for raw water pump | 2017-02-21 | 2017-03-23
GRT-XW03-P0ZEN-156182 | 150KV GRATI GENERAL ARRANGEMENT MARSHALLING KIOSK | 2018-10-09 | 2018-11-08
GRT-YU01-P0ZEN-155076 | [Electrical General] Overall Single Line Diagram for 150 kv | 2017-02-19 | 2017-03-21
GRT-YT01-P0MAJ-460215 | Recirculation Pump Data Sheet and Characteristic Curves and Drawing For WBVP | 2017-07-07 | 2017-09-08
GRT-CC03-P0UZA-175426 | [Structure for Transport, Trafic & Other Purpose] Local Foundation and Pipe Sleeper Foundation Plan | 2017-07-20 | 2017-03-30
GRT-XJ00-P0LBA-143002 | Piping ISO (Small Bore) - LP Steam | 2017-07-07 | 2018-01-31
GRT-XW03-P0ZEN-155088 | [Electrical General] Lighting Illumination Level Calculation | 2017-06-14 | 2017-07-14
GRT-CC09-P0UZA-175449(3OF5) | PIPERACK STEEL STRUCTURE FRAMING PLAN EL. + 14.604 (T.O.S) | 2017-07-30 | 2017-08-29
GRT-YQ07-P0ZEN-165120 | [Instrument General] General Specification for Telephone System | 2017-04-17 | 2017-05-17
GRT-XB02-P0BAA-156313 | Layout Foundation Detail of 15. 75kV IPBD | 2017-11-24 | 2017-12-24
GRT-YE06-P1UHA-155216 | [HRSG] Lightning Protection Layout | 2017-06-15 | 2017-07-15
GRT-XW01-P0PA-110204 | [Aux. Cooling Water System]_DESIGN CRITERIA | 2017-02-22 | 2017-07-14
GRT-YK08-P0ZEN-111200 | [Safety Relief Valve(DHI)]_OUTLINE DRAWING FOR SAFEY AND RELIEF VALVE | 2017-09-26 | 2017-12-25
GRT-VS02-P0BTL-156365 | Battery Rack 800AH for DC System | 2017-11-24 | 2017-12-24
GRT-YK08-P0LBG-111300 | [Silencer]_OUTLINE DRAWING FOR SILENCER | 2017-10-24 | 2018-01-22
GRT-CC07-P0PAD-175178(3OF3) | [Circulating Water Pump Outfall] Circulating Water Pump Outfall Section and Detail | 2017-02-11 | 2017-03-13
GRT-YD00-P0ZEN-120004 | Shell Plate Arrangement Section & Detail Make up Demin Tank | 2017-11-09 | 2017-10-10
GRT-CA00-P0UGD-175345 | [WTP] Water Treatment Plant Architectural Plan, View, Section & Finishing Schedule | 2017-03-15 | 2017-04-14
GRT-CC00-P0UGD-145307 | [WTP] Piping Layout Drawing Demin Water Area | 2017-06-23 | 2017-07-23
GRT-XG02-P0UGD-115469-1 | P & ID For Waste Water Transfer System ( 1 of 2 ) | 2017-06-12 | 2017-07-12
GRT-YU03-P0MA-200041 | [STG]_Control system function philosophy | 2017-05-22 | 2017-09-21
GRT-FF03-P0SGM-125442 | Fire Suppression/FM/200 Layout | 2017-11-28 | 2017-12-28
GRT-YL00-P0MAJ-460127 | Instrument Data sheet For Condenser Vacuum Pump | 2017-07-14 | 2017-09-08
GRT-XG07-P0GAC-135936 | PFD | 2017-07-21 | 2017-08-20
GRT-YT01-P0SG-125391 | [Fire Fighting System] Mech. Data Sheet for Jockey Pump | 2017-03-27 | 2017-04-26
GRT-XB02-P1H-300016 | [HRSG]_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | 2017-03-30 | 2017-06-30
GRT-CQ02-P0QC-130023 | [Chemical Dosing System]_O&M MANUAL | 2018-01-17 | 2018-05-01
GRT-YU01-P0BFA-156019 | Single Line Diagram LV Switchgear 1 | 2018-01-26 | 2018-02-25
GRT-YL00-P0MA-200045 | [STG]_List of signals | 2017-03-22 | 2017-07-22
GRT-QA00-P0H-040015 | Welders List for HRSG Piping | 2017-08-29 | 2017-11-29
GRT-YQ01-P0UGX-155197 | [Chlorination System] Lighting and Receptacle Panel Schedule and Connection Diagram | 2017-03-11 | 2017-04-10
GRT-YF00-P0ZEN-161210 | [INC_Other_Sys_Logic&Loop]_Control Logic Diagram for Sampling & Chemical Dosing System | 2017-04-28 | 2017-07-31
GRT-CC04-P0ZEN-156241 | Common Switchgear Steel Structure 3 Pole Disconnector Support - IB571 (S2DA) | 2018-02-05 | 2018-02-19
GRT-CC04-P0ZEN-156239 | Common Switchgear Steel Structure C.T. SUPPORT - H = 4M - IB560 | 2018-02-05 | 2018-02-19
GRT-YD00-P0BFA-156379 | General Arrangement NSPB-B | 2017-11-14 | 2017-12-14
GRT-CA01-P0UGD-175564 | Water Treatment Plant Concrete Structure Section and Detail | 2017-09-04 | 2017-09-04
GRT-YD00-P0BJD-156053 | General Arrangement LV Switchgear 3 | 2017-11-24 | 2017-12-24
GRT-CQ02-P0LAC-122022 | [HP Feed Water Pump]_Operational & Maintenance Manual | 2018-04-20 | 2018-05-31
GRT-XS00-P0LA-110402 | [Feedwater system]_SYSTEM DESCRIPTION | 2017-02-28 | 2017-07-14
GRT-XW03-P0PCH-156394 | TECHNICAL INFORMATION HEAT EXCHANGER IMPRESS CURRENT CATHODIC PROTECTION | 2019-10-30 | 2019-11-29
GRT-XW01-P0ZEN-115013 | [Process General] Process Simulation Report | 2017-03-30 | 2017-04-29
GRT-YU01-P0BJF-156064 | Single Line Diagram BOP Essensial MCC | 2018-01-26 | 2018-02-25
GRT-DN06-P0ZEN-145458 | [Piping General] Piping Pressure Test Procedure | 2017-06-05 | 2017-07-05
GRT-YR02-P0ZEN-156252 | 150KV Grati Switchgear Current Transfoemer Tecnical Particular & Guarantee | 2017-10-05 | 2017-10-05
GRT-CA00-P0PAC-175607 | Calculation Sheet for Intake Electrical Building | 2017-10-23 | 2017-10-23
GRT-XV00-P0MA-200010 | [STG]_List of pipelines | 2017-05-21 | 2017-08-08
GRT-YT01-P0BJP-156315 | Data Sheet HRSG PDB-3 | 2017-11-24 | 2017-12-24
GRT-YT01-P0ZEN-113301 | [MOV (Gate & Globe)(DHI)]_VALVE LIST & DATA SHEET FOR MOV (G&G) | 2017-08-15 | 2017-11-13
GRT-YD05-P0ZEN-161123 | [DCS]_HMI Graphic Drawing | 2017-09-15 | 2017-11-03
GRT-PL03-P0MAJ-460120 | Terminal Point List For Condenser Vacuum Pump | 2017-07-07 | 2017-09-08
GRT-YD00-P0ZEN-165106 | [Instrument General] Paging Location Plan Layout | 2017-06-23 | 2017-07-23
GRT-DF04-P0ZEN-144515 | [Piping General]_Stress Analysis Report for Feedwater system | 2017-06-23 | 2017-09-15
GRT-YR01-P1H-300054 | [HRSG]_CHEMICAL CLEANING PROCEDURE | 2017-09-20 | 2017-12-20
GRT-YT01-P0BJH-156076 | Data Sheet BOP Essensial PDB | 2017-11-24 | 2017-12-24
GRT-YD00-P0UGD-165325 | [WTP] Instrument Cable Wiring Layout for Potable Water System | 2017-03-29 | 2017-04-28
GRT-XS00-P0PA-110404 | [Aux. Cooling Water System]_SYSTEM DESCRIPTION | 2017-02-28 | 2017-07-14
GRT-DC01-P0LDF-125815 | DATA SHEET MIXED BED FEED PUMP | 2017-10-18 | 2017-11-17
GRTBCP-YS01-P0BFD-156035 | Schematic Diagram LV Switch Gear 4 | 2018-01-26 | 2018-02-25
GRT-YE07-POPAC-156416 | [INTAKE BUIILDING] Lighting Layout & Panel Schedule | 2019-08-06 | 2019-09-05
GRT-YD00-P0AT-156306 | General Arrangement Drawing of 3000 KVA | 2017-10-09 | 2017-11-08
GRT-YT01-P0UZA-156405 | CALCULATION CATHODIC PROTECTION FOR THERMAL BARRIER | 2019-01-15 | 2019-02-14
GRT-YF00-P1H-300044 | [HRSG]_SEQUENCES & CONTROLS | 2017-06-20 | 2017-09-20
GRT-CC03-P0PAC-175170(3OF7) | [Circulating Water Pump] Circulating Water Pump Bar Screen and Mechanical Rake/Car Detail | 2017-02-14 | 2017-03-16
GRT-YS00-P0ZEN-163301 | [INC_Typical Elementary]_Typical Elementary Wiring Diagram - Index | 2017-03-03 | 2017-05-31
GRT-YT10-P0ZEN-144502 | [Piping General]_Pipe Thickness Calculation (BOP) | 2017-03-17 | 2017-06-16
GRT-CC03-P0UZA-175424(1OF2) | [Structure for Transport, Trafic & Other Purpose] Thermal Barrier Pile Cap, Plan, Long Section and Detail | 2017-02-28 | 2017-03-30
GRT-DM02-P1H-300005 | [HRSG]_GENERAL NOTE FOR STEEL STRUCTURE | 2017-05-20 | 2017-08-20
GRT-XG02-P0LBG-110004 | [AUX Steam System]_P&I DIAGRAM | 2017-02-22 | 2017-07-14
GRT-YR02-P0ZEN-155051 | [Electrical General] General Specification for Electrical | 2017-03-01 | 2017-03-31
GRT-XW03-P0ZEN-155084 | [Electrical General] Protective Relay Coordination Study for MV & LV Switcgear | 2017-06-14 | 2017-07-14
GRT-YR02-P0ZEN-156251 | 150KV Grati Switchgear Circuit Breaker Technical Particular & Guarantee | 2017-10-05 | 2017-10-05
GRT-YT01-P0MAJ-460105 | Motor Data sheet and Characteristic Curves and Drawing For CVP | 2017-07-07 | 2017-09-08
GRT-YL01-P0SCA-120019 | [Air Compressor]_PLC HARDWIRED IO LIST | 2017-05-20 | 2017-09-17
GRT-CV03-P0ZEN-161112 | [DCS]_Functional Design Specification for Graphic | 2017-04-07 | 2017-07-07
GRT-YF00-P0PG-161308 | [Closed cooling water system_I&C_Loop]_Control Loop Diagram for BOP | 2017-04-21 | 2017-07-31
GRT-XJ00-P0LCW-143014 | Piping ISO (Small Bore) - Seal Water | 2017-07-21 | 2018-01-31
GRT-YL00-P0QU-130028 | [Sampling System]_INSTRUMENT LIST | 2017-07-20 | 2017-11-01
GRT-CV03-P0ZEN-145030 | [Piping General] Piping Design Specification | 2017-03-04 | 2017-04-03
GRT-YT02-P0GD-165923 | Data Sheet Level Transmitter | 2017-07-21 | 2017-08-20
GRT-YR05-P0BYA-165647 | DCS Outline Drawing of DAS | 2017-11-17 | 2017-12-19
GRT-YS02-P0UGD-165342 | [WTP] Instrument Termination Diagram for Raw Water System | 2017-07-07 | 2017-08-06
GRT-XW03-P0ZEN-155089 | [Electrical General] Grounding System Calculation | 2017-03-01 | 2017-03-31
GRT-CC07-P0UZEN-175475 | Calculation Sheet for Liquefaction potential Check | 2017-09-28 | 2017-09-28
GRT-XS01-P0LB-111105 | [Bypass Valve & PRDS]_Operating Description for HPU system for Bypass System | 2017-07-28 | 2017-10-26