## Sheet1
WBS Level | Trimmed ID | Activity Name | Start | Finish | WBS_Level
Activity | 0SF0500W00A01 | LOI | 2016-12-08
Activity | 0SF0500W00A02 | NTP | 2016-12-27
Activity | 1SF0500W00A03 | Start of HRSG #21 Erection works | 2017-12-16
Activity | 1SF0500W00A04 | STG #20 On foundation | 2018-05-01
Activity | 1SF0500W00A05 | HRSG #21 MCC |  | 2018-08-14
Activity | 2SF0500W00A06 | HRSG #22 MCC |  | 2018-08-24
Activity | 3SF0500W00A07 | HRSG #23 MCC |  | 2018-09-08
Activity | 1SF0500W00A08 | Steam Blowing | 2018-10-14
Activity | 1SF0500W00A09 | STG #20 TOD |  | 2019-02-26
Activity | 0SF0500W00A11 | Power Receiving from Owner |  | 2018-04-30
Activity | 0SF0500W00A10 | Desalinated Water Available from Owner |  | 2018-05-14
Activity | 0SF0500W00A12 | Aux Steam Available from Owner |  | 2018-08-09
Activity | 0EF1000W00A07 | Mechanical Design Criteria | 2016-12-22 | 2017-05-02
Activity | 0EF1000W00A03 | P&ID | 2016-12-08 | 2017-06-16
Activity | 0EF1000W00A01 | Heat Balance Diagram | 2016-12-08 | 2017-04-10
Activity | 0EF1000W00A05 | Operational Philosophy of Overall Plant | 2016-12-08 | 2017-08-03
Activity | 0EF1000W00A02 | Plant Plot Plan | 2016-12-08 | 2017-06-06
Activity | 0EF1000W00A14 | Aux Power Consumption Data | 2016-12-08 | 2017-02-15
Activity | 0EF1000W00A08 | Plant General Arrangement | 2017-01-06 | 2017-09-07
Activity | 0EF1000W00A04 | Single Line Diagram | 2016-12-08 | 2017-07-21
Activity | 0EF1000W00A06 | DCS I/O List of Overall Plant | 2016-12-08 | 2017-08-10
Activity | 0EF1000W00A10 | Instrument Installation Detail | 2017-02-17 | 2017-10-09
Activity | 0EF1000W00A09 | Control Room Layout | 2017-01-06 | 2017-08-23
Activity | 0EF1000W00A12 | O&M Manual Key Data (BOP) | 2016-12-27 | 2017-12-22
Activity | 0EF1000W00A11 | O&M Manual Key Data (Power Block) | 2016-12-27 | 2017-12-22
Activity | 0EF1000W00A13 | O&M Manual First Issue |  | 2018-03-23
Activity | 0EF6010W10A06 | Soil Investigation Plan Data | 2016-12-08 | 2016-12-22
Activity | 0EF6010W10A01 | Soil Investigation Plan | 2016-12-23 | 2017-01-10
Activity | 0EF6010W10A02 | Request Site Access to Owner | 2016-12-27 | 2016-12-30
Activity | 0CF6010W10A02 | Soil Investigation Work | 2017-01-11 | 2017-02-09
Activity | 0EF6010W10A03 | Site Access Approval | 2016-12-31 | 2017-01-03
Activity | 0EF6010W10A05 | Government Declaration | 2017-01-05 | 2017-01-09
Activity | 0EF6010W10A04 | Site Preparation Layout | 2016-12-27 | 2017-03-24
Activity | 0CF6010W28A03 | Land Scape | 2016-12-27 | 2017-04-25
Activity | 0CF6010W10A05 | Site Preparation Civil Work | 2017-01-26 | 2017-07-26
Activity | 0EF6010W14A010 | Load Data for STG BLDG | 2016-12-08 | 2017-02-28
Activity | 0EF6010W14A011 | Load Data for HRSG | 2016-12-08 | 2017-03-15
Activity | 0EF6010W12A06 | Soil Improvement Design | 2017-01-11 | 2017-03-30
Activity | 0EF6010W14A07 | STG Area Pile Design | 2017-02-09 | 2017-03-20
Activity | 0EF6010W14A08 | HRSG Area Pile Design | 2017-02-10 | 2017-03-21
Activity | 0EF6010W14A09 | BOP Area Pile Design | 2017-02-10 | 2017-03-21
Activity | 0CF6010W12A13 | Excavation(STG Area) | 2017-03-21 | 2017-04-12
Activity | 0CF6010W12A11 | Excavation(HRSG Area) | 2017-03-22 | 2017-04-13
Activity | 0CF6010W12A10 | Excavation(BOP Area) | 2017-03-22 | 2017-04-13
Activity | 0CF6010W12A12 | Soil Improvement Work | 2017-03-31 | 2017-05-02
Activity | 0CF6010W14A19 | STG Area Piling Work | 2017-04-13 | 2017-05-23
Activity | 0CF6010W14A15 | Intake Area Piling Work | 2017-04-14 | 2017-05-24
Activity | 0CF6010W14A16 | Outtake Area Piling Work | 2017-04-14 | 2017-05-24
Activity | 0CF6010W14A17 | Switchyard Area Piling Work | 2017-04-14 | 2017-05-24
Activity | 0CF6010W14A18 | HRSG Area Piling Work | 2017-04-14 | 2017-05-29
Activity | 0CF6010W14A14 | Tank Area Piling Work | 2017-04-14 | 2017-05-24
Activity | 0EF3025W00A19 | (Intake Screening System) P&ID & System Design | 2017-01-16 | 2017-08-30
Activity | 0EF3025W42A20B | (Intake Screening Equipment) MPS Issue |  | 2017-03-03
Activity | 0PF3025W42A21P | (Intake Screening Equipment) P.O & Procurement | 2017-04-04 | 2018-01-08
Activity | 0PF3025W42A22T | (Intake Screening Equipment) Transportation | 2018-01-09 | 2018-02-22
Activity | 0CF3025W42A23 | (Intake System) Equipment Installation(Stop gate, screening sys.) | 2018-02-23 | 2018-05-28
Activity | 0CF3025W58A24 | (Intake System) Piping Work | 2018-03-16 | 2018-05-30
Activity | 0CF3025W74A25 | (Intake System) Installation & Test - Elec. | 2018-03-16 | 2018-06-11
Activity | 0CF3025W90A26 | (Intake System) Installation & Test - I&C | 2018-03-16 | 2018-06-11
Activity | 0SF3025W62A27 | (Intake System) Loop chek | 2018-06-12 | 2018-06-16
Activity | 0SF3025W62A28 | (Intake System) Motor Solo Test | 2018-06-17 | 2018-06-21
Activity | 0EF3025W00A29 | (Intake Pump Station) GA & Load Data to Civil Design | 2017-02-02
Activity | 0EF3025W16A30C | (Intake Pump Station) FDN Design | 2017-02-02 | 2017-03-30
Activity | 0EF3025W12A31 | (Intake Pump Station) Excavation | 2017-03-31 | 2017-06-09
Activity | 0EF3025W16A32C | (Intake Pump Station) Structure Design | 2017-05-25 | 2017-08-22
Activity | 0CF3025W16A33 | (Intake Pump Station) FDN Work | 2017-06-10 | 2017-07-28
Activity | 0CF3025W16A34 | (Intake Pump Station) Structure Work(Wall & Top Slab) | 2017-08-23 | 2017-12-05
Activity | 0CF3025W12A35 | (Intake Pump Station) Backfilling | 2017-12-06 | 2018-02-05
Activity | 0EF3025W42A36B | (Gantry Crane) MPS Issue |  | 2017-03-24
Activity | 0PF3025W42A37P | (Gantry Crane) P.O & Procurement | 2017-04-25 | 2017-11-21
Activity | 0PF3025W42A38T | (Gantry Crane) Transportation | 2017-11-22 | 2018-01-11
Activity | 0CF3025W42A39 | (Gantry Crane) Equipment Installation | 2018-01-12 | 2018-02-03
Activity | 0EF3025W00A52 | (CWP) CW Flow Rate | 2016-12-27 | 2017-01-13
Activity | 0EF3025W00A01 | (CWS) P&ID & System Design | 2016-12-08 | 2017-07-24
Activity | 0EF3025W00A02 | (CWS) CWP Key data | 2017-01-23 | 2017-02-22
Activity | 0EF3025W42A03B | (CWP) MPS Issue |  | 2017-04-25
Activity | 0PF3025W42A04P | (CWP) P.O & Procurement | 2017-05-25 | 2018-02-08
Activity | 0PF3025W42A05T | (CWP) Transportation | 2018-02-09 | 2018-03-26
Activity | 0CF3025W42A06 | (CWP) Installation | 2018-03-27 | 2018-05-21
Activity | 0CF3025W38A07 | (CWS) Installation & Test - Fire Fighting Sys. | 2018-04-02 | 2018-05-24
Activity | 0CF3025W74A08 | (CWS) Installation & Test - Elec. | 2018-04-30 | 2018-06-29
Activity | 0CF3025W90A09 | (CWS) Installation & Test - I&C | 2018-04-30 | 2018-06-29
Activity | 0SF3025W62A10 | (CWS) Loop chek | 2018-06-30 | 2018-07-06
Activity | 0SF3025W62A11 | (CWS) Motor Solo Test & Function Test | 2018-07-07 | 2018-07-24
Activity | 0SF3025W62A12 | (CWS) CTCS Function Test | 2018-07-25 | 2018-07-29
Activity | 0SF3025W62A13 | (CWS) Pump Operation | 2018-07-30 | 2018-08-03
Activity | 0EF3025W22A14B | (CW Piping) MPS Issue |  | 2017-02-27
Activity | 0PF3025W22A15P | (CW Piping) P.O & Procurement | 2017-03-27 | 2017-10-13
Activity | 0PF3025W22A16T | (CW Piping) Transportation | 2017-10-14 | 2017-11-21
Activity | 0CF3025W22A17 | (CW Piping) Piping Work | 2017-11-22 | 2018-05-31
Activity | 0CF3025W62A18 | (CW Piping) Hydro Test | 2018-06-01 | 2018-06-29
Activity | 0EF3045W00A01 | (Chlorination System) P&ID & System Design | 2017-01-06 | 2017-08-22
Activity | 0EF3045W42A02B | (Chlorination Plant) MPS Issue |  | 2017-04-28
Activity | 0PF3045W42A03P | (Chlorination Plant) P.O & Procurement | 2017-05-29 | 2018-02-01
Activity | 0EF3045W16A04C | (Chlorination Plant) FDN Design | 2017-05-29 | 2017-08-28
Activity | 0CF3045W16A05 | (Chlorination Plant) FDN Work | 2017-08-29 | 2017-11-29
Activity | 0PF3045W42A06T | (Chlorination Plant) Transportation | 2018-02-02 | 2018-03-13
Activity | 0CF3045W42A07 | (Chlorination Plant) Installation | 2018-03-14 | 2018-05-30
Activity | 0CF3045W74A08 | (Chlorination System) Installation & Test - Elec. | 2018-03-14 | 2018-06-08
Activity | 0CF3045W90A09 | (Chlorination System) Installation & Test - I&C | 2018-03-14 | 2018-06-08
Activity | 0SF3045W62A10 | (Chlorination System) Loop check | 2018-06-25 | 2018-07-11
Activity | 0SF3045W62A11 | (Chlorination System) System Function Test | 2018-07-12 | 2018-07-16
Activity | 0SF3045W62A12 | (Chlorination System) System Operation | 2018-07-17 | 2018-07-21
Activity | 0EF3045W58A13B | (Chlorination System Piping) MPS Issue |  | 2017-05-05
Activity | 0PF3045W58A14P | (Chlorination System Piping) Raw Material Procurement | 2017-06-06 | 2017-08-03
Activity | 0PF3045W58A15P | (Chlorination System Piping) Manufacturing | 2017-08-04 | 2017-12-19
Activity | 0PF3045W58A16T | (Chlorination System Piping) Transportation | 2017-12-20 | 2018-01-25
Activity | 0CF3045W58A17 | (Chlorination System Piping) Piping Work | 2018-03-14 | 2018-06-08
Activity | 0CF3045W62A18 | (Chlorination System Piping) Hydro Test | 2018-06-09 | 2018-06-23
Activity | 0EF3045W00A19 | (Chlorination BLDG) GA & Load Data to Civil Design | 2017-05-29
Activity | 0EF3045W32A20C | (Chlorination BLDG) Structure Design | 2017-05-29 | 2017-08-28
Activity | 0CF3045W16A21 | (Chlorination BLDG) FDN Work | 2017-08-29 | 2017-11-29
Activity | 0CF3045W32A22 | (Chlorination BLDG) Structure Work | 2017-11-30 | 2018-03-31
Activity | 0CF3045W38A26 | (Chlorination BLDG) Installation & Test - Fire Fighting Sys. | 2018-04-02 | 2018-05-29
Activity | 0CF3045W36A23 | (Chlorination BLDG) Installation & Test - HVAC | 2018-04-02 | 2018-05-29
Activity | 0CF3045W74A24 | (Chlorination BLDG) Installation & Test - Elec | 2018-04-02 | 2018-05-29
Activity | 0CF3045W90A25 | (Chlorination BLDG) Installation & Test - I&C | 2018-04-02 | 2018-05-29
Activity | 0EF3010W00A01 | (WTS) P&ID & System Design | 2016-12-08 | 2017-08-16
Activity | 0EF3010W42A02B | (WTS) MPS Issue |  | 2017-02-21
Activity | 0EF3010W16A03C | (WTS) FDN Design | 2017-03-08 | 2017-07-17
Activity | 0PF3010W42A04P | (WTS) P.O & Procurement | 2017-03-21 | 2017-10-03
Activity | 0CF3010W16A05 | (WTS) FDN Work | 2017-07-18 | 2017-10-12
Activity | 0PF3010W42A06T | (WTS) Transportation | 2017-10-04 | 2017-11-02
Activity | 0CF3010W42A07 | (WTS) Installation | 2017-11-03 | 2018-03-15
Activity | 0CF3010W90A09 | (WTS) Installation & Test - I&C | 2018-01-17 | 2018-03-19
Activity | 0CF3010W58A10 | (WTS) Piping Work | 2018-01-17 | 2018-03-19
Activity | 0CF3010W74A08 | (WTS) Installation & Test - Elec. | 2018-01-17 | 2018-03-19
Activity | 0SF3010W62A11 | (WTS) Loop chek | 2018-03-27 | 2018-04-12
Activity | 0SF3010W62A12 | (WTS) Function Test | 2018-05-25 | 2018-06-21
Activity | 0SF3010W62A13 | (WTS) Load Test(incl. Tank filling) | 2018-06-22 | 2018-07-04
Activity | 0SF3010W62A14 | (WTS) System Operation | 2018-07-05 | 2018-07-09
Activity | 0EF5534W00A01 | (WTP BLDG) GA & Load Data to Civil Design | 2016-12-23
Activity | 0EF5534W16A02C | (WTP BLDG) FDN Design | 2016-12-23 | 2017-04-13
Activity | 0EF5534W32A03C | (WTP BLDG) Structure Design | 2017-01-24 | 2017-05-15
Activity | 0CF5534W16A04 | (WTP BLDG) FDN Work | 2017-05-25 | 2017-08-19
Activity | 0CF5534W32A05 | (WTP BLDG) Station Structure Work | 2017-08-21 | 2017-10-31
Activity | 0CF5534W74A06 | (WTP BLDG) Installation & Test - Elec | 2017-09-21 | 2017-12-06
Activity | 0CF5534W90A07 | (WTP BLDG) Installation & Test - I&C | 2017-09-21 | 2017-12-06
Activity | 0CF5534W24A08 | (WTP BLDG) Building Finish | 2017-12-23 | 2018-03-26
Activity | 0CF5534W36A09 | (WTP BLDG) Installation & Test - HVAC | 2018-01-09 | 2018-03-26
Activity | 0CF5534W38A10 | (WTP BLDG) Installation & Test - Fire Fighting Sys. | 2018-01-15 | 2018-03-13
Activity | 0EF3010W16A15 | (DW Tank) FDN Design | 2017-02-07 | 2017-06-12
Activity | 0EF3010W16A18 | (DW Tank) GA & Load Data to Civil Design | 2017-02-07
Activity | 0EF3010W68A16B | (DW Tank) MPS Issue |  | 2017-02-24
Activity | 0PF3010W68A17P | (DW Tank) P.O & Procurement | 2017-03-24 | 2017-10-16
Activity | 0CF3010W16A19 | (DW Tank) FDN Work | 2017-06-13 | 2017-08-23
Activity | 0PF3010W68A20T | (DW Tank) Transportation | 2017-10-17 | 2017-11-24
Activity | 0CF3010W68A21 | (DW Tank) Installation(incl. Painting & Test) | 2017-11-25 | 2018-05-14
Activity | 0SF3010W62A22 | (DW Tank) Water Filling | 2018-05-15 | 2018-05-24
Activity | 0EF3010W16A26 | (DM Tank) GA & Load Data to Civil Design | 2017-02-07
Activity | 0EF3010W16A23 | (DM Tank) FDN Design | 2017-02-07 | 2017-06-12
Activity | 0EF3010W68A24B | (DM Tank) MPS Issue |  | 2017-02-24
Activity | 0PF3010W68A25P | (DM Tank) P.O & Procurement | 2017-03-24 | 2017-11-07
Activity | 0CF3010W16A27 | (DM Tank) FDN Work | 2017-06-13 | 2017-08-23
Activity | 0PF3010W68A28T | (DM Tank) Transportation | 2017-11-08 | 2017-12-15
Activity | 0CF3010W68A29 | (DM Tank) Installation(incl. Painting & Test) | 2017-12-16 | 2018-05-30
Activity | 0SF3010W62A30 | (DM Tank) Water Filling | 2018-06-25 | 2018-07-04
Activity | 0EF3010W00A52 | (MWSS) Demi WTR Consumption Data | 2016-12-08 | 2017-01-31
Activity | 0EF3010W00A53 | (MWSS) Demi WTR Design Condition of TP | 2016-12-08 | 2017-01-31
Activity | 0EF3010W00A32 | (MWSS) P&ID & System Design | 2016-12-22 | 2017-08-30
Activity | 0EF3010W00A31 | (MWSS) Demi WTR Supply pump Key Data | 2016-12-08 | 2017-02-07
Activity | 0CF3010W58A33 | (MWSS) Piping Work | 2018-03-29 | 2018-05-09
Activity | 0CF3010W58A36 | (MWSS) Piping Work BL#2(upto pump Discharge header) | 2018-03-29 | 2018-04-13
Activity | 0CF3010W74A34 | (MWSS) Installation & Test - Elec. | 2018-03-29 | 2018-05-09
Activity | 0CF3010W90A35 | (MWSS) Installation & Test - I&C | 2018-03-29 | 2018-05-09
Activity | 0EF3010W42A37B | (Make-up WTR Pump) MPS Issue |  | 2017-04-11
Activity | 0PF3010W42A38P | (Make-up WTR Pump) P.O & Procurement | 2017-05-11 | 2018-01-10
Activity | 0EF3010W16A39C | (Make-up WTR Pump) FDN Design | 2017-05-11 | 2017-09-19
Activity | 0CF3010W16A40 | (Make-up WTR Pump) FDN Work | 2017-09-20 | 2017-11-04
Activity | 0PF3010W42A41T | (Make-up WTR Pump) Transportation | 2018-01-11 | 2018-02-24
Activity | 0CF3010W42A42 | (Make-up WTR Pump) Installation | 2018-02-26 | 2018-03-28
Activity | 0SF3010W62A43 | (Make-up WTR Pump) Loop check | 2018-05-10 | 2018-05-15
Activity | 0SF3010W62A44 | (Make-up WTR Pump) Motor Solo run Test & Function Test | 2018-05-16 | 2018-05-25
Activity | 0SF3010W62A45 | (Make-up WTR Pump) Operation Test | 2018-07-05 | 2018-07-08
Activity | 0EF3035W00A33 | (SWS) Service Water Required Flow Rate | 2016-12-27 | 2017-01-30
Activity | 0EF3035W00A01 | (SWS) P&ID & System Design | 2016-12-22 | 2017-08-30
Activity | 0EF3035W00A02 | (SWS) Service Water Supply pump Key data | 2017-01-31 | 2017-02-24
Activity | 0EF3035W42A03B | (SWS) MPS Issue |  | 2017-02-24
Activity | 0PF3035W42A04P | (SWS) P.O & Procurement | 2017-05-19 | 2018-01-18
Activity | 0EF3035W16A05C | (SWS) FDN Design | 2017-07-20 | 2017-11-21
Activity | 0CF3035W16A06 | (SWS) FDN Work | 2017-11-22 | 2018-02-22
Activity | 0PF3035W42A07T | (SWS) Transportation | 2018-01-19 | 2018-03-05
Activity | 0CF3035W42A08 | (SWP) Installation (upto pump Discharge header) | 2018-03-06 | 2018-05-05
Activity | 0CF3035W74A09 | (SWS) Installation & Test - Elec. | 2018-04-26 | 2018-05-28
Activity | 0CF3035W90A10 | (SWS) Installation & Test - I&C | 2018-04-26 | 2018-05-28
Activity | 0SF3035W62A11 | (SWS) Loop chek | 2018-05-29 | 2018-06-05
Activity | 0SF3035W62A12 | (SWP) Motor Solo run Test & Function Test | 2018-06-06 | 2018-06-12
Activity | 0SF3035W62A13 | (SWS) Load Test | 2018-06-13 | 2018-06-15
Activity | 0EF3035W00A18 | (PWS) P&ID & System Design | 2017-01-24 | 2017-09-07
Activity | 0EF3035W00A19 | (PWS) Potable Water Supply System Key data | 2017-02-03 | 2017-03-09
Activity | 0EF3035W42A20B | (PWP) MPS Issue |  | 2017-04-05
Activity | 0PF3035W42A21P | (PWP) P.O & Procurement | 2017-07-07 | 2018-05-07
Activity | 0EF3035W16A22C | (PWP) FDN Design | 2017-10-09 | 2018-01-08
Activity | 0CF3035W16A23 | (PWP) FDN Work | 2018-01-09 | 2018-03-10
Activity | 0PF3035W42A24T | (PWP) Transportation | 2018-05-08 | 2018-06-21
Activity | 0CF3035W42A25 | (PWP) Installation (upto pump Discharge header) | 2018-06-22 | 2018-07-23
Activity | 0CF3035W74A26 | (PWS) Installation & Test - Elec. | 2018-07-21 | 2018-08-18
Activity | 0CF3035W90A27 | (PWS) Installation & Test - I&C | 2018-07-21 | 2018-08-18
Activity | 0SF3035W62A28 | (PWS) Loop chek | 2018-08-20 | 2018-08-30
Activity | 0SF3035W62A29 | (PWS) System Function Test | 2018-08-31 | 2018-09-04
Activity | 0SF3035W62A30 | (PWS) Load Test | 2018-09-08 | 2018-09-12
Activity | 0EF5000W00A01 | (HVAC System) P&ID & System Design | 2017-01-24 | 2017-08-28
Activity | 0EF5000W36A02B | (HVAC Equipment) MPS Issue |  | 2017-03-24
Activity | 0PF5000W36A03P | (HVAC Equipment) P.O & Procurement | 2017-04-26 | 2017-11-22
Activity | 0PF5000W36A04T | (HVAC Equipment) Transportation | 2017-11-23 | 2018-03-26
Activity | 0PF5000W36A05T | (HVAC Equipment) 1st Delivery on site_Transportation |  | 2018-01-08
Activity | 0EF4500W00A01 | (Fire Fighting System) P&ID & System Design | 2017-01-24 | 2017-08-28
Activity | 0EF4500W38A02B | (Fire Fighting System) MPS Issue |  | 2017-03-24
Activity | 0PF4500W38A03P | (Fire Fighting System) P.O & Procurement_piping | 2017-04-26 | 2017-09-25
Activity | 0PF4500W38A04T | (Fire Fighting System) Transportation | 2017-09-26 | 2017-11-09
Activity | 0CF4500W38A05 | (Fire Fighting System) Piping Work(Ring Main) | 2017-11-10 | 2018-02-10
Activity | 0CF4500W62A06 | (Fire Fighting System) Hydro Test | 2018-06-18 | 2018-07-03
Activity | 0EF4500W38A07B | (Fire Fighting Equip) MPS Issue |  | 2017-03-13
Activity | 0PF4500W38A08P | (Fire Fighting Equip) P.O & Procurement | 2017-04-13 | 2017-11-29
Activity | 0PF4500W38A09T | (Fire Fighting Equip) Transportation | 2017-11-30 | 2018-06-14
Activity | 0PF4500W38A10T | (Fire Fighting Equip) 1st Delivery on site_Transportation |  | 2018-01-13
Activity | 0PF4500W38A11T | (Fire Fighting Equip) 2nd Delivery on site_Transportation |  | 2018-03-31
Activity | 0PF4500W38A12T | (Fire Fighting Equip) 3rd Delivery on site_Transportation |  | 2018-06-14
Activity | 0EF4500W00A13 | (Fire WTR Pump Shelter) GA & Load Data to Civil Design | 2017-03-14
Activity | 0EF4500W32A14C | (Fire WTR Pump Shelter) Structure Design | 2017-03-14 | 2017-07-10
Activity | 0CF4500W32A15 | (Fire WTR Pump Shelter) Structure Work | 2017-09-11 | 2018-01-10
Activity | 0CF4500W38A16 | (Fire WTR Pump Shelter) Installation & Test - Fire Fighting Sys. | 2018-01-15 | 2018-03-01
Activity | 0CF4500W36A17 | (Fire WTR Pump Shelter) Installation & Test - HVAC | 2018-01-15 | 2018-03-01
Activity | 0CF4500W24A18 | (Fire WTR Pump Shelter) Building Finish | 2018-01-15 | 2018-03-13
Activity | 0EF4500W16A19C | (Fire WTR Pump) FDN Design | 2017-04-13 | 2017-07-13
Activity | 0CF4500W16A20 | (Fire WTR Pump) FDN Work | 2017-07-14 | 2017-09-09
Activity | 0CF4500W38A21 | (Fire WTR Pump) Installation F/F pump | 2018-01-15 | 2018-03-13
Activity | 0CF4500W74A22 | (Fire WTR Pump) Installation & Test - Elec | 2018-02-09 | 2018-03-13
Activity | 0CF4500W90A23 | (Fire WTR Pump) Installation & Test - I&C | 2018-02-09 | 2018-03-13
Activity | 0SF4500W62A24 | (Fire WTR Pump) Loop chek | 2018-03-14 | 2018-03-15
Activity | 0SF4500W62A25 | (Fire WTR Pump) System Function Test | 2018-05-01 | 2018-05-02
Activity | 0SF4500W62A26 | (Fire WTR Pump) Load(running) Test | 2018-06-16 | 2018-06-17
Activity | 0EF6020W00A01 | (BOP Piping) Pipe Material Specification | 2017-01-03 | 2017-11-30
Activity | 0EF6020W00A04 | (BOP Piping) Piping Insulation Specification | 2017-02-02 | 2017-11-30
Activity | 0EF6020W00A02 | (BOP Piping) Pipe Arrangement | 2017-02-06 | 2018-07-10
Activity | 0EF6020W00A03 | (BOP Piping) Valve List | 2017-02-06 | 2017-10-12
Activity | 0EF6020W00A05 | (BOP Piping) Piping Isometric Drawing | 2017-02-24 | 2017-11-09
Activity | 0EF6020W58A08B | (Piping) MPS Issue |  | 2017-05-08
Activity | 0EF6020W46A06B | (Hanger & Support & Fitting) MPS Issue |  | 2017-05-08
Activity | 0EF6020W52A07B | (Piping Insulation) MPS Issue |  | 2017-05-08
Activity | 0PF6020W58A10P | (Piping) P.O & Procurement | 2017-06-22 | 2018-03-20
Activity | 0PF6020W46A09P | (Hanger & Support & Fitting) P.O & Procurement | 2017-06-23 | 2017-12-08
Activity | 0PF6020W52A11P | (Piping Insulation) P.O & Procurement | 2017-07-10 | 2018-02-07
Activity | 0PF6020W58A12T | (Piping) Transportation | 2017-10-24 | 2018-04-24
Activity | 0PF6020W58A14T | (Piping) 1st Delivery on site_Transportation |  | 2017-12-08
Activity | 0PF6020W46A13T | (Hanger & Support & Fitting) Transportation | 2017-12-09 | 2018-01-23
Activity | 0PF6020W52A15T | (Piping Insulation) Transportation | 2018-02-08 | 2018-03-24
Activity | 0PF6020W58A16T | (Piping) 2nd Delivery on site_Transportation |  | 2018-02-20
Activity | 0PF6020W58A17T | (Piping) 3rd Delivery on site_Transportation |  | 2018-04-24
Activity | 0EF6050W86A01B | (Manual Valve) MPS Issue |  | 2017-05-08
Activity | 0PF6050W86A02P | (Manual Valve) P.O & Procurement | 2017-07-03 | 2017-12-08
Activity | 0PF6050W86A03T | (Manual Valve) Transportation | 2017-12-09 | 2018-01-23
Activity | 0EF6050W00A04 | (MOV) MOV Key Data | 2017-01-24 | 2017-03-21
Activity | 0EF6050W86A05B | (MOV) MPS Issue |  | 2017-03-24
Activity | 0PF6050W86A06P | (MOV) P.O & Procurement | 2017-05-22 | 2017-12-01
Activity | 0PF6050W86A07T | (MOV) Transportation | 2017-12-02 | 2018-01-16
Activity | 0EF6050W00A08 | (Safety Valve) Key Data | 2017-01-24 | 2017-04-10
Activity | 0EF6050W86A09B | (Safety Valve) MPS Issue |  | 2017-04-10
Activity | 0PF6050W86A10P | (Safety Valve) P.O & Procurement | 2017-06-12 | 2018-01-30
Activity | 0PF6050W86A11T | (Safety Valve) Transportation | 2018-01-31 | 2018-03-16
Activity | 0EF7000W86A08B | (Control Valve) MPS Issue |  | 2017-04-06
Activity | 0PF7000W86A09P | (Control Valve) P.O & Procurement | 2017-07-10 | 2018-05-01
Activity | 0PF7000W86A10T | (Control Valve) 1st Delivery(On site) |  | 2018-02-22
Activity | 0PF7000W86A11T | (Control Valve) Transportation | 2018-05-02 | 2018-06-15
Activity | 0CF3010W58A46 | (MWSS) Piping Work(DMTK->TBN BLDG) | 2018-03-29 | 2018-05-29
Activity | 0CF3010W62A47 | (MWSS) Hydro Test | 2018-05-30 | 2018-06-06
Activity | 0CF3010W58A49 | (WTS) Piping Work(DWTK->WTP) | 2018-01-17 | 2018-03-19
Activity | 0CF3010W58A50 | (WTS) Piping Work(WTP->DMTK) | 2018-01-17 | 2018-03-19
Activity | 0CF3010W58A48 | (WTS) Piping Work(DWP->DWTK) | 2018-01-17 | 2018-03-19
Activity | 0CF3010W62A51 | (WTS) Hydro Test | 2018-03-20 | 2018-03-27
Activity | 0CF3035W58A14 | (SWS) Piping Work(DWTK->SWP) | 2018-03-06 | 2018-05-05
Activity | 0CF3035W58A15 | (SWS) Piping Work(SWP->WTP) | 2018-03-06 | 2018-05-05
Activity | 0CF3035W58A16 | (SWS) Piping Work(SWP->Chl. BLDG) | 2018-03-06 | 2018-05-05
Activity | 0CF3035W62A17 | (SWS) Hydro Test | 2018-05-07 | 2018-05-22
Activity | 0CF3035W58A31 | (PWS) Piping Work(Block #2) | 2018-06-22 | 2018-08-22
Activity | 0CF3035W62A32 | (PWS) Hydro Test | 2018-08-23 | 2018-09-07
Activity | 0CF4035W58A05 | (WWTS) Waste Water Flow Rate | 2016-12-27 | 2017-02-08
Activity | 0CF4035W58A01 | (WWTS) Piping Work(Chl. BLDG->WWTP) | 2018-02-02 | 2018-04-04
Activity | 0CF4035W58A02 | (WWTS) Piping Work(WTP->WWTP) | 2018-02-02 | 2018-04-04
Activity | 0CF4035W58A03 | (WWTS) Piping Work(HRSG->WWTP) | 2018-02-02 | 2018-04-04
Activity | 0CF4035W62A04 | (WWTS) Hydro Test | 2018-04-05 | 2018-04-20
Activity | 0CF3510W58A19 | (COMP) Piping Work(STG->Chl. BLDG) | 2018-03-20 | 2018-05-19
Activity | 0CF3510W58A20 | (COMP) Piping Work(STG->WTP) | 2018-03-20 | 2018-05-19
Activity | 0CF3510W62A21 | (COMP) Hydro Test | 2018-05-21 | 2018-06-05
Activity | 0CF4035W22A05 | (SWS) Piping Work(Block #2) | 2018-03-06 | 2018-06-06
Activity | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2017-01-23 | 2017-02-20
Activity | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2017-02-21
Activity | 1EF5550W20A03C | (PipeRack) Structure Design | 2017-02-21 | 2017-05-25
Activity | 1EF5550W16A05C | (PipeRack) FDN Design | 2017-02-21 | 2017-05-25
Activity | 1CF5550W16A06 | (PipeRack) FDN Work for HRSG Area | 2017-05-26 | 2017-09-25
Activity | 1EF5550W46A04B | (PipeRack) MPS Issue |  | 2017-05-26
Activity | 1PF5550W46A07P | (PipeRack) P.O & Procurement | 2017-06-27 | 2017-11-28
Activity | 1PF5550W46A08T | (PipeRack) Trasnportation | 2017-11-29 | 2018-01-06
Activity | 1CF5550W46A09 | (PipeRack) Structure Work for HRSG Area | 2018-01-08 | 2018-03-20
Activity | 1EF6500W70A01B | (ST GCB) MPS Issue |  | 2017-03-24
Activity | 1PF6500W70A02P | (ST GCB) P.O & Procurement | 2017-04-24 | 2018-03-01
Activity | 1PF6500W70A03T | (ST GCB) Transportation | 2018-03-02 | 2018-05-16
Activity | 1CF6500W70A04 | (ST GCB) Installation | 2018-06-06 | 2018-07-03
Activity | 1SF6500W62A05 | (ST GCB) Function Test | 2018-07-04 | 2018-07-15
Activity | 1EF6500W70A06B | (IPB) MPS Issue |  | 2017-03-24
Activity | 1PF6500W70A07P | (IPB) P.O & Procurement | 2017-04-24 | 2018-03-01
Activity | 1PF6500W70A08T | (IPB) Transportation | 2018-03-02 | 2018-05-16
Activity | 1CF6500W70A09 | (IPB) Installation form TR to GCB(incl. Support) | 2018-05-18 | 2018-07-03
Activity | 1CF6500W62A10 | (IPB) Insulation Test & Hi potential Test | 2018-07-04 | 2018-07-10
Activity | 1CF6500W70A11 | (IPB) IPB connection with TR & GCB | 2018-07-29 | 2018-08-04
Activity | 1EF6500W70A12B | (GSUT) MPS Issue |  | 2017-02-15
Activity | 1PF6500W70A13P | (GSUT) P.O & Procurement | 2017-03-15 | 2017-11-30
Activity | 1EF6500W16A14C | (GSUT) FDN Design | 2017-07-25 | 2017-11-21
Activity | 1CF6500W16A15 | (GSUT) FDN & Firewall Work | 2017-11-22 | 2018-03-21
Activity | 1PF6500W70A16T | (GSUT) Transportation | 2017-12-01 | 2018-01-01
Activity | 1CF6500W70A17 | (GSUT) Installation | 2018-03-22 | 2018-05-07
Activity | 1CF6500W38A18 | (GSUT) F/F Install & test | 2018-06-18 | 2018-07-11
Activity | 1SF6500W62A19 | (GSUT) Function Test | 2018-08-05 | 2018-08-16
Activity | 1EF6500W70A20B | (STG UAT) MPS Issue |  | 2017-02-15
Activity | 1PF6500W70A21P | (STG UAT) P.O & Procurement | 2017-03-15 | 2017-11-30
Activity | 1EF6500W16A22C | (STG UAT) FDN Design | 2017-07-25 | 2017-11-21
Activity | 1CF6500W16A23 | (STG UAT) FDN Work & Firewall Work | 2017-11-22 | 2018-03-21
Activity | 1PF6500W70A24T | (STG UAT) Transportation | 2017-12-01 | 2018-01-01
Activity | 1CF6500W70A25 | (STG UAT) Installation | 2018-03-22 | 2018-05-07
Activity | 1CF6500W38A26 | (STG UAT) F/F Install & test | 2018-06-18 | 2018-07-16
Activity | 1SF6500W62A27 | (STG UAT) Function Test | 2018-07-17 | 2018-07-28
Activity | 1EF6500W70A49 | (MV SWGR) Electrical Load List for MPS | 2016-12-27 | 2017-04-14
Activity | 1EF6500W70A28B | (MV SWGR) MPS Issue |  | 2017-04-14
Activity | 1PF6500W70A29P | (MV SWGR) P.O & Procurement | 2017-06-15 | 2017-10-02
Activity | 1PF6500W70A30T | (MV SWGR) Transportation | 2017-10-03 | 2017-10-31
Activity | 1CF6500W70A31 | (MV SWGR) Installation | 2017-11-01 | 2018-01-01
Activity | 1SF6500W62A32 | (MV SWGR) Function Test | 2018-03-22 | 2018-05-20
Activity | 1EF6500W70A50 | (LV SWGR) Electrical Load List for MPS | 2016-12-27 | 2017-04-14
Activity | 1EF6500W70A33B | (LV SWGR) MPS Issue |  | 2017-04-14
Activity | 1PF6500W70A34P | (LV SWGR) P.O & Procurement | 2017-06-15 | 2017-09-15
Activity | 1PF6500W70A35T | (LV SWGR) Transportation | 2017-09-16 | 2017-10-14
Activity | 1CF6500W70A36 | (LV SWGR) Installation | 2017-10-16 | 2018-03-01
Activity | 1SF6500W62A37 | (LV SWGR) Function Test | 2018-03-22 | 2018-05-20
Activity | 1EF6040W74A01B | (Electrical Cable) MPS Issue |  | 2017-05-15
Activity | 1PF6040W74A02P | (Electrical Cable) P.O & Procurement | 2017-06-15 | 2017-12-20
Activity | 1PF6040W74A03T | (Electrical Cable) Transportation | 2017-12-21 | 2018-02-03
Activity | 1CF6040W74A05 | (Electrical Cable) Cable Pulling for CCB-AIS Builiding | 2018-03-01 | 2018-03-10
Activity | 1CF6040W74A04 | (Electrical Cable) Cable Pulling for CCB-STG Builiding | 2018-03-01 | 2018-03-21
Activity | 1EF6500W70A38B | (Electrical Protection Panel) MPS Issue |  | 2017-05-15
Activity | 1PF6500W70A39P | (Electrical Protection Panel) P.O & Procurement | 2017-06-15 | 2017-12-25
Activity | 1PF6500W70A40T | (Electrical Protection Panel) Transportation | 2017-12-26 | 2018-02-08
Activity | 1CF6500W70A41 | (Electrical Protection Panel) Installation | 2018-02-09 | 2018-03-12
Activity | 1SF6500W62A42 | (Electrical Protection Panel) Function Test | 2018-06-01 | 2018-06-10
Activity | 1SF6500W62A43 | (Electrical Protection Panel) Secondary & Primary Test | 2018-06-11 | 2018-06-20
Activity | 1EF6040W70A06B | (Lighting Equip) MPS Issue |  | 2017-05-15
Activity | 1PF6040W70A07P | (Lighting Equip) P.O & Procurement | 2017-06-15 | 2018-01-11
Activity | 1PF6040W70A08T | (Lighting Equip) Transportation | 2018-01-12 | 2018-02-26
Activity | 1CF6040W70A09 | (Lighting Equip) Installation | 2018-02-27 | 2018-05-15
Activity | 1EF6040W80A10B | (Earthing & Lightning Material) MPS Issue |  | 2017-05-15
Activity | 1PF6040W80A11P | (Earthing & Lightning Material) P.O & Procurement | 2017-06-15 | 2017-10-16
Activity | 1PF6040W80A12T | (Earthing & Lightning Material) Transportation | 2017-10-17 | 2017-11-25
Activity | 1CF6040W80A13 | (Earthing & Lightning Material) Installation | 2017-11-27 | 2018-05-31
Activity | 1EF6040W74A14B | (Raceway) MPS Issue |  | 2017-06-13
Activity | 1PF6040W74A15P | (Raceway) P.O & Procurement | 2017-07-14 | 2017-12-13
Activity | 1PF6040W74A16T | (Raceway) Transportation | 2017-12-14 | 2018-01-27
Activity | 1CF6040W74A17 | (Raceway) Installation for CCB-STG Builiding | 2018-01-29 | 2018-02-28
Activity | 1CF6040W74A18 | (Raceway) Installation for CCB-AIS Builiding | 2018-01-29 | 2018-02-28
Activity | 1EF6500W70A44B | (Power Metering Equip) MPS Issue |  | 2017-05-15
Activity | 1PF6500W70A45P | (Power Metering Equip) P.O & Procurement | 2017-06-15 | 2018-01-15
Activity | 1PF6500W70A46T | (Power Metering Equip) Transportation | 2018-01-16 | 2018-03-01
Activity | 1CF6500W70A47 | (Power Metering Equip) Installation | 2018-03-02 | 2018-04-02
Activity | 1SF6500W62A48 | (Power Metering Equip) Function Test | 2018-04-03 | 2018-05-02
Activity | 1EF7000W86A15 | (DCS) I/O Point List for MPS | 2016-12-08 | 2017-01-05
Activity | 1EF7000W86A01B | (DCS) MPS Issue |  | 2017-01-06
Activity | 1PF7000W86A02P | (DCS) P.O & Procurement | 2017-02-13 | 2018-04-09
Activity | 1PF7000W86A03T | (DCS) Transportation | 2018-04-10 | 2018-05-17
Activity | 1CF7000W86A04 | (DCS) Installation | 2018-05-18 | 2018-06-18
Activity | 1SF7000W62A05 | (DCS) Loop Check | 2018-06-19 | 2018-07-14
Activity | 1SF7000W62A06 | (DCS) Start up | 2018-07-15 | 2018-08-05
Activity | 1SF7000W62A07 | (DCS) Electrical signal Test for Combined power | 2018-08-06 | 2018-08-14
Activity | 1EF7000W86A08B | (GTCS) MPS Issue |  | 2017-03-23
Activity | 1PF7000W86A09P | (GTCS) P.O & Procurement | 2017-04-24 | 2018-04-24
Activity | 1PF7000W86A10T | (GTCS) Transportation | 2018-04-25 | 2018-05-28
Activity | 1CF7000W86A11 | (GTCS #21) Installation | 2018-05-29 | 2018-06-08
Activity | 1SF7000W62A12 | (GTCS #21) Loop Check | 2018-06-09 | 2018-06-12
Activity | 1SF7000W62A13 | (GTCS #21) Skid Function Test | 2018-06-13 | 2018-06-19
Activity | 1SF7000W62A14 | (GTCS #21) Cranking Test / Load Test | 2018-06-20 | 2018-06-27
Activity | 2CF7000W86A01 | (GTCS #22) Installation | 2018-06-28 | 2018-07-09
Activity | 2SF7000W62A02 | (GTCS #22) Loop Check | 2018-07-10 | 2018-07-12
Activity | 2SF7000W62A03 | (GTCS #22) Skid Function Test | 2018-07-13 | 2018-07-19
Activity | 2SF7000W62A04 | (GTCS #22) Cranking Test / Load Test | 2018-07-20 | 2018-07-27
Activity | 3CF7000W86A01 | (GTCS #23) Installation | 2018-07-28 | 2018-08-08
Activity | 3SF7000W62A02 | (GTCS #23) Loop Check | 2018-08-09 | 2018-08-11
Activity | 3SF7000W62A03 | (GTCS #23) Skid Function Test | 2018-08-12 | 2018-08-18
Activity | 3SF7000W62A04 | (GTCS #23) Cranking Test / Load Test | 2018-08-19 | 2018-08-26
Activity | 0EF3025W00A40 | (Outtake Structure) GA & Load Data to Civil Design | 2017-01-24
Activity | 0EF3025W16A41C | (Outtake Structure) Structure Design | 2017-01-24 | 2017-04-21
Activity | 0EF3025W16A42C | (Outtake Structure) FDN Design | 2017-03-10 | 2017-05-19
Activity | 0EF3025W12A43 | (Outtake Structure) Excavation | 2017-05-22 | 2017-07-31
Activity | 0CF3025W16A44 | (Outtake Structure) FDN Work | 2017-08-01 | 2017-09-18
Activity | 0CF3025W16A45 | (Outtake Structure) Structure Work(Wall & Top Slab) | 2017-09-19 | 2018-01-01
Activity | 0CF3025W12A46 | (Outtake Structure) Backfilling | 2018-01-02 | 2018-03-03
Activity | 0EF3025W22A47B | (Outtake Culvert) MPS Issue |  | 2017-05-05
Activity | 0PF3025W22A48P | (Outtake Culvert) P.O & Procurement | 2017-06-05 | 2017-11-15
Activity | 0PF3025W22A49T | (Outtake Culvert) Transportation | 2017-11-16 | 2017-12-30
Activity | 0CF3025W22A50 | (Outtake Culvert) Installation | 2018-01-01 | 2018-05-31
Activity | 0CF3025W62A51 | (Outtake Culvert) Hydro Test | 2018-06-01 | 2018-06-29
Activity | 0EF6010W00A13 | (Cable Trench) GA & Load Data to Civil Design | 2017-04-07
Activity | 0EF6010W16A14C | (Cable Trench) Design | 2017-04-07 | 2017-08-04
Activity | 0CF6010W12A15 | (Cable Trench) Excavation | 2017-04-07 | 2017-09-04
Activity | 0CF6010W16A16 | (Cable Trench) Structure Work | 2017-08-05 | 2017-11-24
Activity | 0CF6010W12A17 | (Cable Trench) Backfilling | 2017-09-21 | 2017-12-23
Activity | 0EF6030W42A02B | (Crane & Hoist) MPS Issue(BFP C/H) |  | 2017-02-06
Activity | 0EF6030W42A01B | (Crane & Hoist) MPS Issue |  | 2017-03-07
Activity | 0PF6030W42A04P | (Crane & Hoist) P.O & Procurement(BFP C/H) | 2017-04-07 | 2017-12-01
Activity | 0PF6030W42A03P | (Crane & Hoist) P.O & Procurement | 2017-04-07 | 2017-12-01
Activity | 0PF6030W42A05T | (Crane & Hoist) Transportation | 2017-12-02 | 2018-01-16
Activity | 0PF6030W42A06T | (Crane & Hoist) Transportation(BFP C/H) | 2017-12-02 | 2018-01-16
Activity | 0PF6030W42A07T | (Crane & Hoist) 1st Delivery |  | 2018-01-16
Activity | 0CF2010W42A13 | (Crane & Hoist) Crane accessory Installation for OHC extension | 2018-01-20 | 2018-02-13
Activity | 0PF6030W42A08T | (Crane & Hoist) 2nd Delivery |  | 2018-01-24
Activity | 0CF6030W42A10 | (Crane & Hoist) Crane Erection for Power Block Building | 2018-01-25 | 2018-02-24
Activity | 0CF6030W42A09 | (Crane & Hoist) Crane Erection for BOP Building(Chl./ FF/ WTP BLDG) | 2018-04-02 | 2018-05-02
Activity | 0EF6500W70A01B | (Switchyard) MPS Issue |  | 2017-02-16
Activity | 0PF6500W70A02P | (Switchyard) P.O & Procurement | 2017-02-23 | 2017-09-26
Activity | 0EF6500W70A03C | (Switchyard) FDN Design | 2017-04-07 | 2017-08-02
Activity | 0PF6500W70A04T | (Switchyard) FDN Work | 2017-08-03 | 2017-10-30
Activity | 0PF6500W70A05T | (Switchyard) Transportation | 2017-09-27 | 2017-11-03
Activity | 0CF6500W70A06 | (Switchyard) Installation | 2017-11-04 | 2018-02-02
Activity | 0SF6500W62A07 | (Switchyard) Commissioning | 2018-02-03 | 2018-03-04
Activity | 0EF6500W70A08B | (SST) MPS Issue |  | 2016-12-08
Activity | 0EF6500W16A10C | (SST) FDN Design | 2017-02-23 | 2017-05-31
Activity | 0PF6500W70A09P | (SST) P.O & Procurement | 2017-02-07 | 2017-09-14
Activity | 0CF6500W16A11 | (SST) FDN & Firewall Work | 2017-06-01 | 2017-09-15
Activity | 0PF6500W70A12T | (SST) Transportation | 2017-09-15 | 2017-10-30
Activity | 0CF6500W70A13 | (SST) Installation | 2017-10-31 | 2018-01-29
Activity | 0CF6500W38A14 | (SST) F/F Install & test | 2018-01-30 | 2018-02-16
Activity | 0SF6500W62A15 | (SST) Function Test | 2018-02-17 | 2018-03-02
Activity | 0EF6500W70A53 | (MV SWGR) Electrical Load List | 2016-12-27 | 2017-04-14
Activity | 0EF6500W70A16B | (MV SWGR) MPS Issue |  | 2017-04-14
Activity | 0PF6500W70A17P | (MV SWGR) P.O & Procurement for Power recieving | 2017-06-15 | 2017-10-02
Activity | 0PF6500W70A18T | (MV SWGR) Transportation | 2017-10-03 | 2017-10-31
Activity | 0CF6500W70A19 | (MV SWGR) Installation for Power recieving | 2017-11-01 | 2017-12-30
Activity | 0SF6500W62A20 | (MV SWGR) Function Test | 2018-02-07 | 2018-02-27
Activity | 0EF6500W70A54 | (LV SWGR) Electrical Load List | 2016-12-27 | 2017-04-14
Activity | 0EF6500W70A21B | (LV SWGR) MPS Issue |  | 2017-04-14
Activity | 0PF6500W70A22P | (LV SWGR) P.O & Procurement for Power recieving | 2017-06-15 | 2017-09-15
Activity | 0PF6500W70A23T | (LV SWGR) Transportation | 2017-09-16 | 2017-10-14
Activity | 0CF6500W70A24 | (LV SWGR) Installation for Power recieving | 2017-10-16 | 2018-03-03
Activity | 0SF6500W62A25 | (LV SWGR) Function Test | 2018-03-04 | 2018-03-24
Activity | 0EF6500W70A26B | (DC & UPS) MPS Issue |  | 2017-01-23
Activity | 0PF6500W70A27P | (DC & UPS) P.O & Procurement | 2017-03-06 | 2017-10-13
Activity | 0PF6500W70A28T | (DC & UPS) Transportation | 2017-10-14 | 2017-12-27
Activity | 0CF6500W70A29 | (DC & UPS) Installation(incl. DB) | 2017-12-28 | 2018-02-02
Activity | 0SF6500W62A30 | (DC & UPS) Function Test | 2018-02-03 | 2018-02-06
Activity | 0EF6500W70A31B | (Battery) MPS Issue |  | 2017-01-23
Activity | 0PF6500W70A32P | (Battery) P.O & Procurement | 2017-03-06 | 2017-10-13
Activity | 0PF6500W70A33T | (Battery) Transportation | 2017-10-14 | 2017-12-27
Activity | 0CF6500W70A34 | (Battery) Installation | 2017-12-28 | 2018-02-02
Activity | 0SF6500W62A35 | (Battery) System Test(Incl. Acid Filling & Initial charging) | 2018-02-03 | 2018-02-06
Activity | 0EF3530W00A01 | (EDG) Key data | 2016-12-26 | 2017-02-22
Activity | 0EF3530W42A02B | (EDG) MPS Issue |  | 2017-03-24
Activity | 0PF3530W42A03P | (EDG) P.O & Procurement | 2017-04-25 | 2017-10-09
Activity | 0PF3530W42A06T | (EDG) Transportation | 2017-10-10 | 2017-11-23
Activity | 0CF3530W42A07 | (EDG) Installation | 2017-11-24 | 2017-12-26
Activity | 0CF3530W38A18 | (EDG) Installation - Fire Fighting Sys. | 2017-12-27 | 2018-02-10
Activity | 0CF3530W74A19 | (EDG) Installation & Test - Elec | 2017-12-27 | 2018-02-10
Activity | 0CF3530W90A21 | (EDG) Installation & Test - I&C | 2017-12-27 | 2018-02-10
Activity | 0SF3530W62A08 | (EDG) Loop chek | 2018-02-12 | 2018-02-19
Activity | 0SF3530W62A09 | (EDG) System Function Test | 2018-02-20 | 2018-02-27
Activity | 0SF3530W62A10 | (EDG) Initial Start up | 2018-02-28 | 2018-03-02
Activity | 0SF3530W62A11 | (EDG) Synchronization | 2018-03-03 | 2018-03-04
Activity | 0SF3530W62A12 | (EDG) Load Operation | 2018-03-05 | 2018-03-09
Activity | 0EF3530W00A13 | (EDG Shelter) GA & Load Data to Civil Design |  | 2017-03-24
Activity | 0EF3530W16A14C | (EDG Shelter) FDN Design | 2017-04-25 | 2017-07-21
Activity | 0EF3530W32A15 | (EDG Shelter) Structure Design | 2017-05-24 | 2017-09-22
Activity | 0CF3530W16A16 | (EDG Shelter) FDN Work | 2017-07-22 | 2017-09-18
Activity | 0CF3530W32A17 | (EDG Shelter) Structure Work | 2017-11-24 | 2018-02-01
Activity | 0EF6040W74A01B | (Electrical Cable) MPS Issue |  | 2017-03-10
Activity | 0PF6040W74A02P | (Electrical Cable) P.O & Procurement | 2017-04-12 | 2017-10-17
Activity | 0PF6040W74A03T | (Electrical Cable) Transportation | 2017-10-18 | 2017-12-01
Activity | 0CF6040W74A04 | (Electrical Cable) Cable Pulling for CCB-STG Building | 2017-12-27 | 2018-01-16
Activity | 0CF6040W74A05 | (Electrical Cable) Cable Pulling for CCB-AIS BLDG(for P/R) | 2018-01-25 | 2018-02-03
Activity | 0EF6500W70A36B | (Electrical Protection Panel) MPS Issue |  | 2017-03-24
Activity | 0PF6500W70A37P | (Electrical Protection Panel) P.O & Procurement | 2017-04-24 | 2017-11-01
Activity | 0PF6500W70A38T | (Electrical Protection Panel) Transportation | 2017-11-02 | 2017-12-16
Activity | 0CF6500W70A39 | (Electrical Protection Panel) Installation | 2017-12-18 | 2018-01-17
Activity | 0SF6500W62A40 | (Electrical Protection Panel) Function Test | 2018-03-04 | 2018-03-13
Activity | 0SF6500W62A41 | (Electrical Protection Panel) Secondary & Primary Test | 2018-03-14 | 2018-03-23
Activity | 0EF6040W80A07B | (Earthing & Lightning Material) MPS Issue |  | 2017-03-10
Activity | 0PF6040W80A08P | (Earthing & Lightning Material) P.O & Procurement | 2017-04-12 | 2017-08-11
Activity | 0PF6040W80A09T | (Earthing & Lightning Material) Transportation | 2017-08-12 | 2017-09-21
Activity | 0CF6040W80A10 | (Earthing & Lightning Material) Installation | 2017-09-22 | 2018-03-03
Activity | 0EF6040W74A16 | (Raceway) Design | 2017-02-17 | 2017-10-09
Activity | 0EF6040W74A11B | (Raceway) MPS Issue |  | 2017-04-11
Activity | 0PF6040W74A12P | (Raceway) P.O & Procurement | 2017-05-11 | 2017-10-10
Activity | 0PF6040W74A13T | (Raceway) Transportation | 2017-10-11 | 2017-11-24
Activity | 0CF6040W74A14 | (Raceway) Installation for CCB-STG Building | 2017-11-25 | 2017-12-26
Activity | 0CF6040W74A15 | (Raceway) Installation for CCB-AIS BLDG | 2017-12-25 | 2018-01-24
Activity | 0EF6500W70A42B | (Power Metering Equip) MPS Issue |  | 2017-03-06
Activity | 0PF6500W70A43P | (Power Metering Equip) P.O & Procurement | 2017-04-06 | 2017-11-06
Activity | 0PF6500W70A44T | (Power Metering Equip) Transportation | 2017-11-07 | 2017-12-21
Activity | 0CF6500W70A45 | (Power Metering Equip) Installation | 2017-12-22 | 2018-01-22
Activity | 0SF6500W62A46 | (Power Metering Equip) Function Test | 2018-01-23 | 2018-02-21
Activity | 0SF6500W62A47 | (Power Receiving) Interface signal Test | 2018-03-31 | 2018-04-05
Activity | 0SF6500W62A48 | (Power Receiving) Interlock Test between power plant & LCC | 2018-04-06 | 2018-04-09
Activity | 0SF6500W62A49 | (Power Receiving) Overall Interlock & Intertrip Test | 2018-04-10 | 2018-04-15
Activity | 0SF6500W62A50 | (Power Receiving) Protection Secondary & Primary Test | 2018-04-16 | 2018-04-23
Activity | 0SF6500W62A51 | (Power Receiving) Back Charging of Transformer | 2018-04-24 | 2018-04-26
Activity | 0SF6500W62A52 | (Power Receiving) Permit power receiving from LCC | 2018-04-27 | 2018-04-30
Activity | 0EF7000W86A16 | (DCS for P/R) I/O Point List for P/R | 2016-12-08 | 2017-01-05
Activity | 0EF7000W86A01B | (DCS for P/R) MPS Issue |  | 2017-01-06
Activity | 0PF7000W86A02P | (DCS for P/R) P.O & Procurement | 2017-02-13 | 2018-01-25
Activity | 0PF7000W86A03T | (DCS for P/R) Transportation | 2018-01-26 | 2018-03-05
Activity | 0CF7000W86A04 | (DCS for P/R) Installation | 2018-03-06 | 2018-03-21
Activity | 0SF7000W62A05 | (DCS for P/R) Loop Check | 2018-03-22 | 2018-03-24
Activity | 0SF7000W62A06 | (DCS for P/R) Start up | 2018-03-25 | 2018-03-27
Activity | 0SF7000W62A07 | (DCS for P/R) Electrical signal Test for Power Receiving | 2018-03-28 | 2018-03-30
Activity | 1EF3030W00A01 | (ACWS) P&ID & System Design | 2016-12-08 | 2017-06-14
Activity | 1EF3030W00A02 | (ACWS) ACWP Key data | 2017-01-23 | 2017-02-03
Activity | 1EF3030W42A03B | (ACW PUMP) MPS Issue |  | 2017-02-03
Activity | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2017-04-14 | 2018-04-12
Activity | 1PF3030W42A05T | (ACW PUMP) Transportation | 2018-04-13 | 2018-05-28
Activity | 1CF3030W42A06 | (ACW PUMP) Installation | 2018-05-29 | 2018-06-22
Activity | 1CF3030W74A07 | (ACW PUMP) Installation - Elec | 2018-06-23 | 2018-07-18
Activity | 1CF3030W90A08 | (ACW PUMP) Installation - I&C | 2018-06-23 | 2018-07-18
Activity | 1SF3030W62A14 | (ACWS) Loop check | 2018-07-25 | 2018-08-04
Activity | 1SF3030W62A15 | (ACWS) System Function Test | 2018-08-05 | 2018-08-09
Activity | 1SF3030W62A16 | (ACWS) Pump Operation | 2018-08-10 | 2018-08-14
Activity | 1EF3030W00A58 | (CCWP) CCW Consumption Data | 2016-12-08 | 2017-01-20
Activity | 1EF3030W00A59 | (CCWP) CCW Design Condition of TP | 2016-12-08 | 2017-01-30
Activity | 1EF3030W00A17 | (CCWP) Key data | 2016-12-08 | 2017-02-03
Activity | 1EF3030W42A18B | (CCWP) MPS Issue |  | 2017-02-03
Activity | 1PF3030W42A19P | (CCWP) P.O & Procurement | 2017-04-14 | 2018-02-28
Activity | 1EF3030W16A20C | (CCWP) FDN Design | 2017-04-17 | 2017-08-02
Activity | 1CF3030W16A21 | (CCWP) FDN Work | 2017-08-03 | 2017-09-29
Activity | 1PF3030W42A23T | (CCWP) Transportation | 2018-03-01 | 2018-04-14
Activity | 1CF3030W42A26 | (CCWP) Installation | 2018-04-16 | 2018-06-22
Activity | 1CF3030W58A22 | (CCWS) Piping Work | 2018-04-24 | 2018-06-23
Activity | 1CF3030W74A24 | (CCWS) Installation & Test - Elec. | 2018-04-24 | 2018-06-23
Activity | 1CF3030W90A25 | (CCWS) Installation & Test - I&C | 2018-04-24 | 2018-06-23
Activity | 1SF3030W62A27 | (CCWS) Loop chek | 2018-06-25 | 2018-06-29
Activity | 1SF3030W62A28 | (CCWS) System Function Test | 2018-06-30 | 2018-07-04
Activity | 1SF3030W62A29 | (CCWS) Pump Operation | 2018-07-09 | 2018-07-11
Activity | 1SF3030W62A30 | (CCWS) CCW Flushing | 2018-07-12 | 2018-08-05
Activity | 0EF3032W00A01B | (Temp. Cooling Tower) MPS Issue |  | 2017-05-31
Activity | 0PF3032W42A02P | (Temp. Cooling Tower) P.O & Procurement | 2017-08-23 | 2017-12-20
Activity | 0PF3032W42A03T | (Temp. Cooling Tower)Transportation | 2017-12-21 | 2018-01-27
Activity | 0CF3032W42A04 | (Temp. Cooling Tower) Installation | 2018-01-29 | 2018-04-03
Activity | 0CF3032W58A05 | (Temp. Cooling Tower) Temp. pipe install | 2018-04-04 | 2018-04-23
Activity | 0SF3032W62A06 | (Temp. Cooling Tower) Function Test | 2018-04-24 | 2018-04-29
Activity | 1EF3030W00A31 | (CCW H/EX) CCW H/EX key data | 2016-12-08 | 2017-01-24
Activity | 1EF3030W00A54 | (CCW H/EX) GA & Load Data to Civil Design | 2017-01-26 | 2017-03-08
Activity | 1EF3030W00A57 | (CCW H/EX) Owner Approval for Key Data | 2017-01-26 | 2017-02-08
Activity | 1EF3030W42A32B | (CCW H/EX) MPS Issue |  | 2017-02-24
Activity | 1EF3030W16A34C | (CCW H/EX) FDN Design | 2017-03-09 | 2017-06-26
Activity | 1PF3030W42A33P | (CCW H/EX) P.O & Procurement | 2017-05-25 | 2018-03-23
Activity | 1CF3030W16A35 | (CCW H/EX) FDN Work | 2017-06-27 | 2017-09-21
Activity | 1PF3030W42A36T | (CCW H/EX) Transportation | 2018-03-24 | 2018-05-01
Activity | 1CF3030W42A37 | (CCW H/EX) Installation | 2018-05-02 | 2018-06-02
Activity | 1EF3030W68A38B1 | (EXP Head Tank) key data | 2017-01-04 | 2017-02-21
Activity | 1EF3030W68A55 | (EXP Head Tank) GA & Load Data to Civil Design | 2017-02-22 | 2017-04-04
Activity | 1EF3030W00A56 | (EXP Head Tank) Owner Approval for Key Data | 2017-02-22 | 2017-03-07
Activity | 1EF3030W68A38B | (EXP Head Tank) MPS Issue |  | 2017-03-23
Activity | 1PF3030W68A39P | (EXP Head Tank) P.O & Procurement | 2017-06-21 | 2018-01-22
Activity | 1EF3030W16A40C | (EXP Head Tank) FDN Design | 2017-07-10 | 2017-12-06
Activity | 1CF3030W16A41 | (EXP Head Tank) FDN Work | 2018-01-20 | 2018-02-17
Activity | 1PF3030W68A42T | (EXP Head Tank) Transportation | 2018-01-23 | 2018-03-08
Activity | 1CF3030W68A43 | (EXP Head Tank) Installation | 2018-03-09 | 2018-04-06
Activity | 1EF3030W00A46 | (CCW Chemical Additive Tank) key data | 2016-12-08 | 2017-02-21
Activity | 1EF3030W00A61 | (CCW Chemical Additive Tank) GA & Load Data to Civil Design | 2017-02-22 | 2017-04-04
Activity | 1EF3020W00A55 | (CCW Chemical Additive Tank) Owner Approval for Key Data | 2017-02-22 | 2017-03-07
Activity | 1EF3030W42A47B | (CCW Chemical Additive Tank) MPS Issue |  | 2017-03-23
Activity | 1EF3030W16A49C | (CCW Chemical Additive Tank) FDN Design | 2017-04-05 | 2017-07-21
Activity | 1PF3030W42A48P | (CCW Chemical Additive Tank) P.O & Procurement | 2017-06-21 | 2018-01-22
Activity | 1EF3030W16A46 | (CCW Chemical Additive Tank) FDN Work | 2017-07-22 | 2017-10-17
Activity | 1PF3030W42A51T | (CCW Chemical Additive Tank) Transportation | 2018-01-23 | 2018-03-08
Activity | 1CF3030W42A52 | (CCW Chemical Additive Tank) Installation | 2018-03-09 | 2018-04-10
Activity | 1EF3030W00A53 | (CCW Tube Cleaning system) key data | 2016-12-08 | 2017-02-21
Activity | 1EF3030W00A62 | (CCW Tube Cleaning system) GA & Load Data to Civil Design | 2017-02-22 | 2017-04-04
Activity | 1EF3020W00A56 | (CCW Tube Cleaning system) Owner Approval for Key Data | 2017-02-22 | 2017-03-07
Activity | 1EF3030W42A54B | (CCW Tube Cleaning system) MPS Issue |  | 2017-03-23
Activity | 1EF3030W16A50C | (CCW Tube Cleaning system) FDN Design | 2017-04-05 | 2017-07-21
Activity | 1PF3030W42A55P | (CCW Tube Cleaning system) P.O & Procurement | 2017-06-21 | 2018-01-22
Activity | 1EF3030W16A49 | (CCW Tube Cleaning system) FDN Work | 2017-07-22 | 2017-10-17
Activity | 1PF3030W42A56T | (CCW Tube Cleaning system) Transportation | 2018-01-23 | 2018-03-08
Activity | 1CF3030W42A57 | (CCW Tube Cleaning system) Installation | 2018-03-09 | 2018-04-10
Activity | 1EF3510W00A22 | (COMP Air System) Air Consumption Data for IA,SA | 2016-12-08 | 2017-01-16
Activity | 1EF3510W00A01 | (COMP Air System) Compressed Air Sys. Key data | 2017-01-06 | 2017-02-06
Activity | 1EF3510W00A02 | (COMP Air System) P&ID & System Design | 2017-02-06 | 2017-09-20
Activity | 1EF3510W42A03B | (COMP Air PKG) MPS Issue |  | 2017-02-06
Activity | 1PF3510W42A04P | (COMP Air PKG) P.O & Procurement | 2017-03-09 | 2018-01-04
Activity | 1EF3510W16A05C | (COMP Air PKG) FDN Design | 2017-03-09 | 2017-07-11
Activity | 1CF3510W16A06 | (COMP Air PKG) FDN Work | 2017-07-12 | 2017-09-09
Activity | 1PF3510W42A07T | (COMP Air PKG) Transportation | 2018-01-05 | 2018-02-12
Activity | 1CF3510W42A08 | (COMP Air PKG) Installation_Compressor, Dryer, Reciever Tank | 2018-02-13 | 2018-04-10
Activity | 1CF3510W58A09 | (COMP Air System) IA Piping Work(Upto IA header) | 2018-03-08 | 2018-05-03
Activity | 1CF3510W58A10 | (COMP Air System) SA Piping Work(Upto SA Header) | 2018-03-08 | 2018-05-09
Activity | 1CF3510W74A11 | (COMP Air System) Installation & Test - Elec. | 2018-03-20 | 2018-04-19
Activity | 1CF3510W90A12 | (COMP Air System) Installation & Test - I&C | 2018-03-20 | 2018-04-19
Activity | 1CF3510W58A14 | (COMP Air System) Piping Work for CP(incl. Air Blowing) | 2018-04-24 | 2018-07-02
Activity | 1SF3510W62A13 | (COMP Air System) Loop chek | 2018-05-10 | 2018-05-17
Activity | 1SF3510W62A15 | (COMP Air System) Motor Solo Test & System Function Test | 2018-05-18 | 2018-06-02
Activity | 1SF3510W62A16 | (COMP Air System) Load Test | 2018-07-11 | 2018-07-25
Activity | 1EF3020W00A03 | (COND System) P&ID & System Design | 2016-12-26 | 2017-08-25
Activity | 1EF3020W00A04 | (COND System) Key data | 2016-12-08 | 2017-01-16
Activity | 1EF3020W00A01 | (COND) Condenser Design Data | 2016-12-08 | 2017-01-20
Activity | 1EF3020W00A02 | (COND) Utility Consumption Data | 2016-12-08 | 2017-02-02
Activity | 1EF3020W00A51 | (COND) Owner Approval for Key Data | 2017-01-17 | 2017-01-30
Activity | 1EF3020W42A05B | (COND) MPS Issue |  | 2017-02-15
Activity | 1EF3020W00A67 | (COND) GA & Load Data to Civil Design | 2017-02-28 | 2017-04-10
Activity | 1EF3020W16A06C | (COND) FDN Design | 2017-04-11 | 2017-07-14
Activity | 1PF3020W42A07P | (COND) P.O & Procurement | 2017-05-16 | 2018-03-07
Activity | 1CF3020W16A08 | (COND) FDN Work | 2017-07-15 | 2017-10-16
Activity | 1PF3020W42A09T | (COND) Transportation | 2018-03-08 | 2018-04-14
Activity | 1CF3020W58A11 | (COND System) Piping Work(incl. Insulation) | 2018-04-16 | 2018-07-17
Activity | 1CF3020W74A12 | (COND System) Installation & Test - Elec. | 2018-04-16 | 2018-07-17
Activity | 1CF3020W90A13 | (COND System) Installation & Test - I&C | 2018-04-16 | 2018-07-17
Activity | 1CF3020W42A10 | (COND) Installation | 2018-04-16 | 2018-07-17
Activity | 1SF3020W62A14 | (COND System) Loop check | 2018-07-18 | 2018-08-01
Activity | 1SF3020W62A15 | (COND System) System Function Test | 2018-08-02 | 2018-08-19
Activity | 1SF3020W62A16 | (COND System) Pump Operation | 2018-08-20 | 2018-09-04
Activity | 1EF3020W00A17 | (ATM Flash Tank) key data | 2016-12-08 | 2017-02-06
Activity | 1EF3020W00A49 | (ATM Flash Tank) Owner Approval for Key Data | 2017-02-07 | 2017-02-20
Activity | 1EF3020W42A18B | (ATM Flash Tank) MPS Issue |  | 2017-03-08
Activity | 1EF3020W00A58 | (ATM Flash Tank) GA & Load Data to Civil Design | 2017-03-21 | 2017-05-01
Activity | 1EF3020W16A20C | (ATM Flash Tank) FDN Design | 2017-05-02 | 2017-08-07
Activity | 1PF3020W42A19P | (ATM Flash Tank) P.O & Procurement | 2017-06-06 | 2018-01-05
Activity | 1CF3020W16A21 | (ATM Flash Tank) FDN Work | 2017-08-08 | 2017-10-16
Activity | 1PF3020W42A22T | (ATM Flash Tank) Transportation | 2018-01-06 | 2018-02-13
Activity | 1CF3020W42A23 | (ATM Flash Tank) Installation | 2018-04-16 | 2018-05-14
Activity | 1EF3020W00A24 | (CTCS/DF) key data | 2016-12-08 | 2017-01-16
Activity | 1EF3020W00A50 | (CTCS/DF) Owner Approval for Key Data | 2017-01-17 | 2017-01-30
Activity | 1EF3020W42A25B | (CTCS/DF) MPS Issue |  | 2017-02-15
Activity | 1EF3020W00A59 | (CTCS/DF) GA & Load Data to Civil Design | 2017-02-28 | 2017-04-10
Activity | 1EF3020W16A31C1 | (CTCS/DF) FDN Design | 2017-04-11 | 2017-08-07
Activity | 1PF3020W42A26P | (CTCS/DF) P.O & Procurement | 2017-05-16 | 2017-12-15
Activity | 1CF3020W16A44 | (CTCS/DF) FDN Work | 2017-08-08 | 2017-10-16
Activity | 1PF3020W42A27T | (CTCS/DF) Transportation | 2017-12-16 | 2018-01-23
Activity | 1CF3020W42A28 | (CTCS/DF) Installation | 2018-01-24 | 2018-03-07
Activity | 1EF3020W42A60 | (CEP) GA & Load Data to Civil Design | 2017-01-17 | 2017-02-27
Activity | 1EF3020W42A29B | (CEP) MPS Issue |  | 2017-02-16
Activity | 1EF3020W16A31C | (CEP) FDN Design | 2017-03-20 | 2017-06-15
Activity | 1PF3020W42A30P | (CEP) P.O & Procurement | 2017-05-01 | 2018-02-12
Activity | 1CF3020W16A32 | (CEP) FDN Work | 2017-06-16 | 2017-10-17
Activity | 1PF3020W42A33T | (CEP) Transportation | 2018-02-13 | 2018-03-29
Activity | 1CF3020W42A34 | (CEP) Installation | 2018-03-30 | 2018-05-30
Activity | 1EF3020W42A35 | (Catridge Filter) MPS Issue |  | 2017-02-08
Activity | 1PF3020W42A36 | (Catridge Filter) P.O & Procurement | 2017-04-07 | 2018-03-23
Activity | 1PF3020W42A37 | (Catridge Filter) Transportation | 2018-03-24 | 2018-05-08
Activity | 1CF3020W42A38 | (Catridge Filter) Installation - Catridge Filter | 2018-05-09 | 2018-05-24
Activity | 1CF3020W42A47 | (Catridge Filter) Installation - LCP | 2018-05-09 | 2018-05-24
Activity | 1CF3020W42A46 | (Catridge Filter) Installation - Backwash Pump | 2018-05-25 | 2018-06-09
Activity | 1CF3020W42A49 | (Catridge Filter) Installation - Elec. & I&C | 2018-05-25 | 2018-06-09
Activity | 1SF3020W62A40 | (Catridge Filter) Loop check | 2018-06-11 | 2018-06-26
Activity | 1CF3020W42A48 | (Catridge Filter) Installation & Piping | 2018-06-11 | 2018-06-26
Activity | 1SF3020W62A41 | (Catridge Filter) System Function Test | 2018-06-27 | 2018-07-11
Activity | 1SF3020W62A39 | (Catridge Filter) System Operation | 2018-07-12 | 2018-07-26
Activity | 1EF3020W00A39 | (CVP/WBVP) key data | 2016-12-08 | 2017-03-09
Activity | 1EF3020W42A40B | (CVP/WBVP) MPS Issue |  | 2017-03-09
Activity | 1EF3020W42A61 | (CVP/WBVP) GA & Load Data to Civil Design | 2017-03-10 | 2017-04-20
Activity | 1EF3020W16A42C | (CVP/WBVP) FDN Design | 2017-04-21 | 2017-07-18
Activity | 1PF3020W42A41P | (CVP/WBVP) P.O & Procurement | 2017-06-16 | 2018-05-17
Activity | 1CF3020W16A43 | (CVP/WBVP) FDN Work | 2017-07-19 | 2017-10-17
Activity | 1PF3020W42A44T | (CVP/WBVP) Transportation | 2018-05-18 | 2018-07-02
Activity | 1CF3020W42A45 | (CVP/WBVP) Installation | 2018-07-03 | 2018-09-04
Activity | 1EF3015W00A02 | (FWS) BFP Key data | 2017-01-06 | 2017-03-08
Activity | 1EF3015W00A01 | (FWS) P&ID & System Design | 2017-01-04 | 2017-08-18
Activity | 1CF3015W74A07 | (FWS) Installation & Test - Elec. | 2018-04-23 | 2018-06-23
Activity | 1CF3015W90A08 | (FWS) Installation & Test - I&C | 2018-04-23 | 2018-06-23
Activity | 1SF3015W62A10 | (FWS) Loop check | 2018-08-01 | 2018-08-23
Activity | 1SF3015W62A11 | (FWS) System Function Test | 2018-08-24 | 2018-09-06
Activity | 1SF3015W62A12 | (FWS) Pump Operation | 2018-09-07 | 2018-09-20
Activity | 1EF3015W42A13B | (FWP) MPS Issue |  | 2017-01-06
Activity | 1PF3015W42A14P | (FWP) P.O & Procurement | 2017-03-08 | 2018-03-07
Activity | 1PF3015W42A21 | (FWP) GA & Load Data to Civil Design | 2017-03-09 | 2017-05-16
Activity | 1EF3015W16A15C | (FWP) FDN Design | 2017-05-17 | 2017-07-17
Activity | 1CF3015W16A16 | (FWP) FDN Work | 2017-07-18 | 2017-10-16
Activity | 1PF3015W42A17T | (FWP) Transportation | 2018-03-08 | 2018-04-21
Activity | 1CF3015W42A18 | (FWP) Installation | 2018-04-23 | 2018-08-23
Activity | 1EF3015W00A19 | (FWTK) key data | 2017-01-06 | 2017-03-08
Activity | 1EF3015W00A22 | (FWTK)) GA & Load Data to Civil Design | 2017-03-09 | 2017-04-19
Activity | 1EF3020W00A52 | (FWTK)) Owner Approval for Key Data | 2017-03-09 | 2017-03-22
Activity | 1EF3015W42A20B | (FWTK) MPS Issue |  | 2017-04-07
Activity | 1EF3015W16A22C | (FWTK) FDN Design | 2017-07-25 | 2017-12-21
Activity | 1PF3015W42A21P | (FWTK) P.O & Procurement | 2017-07-31 | 2018-03-07
Activity | 1CF3015W16A23 | (FWTK) FDN Work | 2018-01-20 | 2018-02-17
Activity | 1PF3015W42A24T | (FWTK) Transportation | 2018-03-08 | 2018-04-21
Activity | 1CF3015W42A25 | (FWTK) Installation | 2018-04-23 | 2018-05-21
Activity | 1EF3045W00A27 | (Chemical Dosing System) P&ID & System Design | 2016-12-26 | 2017-08-09
Activity | 1EF3045W42A28B | (Chemical Dosing Equip) MPS Issue |  | 2017-02-08
Activity | 1PF3045W42A29P | (Chemical Dosing Equip) P.O & Procurement | 2017-05-12 | 2018-04-11
Activity | 1PF3045W42A30T | (Chemical Dosing Equip) Transportation | 2018-04-12 | 2018-05-26
Activity | 1CF3045W42A32 | (Chemical Dosing Equip) Installation | 2018-05-28 | 2018-07-28
Activity | 1CF3045W58A31 | (Chemical Dosing System) Piping Work | 2018-05-28 | 2018-08-28
Activity | 1CF3045W74A33 | (Chemical Dosing System) Installation & Test - Elec. | 2018-06-22 | 2018-08-23
Activity | 1CF3045W90A34 | (Chemical Dosing System) Installation & Test - I&C | 2018-06-22 | 2018-08-23
Activity | 1SF3045W62A35 | (Chemical Dosing System) Loop chek | 2018-08-29 | 2018-09-14
Activity | 1SF3045W62A36 | (Chemical Dosing System) System Function Test | 2018-09-21 | 2018-09-27
Activity | 1SF3045W62A37 | (Chemical Dosing System) System Operation | 2018-09-28 | 2018-10-04
Activity | 1EF3040W00A01 | (Sampling System) P&ID & System Design | 2016-12-26 | 2017-05-26
Activity | 1EF3040W42A02B | (Sampling Equip) MPS Issue |  | 2017-02-07
Activity | 1PF3040W42A03P | (Sampling Equip) P.O & Procurement | 2017-05-01 | 2018-03-30
Activity | 1EF3040W16A04C | (Sampling Equip) FDN Design | 2017-06-01 | 2017-08-18
Activity | 1CF3040W16A05 | (Sampling Equip) FDN Work | 2017-08-19 | 2017-10-16
Activity | 1PF3040W42A06T | (Sampling Equip) Transportation | 2018-03-31 | 2018-05-15
Activity | 1CF3040W42A07 | (Sampling Equip) Installation | 2018-05-16 | 2018-06-15
Activity | 1CF3040W58A08 | (Sampling System) Piping Work | 2018-06-16 | 2018-09-11
Activity | 1CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2018-08-11 | 2018-09-11
Activity | 1CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2018-08-11 | 2018-09-11
Activity | 1SF3040W62A11 | (Sampling System) Loop chek | 2018-09-12 | 2018-09-22
Activity | 1SF3040W62A12 | (Sampling System) Chiller Function Test | 2018-09-23 | 2018-09-27
Activity | 1SF3040W62A13 | (Sampling System) Sampling System Function Test | 2018-09-28 | 2018-10-02
Activity | 1SF3040W62A14 | (Sampling System) System Service | 2018-10-03 | 2018-10-07
Activity | 1EF2510W00A02 | (Steam System) P&ID | 2017-01-09 | 2017-08-23
Activity | 1EF2510W00A01 | (Steam System) Silencer Key data | 2016-12-08 | 2017-03-22
Activity | 1EF2510W42A03B | (Silencer) MPS Issue |  | 2017-03-22
Activity | 1EF2510W58A04B | (Steam PIPING) MPS Issue |  | 2017-05-08
Activity | 1PF2510W42A05P | (Silencer) P.O & Procurement | 2017-06-19 | 2018-03-21
Activity | 1PF2510W58A06P | (Steam PIPING) P.O & Procurement | 2017-07-10 | 2018-01-05
Activity | 1PF2510W58A07T | (Steam PIPING) Transportation | 2018-01-06 | 2018-02-20
Activity | 1CF2510W58A08 | (Steam PIPING) Piping Work | 2018-03-21 | 2018-06-21
Activity | 1PF2510W42A09T | (Silencer) Transportation | 2018-03-22 | 2018-05-05
Activity | 1CF2510W74A10 | (Steam System) Installation & Test - Elec. | 2018-05-07 | 2018-08-01
Activity | 1CF2510W90A11 | (Steam System) Installation & Test - I&C | 2018-05-07 | 2018-08-01
Activity | 1CF2510W42A12 | (Silencer) Installation | 2018-05-07 | 2018-06-04
Activity | 1CF2510W62A13 | (Steam PIPING) Hydro Test | 2018-06-22 | 2018-07-23
Activity | 1SF2510W62A14 | (Steam System) Loop chek | 2018-08-02 | 2018-08-24
Activity | 1SF2510W62A15 | (Steam System) System Function Test | 2018-08-25 | 2018-09-03
Activity | 1SF2510W62A16 | (Steam System) System Service | 2018-09-04 | 2018-09-08
Activity | 1EF2510W00A17 | (Bypass System) P&ID & System Design | 2017-01-24 | 2017-08-25
Activity | 1EF2510W00A18 | (Bypass System) Bypass Valve, PRDS key data | 2017-01-24 | 2017-03-21
Activity | 1EF2510W42A19B | (Bypass Valve) MPS Issue |  | 2017-03-21
Activity | 1PF2510W42A20P | (Bypass Valve) P.O & Procurement | 2017-05-22 | 2018-05-04
Activity | 1PF2510W42A21T | (Bypass Valve) Transportation | 2018-05-05 | 2018-06-19
Activity | 1CF2510W58A25 | (Bypass System) Piping Work | 2018-06-20 | 2018-09-19
Activity | 1CF2510W90A22 | (Bypass System) Installation & Test - I&C | 2018-06-20 | 2018-08-20
Activity | 1CF2510W74A23 | (Bypass System) Installation & Test - Elec. | 2018-06-20 | 2018-08-20
Activity | 1CF2510W42A24 | (Bypass Valve) Installation | 2018-06-20 | 2018-08-20
Activity | 1CF2510W62A26 | (Bypass System) Hydro Test | 2018-09-20 | 2018-10-06
Activity | 1SF2510W62A27 | (Bypass System) Loop check | 2018-10-08 | 2018-10-23
Activity | 1SF2510W62A28 | (Bypass System) System Function Test | 2018-10-24 | 2018-11-02
Activity | 1SF2510W62A29 | (Bypass System) System Service | 2018-11-03 | 2018-11-07
Activity | 1EF2510W00A19 | (Aux. Steam System) P&ID & System Design | 2017-01-24 | 2017-08-25
Activity | 1EF2510W00A21 | (Aux. Steam System) Aux Steam Consumption Data | 2016-12-27 | 2017-02-13
Activity | 1EF2510W00A20 | (Aux. Steam System) Valve, PRDS key data | 2017-02-14 | 2017-04-12
Activity | 1EF2510W42A19B1 | (Aux. Steam System) MPS Issue |  | 2017-04-12
Activity | 1PF2510W42A20P1 | (Aux. Steam System) P.O & Procurement | 2017-07-13 | 2018-02-12
Activity | 1PF2510W42A21T1 | (Aux. Steam System) Transportation | 2018-02-13 | 2018-03-29
Activity | 1CF2510W58A34 | (Aux. Steam System) Piping Work | 2018-03-30 | 2018-06-29
Activity | 1CF2510W90A23 | (Aux. Steam System) Installation & Test - I&C | 2018-03-30 | 2018-05-30
Activity | 1CF2510W74A24 | (Aux. Steam System) Installation & Test - Elec. | 2018-03-30 | 2018-05-30
Activity | 1CF2510W42A25 | (Aux. Steam System) Installation | 2018-03-30 | 2018-05-30
Activity | 1SF2510W62A30 | (Aux. Steam System) Loop check | 2018-06-16 | 2018-07-02
Activity | 1SF2510W62A31 | (Aux. Steam System) System Function Test | 2018-07-26 | 2018-08-04
Activity | 1SF2510W62A32 | (Aux. Steam System) System Service | 2018-08-05 | 2018-08-09
Activity | 1EF3515W42A11 | (N2 Gas Bottle) MPS Issue |  | 2017-04-24
Activity | 1PF3515W42A01P | (N2 Gas Equip) P.O & Procurement | 2017-06-19 | 2018-02-15
Activity | 1EF3515W00A02 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2017-06-19
Activity | 1EF3515W32A03C | (N2 Gas Station Shelter) Shelter Design | 2017-06-19 | 2017-09-18
Activity | 1PF3515W42A04P | (N2 Gas Bottle) P.O & Procurement | 2017-07-10 | 2018-03-08
Activity | 1CF3515W16A05 | (N2 Gas Station Shelter) FDN Work | 2017-09-19 | 2017-11-15
Activity | 1CF3515W32A06 | (N2 Gas Station Shelter) Shelter Work | 2017-11-16 | 2018-02-24
Activity | 1PF3515W42A07T | (N2 Gas Equip) Transportation | 2018-02-16 | 2018-03-26
Activity | 1PF3515W42A08T | (N2 Gas Bottle) Transportation | 2018-03-09 | 2018-04-16
Activity | 1CF3515W42A09 | (N2 Gas Equip) Installation | 2018-03-27 | 2018-04-26
Activity | 1CF3515W42A10 | (N2 Gas Bottle) Installation (90 bottle) | 2018-04-27 | 2018-05-02
Activity | 0EF6020W00A18 | (BOP Piping) Pipe Arrangement | 2017-01-09 | 2018-08-24
Activity | 0EF6020W00A19 | (BOP Piping) Valve List | 2017-01-09 | 2017-09-14
Activity | 0EF6020W00A20 | (BOP Piping) Pipe Material Specification | 2017-01-23 | 2017-12-20
Activity | 0EF6020W00A21 | (BOP Piping) Piping Isometric Drawing | 2017-01-27 | 2017-12-20
Activity | 0EF6020W00A22 | (BOP Piping) Piping Insulation Specification | 2017-02-22 | 2017-12-20
Activity | 0EF6020W58A25 | (Piping) MPS Issue |  | 2017-05-26
Activity | 0PF6020W58A27P | (Piping) P.O & Procurement | 2017-06-27 | 2018-02-26
Activity | 0PF6020W58A29T | (Piping) Transportation | 2017-10-27 | 2018-04-27
Activity | 0PF6020W58A31T | (Piping) 1st Delivery on site_Transportation |  | 2017-12-12
Activity | 0PF6020W58A33T | (Piping) 2nd Delivery on site_Transportation |  | 2018-02-23
Activity | 0PF6020W58A34T | (Piping) 3rd Delivery on site_Transportation |  | 2018-04-27
Activity | 0EF6020W46A23 | (Hanger & Support & Fitting) MPS Issue |  | 2017-07-21
Activity | 0PF6020W46A26P | (Hanger & Support & Fitting) P.O & Procurement | 2017-09-07 | 2018-02-22
Activity | 0PF6020W46A30T | (Hanger & Support & Fitting) Transportation | 2018-02-23 | 2018-04-09
Activity | 0EF6050W86A12B | (Manual Valve) MPS Issue |  | 2017-08-25
Activity | 0PF6050W86A13P | (Manual Valve) P.O & Procurement | 2017-10-20 | 2018-03-29
Activity | 0PF6050W86A14T | (Manual Valve) Transportation | 2018-03-30 | 2018-05-14
Activity | 0EF6050W00A19 | (Safety Valve) Key Data | 2017-01-24 | 2017-04-10
Activity | 0EF6050W86A20B | (Safety Valve) MPS Issue |  | 2017-04-10
Activity | 0PF6050W86A21P | (Safety Valve) P.O & Procurement | 2017-06-12 | 2018-02-19
Activity | 0PF6050W86A22T | (Safety Valve) Transportation | 2018-02-20 | 2018-04-05
Activity | 0EF6050W00A15 | (MOV) MOV Key Data | 2017-01-24 | 2017-04-10
Activity | 0EF6050W86A16B | (MOV) MPS Issue |  | 2017-04-10
Activity | 0PF6050W86A17P | (MOV) P.O & Procurement | 2017-06-01 | 2018-01-16
Activity | 0PF6050W86A18T | (MOV) Transportation | 2018-01-17 | 2018-03-02
Activity | 0EF7000W86A12B | (Control Valve) MPS Issue |  | 2017-03-09
Activity | 0PF7000W86A13P | (Control Valve) P.O & Procurement | 2017-06-12 | 2018-04-27
Activity | 0PF7000W86A14T | (Control Valve) 1st Delivery(On site) |  | 2018-01-25
Activity | 0PF7000W86A15T | (Control Valve) Transportation | 2018-04-28 | 2018-06-12
Activity | 0EF6020W52A24 | (Piping Insulation) MPS Issue |  | 2017-10-25
Activity | 0PF6020W52A28P | (Piping Insulation) P.O & Procurement | 2017-12-26 | 2018-04-27
Activity | 0PF6020W52A32T | (Piping Insulation) Transportation | 2018-04-28 | 2018-06-12
Activity | 1CF3030W58A12 | (Aux. Cooling System) Piping Work | 2018-06-06 | 2018-07-07
Activity | 1CF3030W62A13 | (Aux. Cooling System) Hydro Test | 2018-07-09 | 2018-07-24
Activity | 1CF3015W58A26 | (Feed water system) Piping Work(Block #2) | 2018-05-01 | 2018-06-30
Activity | 1CF3015W62A27 | (Feed water system) Hydro Test | 2018-07-02 | 2018-07-17
Activity | 1CF3015W52A28 | (Feed water system) Insulation Install | 2018-07-18 | 2018-08-02
Activity | 1CF3020W58A46 | (Condensate System) Piping Work(Block #2) | 2018-05-15 | 2018-06-30
Activity | 1CF3020W62A47 | (Condensate System) Hydro Test | 2018-07-02 | 2018-07-17
Activity | 1CF3020W52A48 | (Condensate System) Insulation Install | 2018-07-18 | 2018-08-02
Activity | 1CF2510W58A30 | (Steam System) Piping Work(Block #2) | 2018-05-26 | 2018-07-26
Activity | 1CF2510W62A31 | (Steam System) Hydro Test | 2018-07-27 | 2018-08-11
Activity | 1CF2510W52A32 | (Steam System) Insulation Install | 2018-08-13 | 2018-08-28
Activity | 1CF2510W58A33 | (Bypass System) Piping Work(Block #2) | 2018-05-26 | 2018-07-26
Activity | 1CF2510W62A34 | (Bypass System) Hydro Test | 2018-07-27 | 2018-08-11
Activity | 1CF2510W52A35 | (Bypass System) Insulation Install | 2018-08-13 | 2018-08-28
Activity | 1CF2515W58A01 | (Aux. Steam System) Piping Work(Block #2) | 2018-03-30 | 2018-05-30
Activity | 1CF2515W62A02 | (Aux. Steam System) Hydro Test | 2018-05-31 | 2018-06-15
Activity | 1CF2515W52A03 | (Aux. Steam System) Insulation Install | 2018-06-16 | 2018-07-02
Activity | 1CF3510W58A17 | (COMP Air System) Piping Work(incl. Air blowing)_Block #2 | 2018-04-24 | 2018-06-23
Activity | 1CF3510W62A18 | (COMP Air System) Hydro Test | 2018-06-25 | 2018-07-10
Activity | 1CF3030W58A44 | (Closed Cooling Water System) Piping Work(Block #2) | 2018-04-24 | 2018-06-21
Activity | 1CF3030W62A45 | (Closed Cooling Water System) Hydro Test | 2018-06-22 | 2018-07-07
Activity | 1CF3515W58A11 | (N2 Gas supply system) Piping Work(Block #2) | 2018-04-27 | 2018-06-27
Activity | 1CF3515W62A12 | (N2 Gas supply system) Hydro Test | 2018-06-28 | 2018-07-13
Activity | 1EF1600W00A03 | (HRSG #21/#22/#23) Instrument, Service Air Data | 2016-12-08 | 2017-01-05
Activity | 1EF1600W00A04 | (HRSG #21/#22/#23) Utility Consumption Data | 2016-12-08 | 2017-02-02
Activity | 1EF1600W00A05 | (HRSG #21/#22/#23) Emergency Load Data | 2016-12-08 | 2017-01-23
Activity | 1EF1600W00A01 | (HRSG #21/#22/#23) P&ID & System Design | 2016-12-08 | 2017-11-27
Activity | 1EF1600W00A02 | (HRSG #21/#22/#23) HRSG Process, GA Data | 2016-12-08 | 2017-01-05
Activity | 1EF1610W20A02C | (HRSG #21 S/Structure & Casing) Design | 2016-12-08 | 2017-07-06
Activity | 1EF1610W20A01B | (HRSG #21 S/Structure & Casing) MPS Issue |  | 2016-12-09
Activity | 1PF1610W20A05P | (HRSG #21 S/Structure & Casing) P.O & Procurement | 2017-01-20 | 2017-11-15
Activity | 1EF1610W00A03 | (HRSG #21 S/Structure & Casing) GA & Load Data to Civil Design | 2017-04-07
Activity | 1EF1610W16A06C | (HRSG #21 S/Structure & Casing) FDN Design | 2017-06-07 | 2017-08-25
Activity | 1CF1610W16A07 | (HRSG #21 S/Structure & Casing) FDN Work | 2017-08-26 | 2017-10-25
Activity | 1PF1610W20A08T | (HRSG #21 S/Structure & Casing) Transportation | 2017-11-16 | 2017-12-15
Activity | 1CF1610W20A09 | (HRSG #21 S/Structure & Casing) S/Structure Installation | 2017-12-16 | 2018-01-15
Activity | 1CF1610W20A10 | (HRSG #21 S/Structure & Casing) Casing Installation | 2018-01-16 | 2018-03-08
Activity | 1EF1610W42A11B | (HRSG #21 Module) MPS Issue |  | 2016-12-09
Activity | 1PF1610W42A12P | (HRSG #21 Module) P.O & Procurement | 2017-01-20 | 2017-12-15
Activity | 1PF1610W42A13T | (HRSG #21 Module) Transportation | 2017-12-16 | 2018-01-16
Activity | 1CF1610W42A14 | (HRSG #21 Module) Installation | 2018-03-09 | 2018-03-17
Activity | 1EF1645W42A01C | (HRSG #21 Drum) Design | 2016-12-08 | 2017-06-29
Activity | 1EF1645W42A02B | (HRSG #21 Drum) MPS Issue |  | 2016-12-09
Activity | 1PF1645W42A03P | (HRSG #21 Drum) P.O & Procurement | 2017-01-20 | 2018-01-15
Activity | 1PF1645W42A04T | (HRSG #21 Drum) Transportation | 2018-01-16 | 2018-02-15
Activity | 1CF1645W42A05 | (HRSG #21 Drum) Installation | 2018-03-19 | 2018-03-24
Activity | 1EF1615W64A01C | (HRSG #21 Duct) Design | 2016-12-08 | 2017-06-12
Activity | 1EF1615W64A02B | (HRSG #21 EXP Joint & Bellows) MPS Issue |  | 2016-12-09
Activity | 1EF1615W64A04B | (HRSG #21 Duct) MPS Issue |  | 2016-12-09
Activity | 1PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | 2017-01-20 | 2017-11-15
Activity | 1PF1615W64A05P | (HRSG #21 EXP Joint & Bellows) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 1EF1615W00A03 | (HRSG #21 Duct) GA & Load Data to Civil Design | 2017-04-07
Activity | 1EF1615W16A07C | (HRSG #21 Duct) FDN Design | 2017-06-07 | 2017-08-25
Activity | 1CF1615W16A08 | (HRSG #21 Duct) FDN Work | 2017-08-26 | 2017-10-25
Activity | 1PF1615W64A09T | (HRSG #21 Duct) Transportation | 2017-11-16 | 2017-12-23
Activity | 1PF1615W64A10T | (HRSG #21 EXP Joint & Bellows) Transportation | 2018-02-16 | 2018-04-02
Activity | 1CF1615W64A11 | (HRSG #21 Duct) Duct Installation | 2018-03-26 | 2018-06-29
Activity | 1CF1615W64A12 | (HRSG #21 Damper) Installation | 2018-04-30 | 2018-06-29
Activity | 1CF1615W64A13 | (HRSG #21 EXP Joint & Bellows) Installation | 2018-05-15 | 2018-06-29
Activity | 1EF1615W64A14B | (HRSG #21 Damper) MPS Issue |  | 2016-12-09
Activity | 1PF1615W64A15P | (HRSG #21 Damper) P.O & Procurement | 2017-01-20 | 2017-12-15
Activity | 1PF1615W64A16T | (HRSG #21 Damper) Transportation | 2017-12-16 | 2018-01-30
Activity | 1CF1615W64A17 | (HRSG #21) Installation_Diverter Damper | 2018-05-29 | 2018-06-05
Activity | 1CF1615W64A18 | (HRSG #21) Installation_Guillotine Damper | 2018-06-06 | 2018-06-12
Activity | 1CF1615W86A19 | (HRSG #21) Installation_Diverter Damper Control Unit | 2018-06-06 | 2018-06-09
Activity | 1CF1615W62A20 | (HRSG #21) Diverter Damper Control Unit Flushing | 2018-06-11 | 2018-06-19
Activity | 1SF1615W62A21 | (HRSG #21) Diverter Damper Function Test for HRSG #21 | 2018-06-20 | 2018-06-22
Activity | 1SF1615W62A22 | (HRSG #21) Guillotine Damper Function Test for HRSG #21 | 2018-06-20 | 2018-06-22
Activity | 1EF1625W42A02C | (HRSG #21 Main Stack) Design | 2016-12-08 | 2017-06-21
Activity | 1EF1625W42A01B | (HRSG #21 Main Stack) MPS Issue |  | 2016-12-09
Activity | 1EF1625W42A03B | (HRSG #21 Main Stack Silencer) MPS Issue |  | 2016-12-09
Activity | 1PF1625W42A06P | (HRSG #21 Main Stack Silencer) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 1PF1625W42A04P | (HRSG #21 Main Stack) P.O & Procurement | 2017-01-20 | 2017-11-15
Activity | 1EF1625W00A05 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | 2017-04-07
Activity | 1EF1625W16A07C | (HRSG #21 Main Stack) FDN Design | 2017-06-07 | 2017-08-25
Activity | 1CF1625W16A08 | (HRSG #21 Main Stack) FDN Work | 2017-08-26 | 2017-10-25
Activity | 1PF1625W42A09T | (HRSG #21 Main Stack) Transportation | 2017-11-16 | 2017-12-30
Activity | 1PF1625W42A10T | (HRSG #21 Main Stack Silencer) Transportation | 2018-02-16 | 2018-04-02
Activity | 1CF1625W42A11 | (HRSG #21 Main Stack) Installation | 2018-03-26 | 2018-06-29
Activity | 1CF1625W42A12 | (HRSG #21 Main Stack Silencer) Installation | 2018-06-04 | 2018-07-02
Activity | 1EF1650W52A01B | (HRSG #21 Insulation) MPS Issue |  | 2016-12-09
Activity | 1PF1650W52A02P | (HRSG #21 Insulation) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 1PF1650W52A03T | (HRSG #21 Insulation) Transportation | 2018-02-16 | 2018-04-02
Activity | 1CF1640W58A05 | (HRSG #21) Piping Work | 2018-03-26 | 2018-06-29
Activity | 1CF1640W62A06 | (HRSG #21) Hydro Test | 2018-07-05 | 2018-07-14
Activity | 1CF1650W52A04 | (HRSG #21 Insulation) Installation | 2018-07-16 | 2018-08-14
Activity | 1CF1640W60A07 | (HRSG #21) Acid Cleaning | 2018-08-10 | 2018-08-18
Activity | 1EF1660W86A03B | (CEMS #21) MPS Issue |  | 2016-12-09
Activity | 1PF1660W86A04P | (CEMS #21) P.O & Procurement | 2017-01-20 | 2018-02-14
Activity | 1EF1660W16A01C | (CEMS #21) FDN Design | 2017-06-07 | 2017-08-25
Activity | 1CF1660W16A02 | (CEMS #21) FDN Work | 2017-08-26 | 2017-10-25
Activity | 1PF1660W86A05T | (CEMS #21) Transportation | 2018-02-16 | 2018-04-02
Activity | 1CF1660W86A06 | (CEMS #21) Installation(incl. Elec, I&C) | 2018-06-30 | 2018-07-16
Activity | 1CF1660W62A07 | (CEMS #21) Loop Test | 2018-07-17 | 2018-07-21
Activity | 1SF1660W62A08 | (CEMS #21) CEMS Function Test for HRSG #21(Main stack) | 2018-07-22 | 2018-07-27
Activity | 1EF1665W42A01B | (HRSG #21 MECH Vendor Equip) MPS Issue |  | 2016-12-09
Activity | 1EF1660W86A10B | (HRSG #21 I&C Vendor Equip) MPS Issue |  | 2016-12-09
Activity | 1EF1655W70A05B | (HRSG #21 ELEC Vendor Equip) MPS Issue |  | 2016-12-09
Activity | 1PF1665W42A02P | (HRSG #21 MECH Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 1PF1660W86A11P | (HRSG #21 I&C Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 1PF1655W70A06P | (HRSG #21 ELEC Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 1PF1655W70A07T | (HRSG #21 ELEC Vendor Equip) Transportation | 2018-02-16 | 2018-04-02
Activity | 1PF1665W42A03T | (HRSG #21 MECH Vendor Equip) Transportation | 2018-02-16 | 2018-04-02
Activity | 1PF1660W86A12T | (HRSG #21 I&C Vendor Equip) Transportation | 2018-02-16 | 2018-04-02
Activity | 1CF1655W70A08 | (HRSG #21 ELEC Vendor Equip) Installation | 2018-04-03 | 2018-05-30
Activity | 1CF1665W42A04 | (HRSG #21 MECH Vendor Equip) Installation | 2018-04-03 | 2018-05-19
Activity | 1CF1660W86A13 | (HRSG #21 I&C Vendor Equip) Installation | 2018-04-03 | 2018-05-30
Activity | 1CF1660W90A14 | (HRSG #21) Installation & Test - I&C | 2018-04-24 | 2018-06-08
Activity | 1CF1655W74A09 | (HRSG #21) Installation & Test - Elec. | 2018-04-24 | 2018-06-08
Activity | 1SF1600W62A01 | (HRSG #21) Cold Commissioning for HRSG #21 | 2018-09-09 | 2018-09-28
Activity | 1SF1600W62A02 | (HRSG #21) Function Test for HRSG #21 | 2018-09-29 | 2018-10-13
Activity | 1SF1600W62A03 | (HRSG #21) Steam Blowing for HRSG #21 | 2018-10-14 | 2018-11-02
Activity | 1SF1600W62A04 | (HRSG #21) Temporary Piping Restoration for HRSG #21 | 2018-11-03 | 2018-11-13
Activity | 2EF1610W20A02C | (HRSG #22 S/Structure & Casing) Design | 2016-12-08 | 2017-07-06
Activity | 2EF1610W20A01B | (HRSG #22 S/Structure & Casing) MPS Issue |  | 2016-12-09
Activity | 2PF1610W20A04P | (HRSG #22 S/Structure & Casing) P.O & Procurement | 2017-01-20 | 2017-11-29
Activity | 2EF1610W00A03 | (HRSG #22 S/Structure & Casing) GA & Load Data to Civil Design | 2017-04-07
Activity | 2EF1610W16A05C | (HRSG #22 S/Structure & Casing) FDN Design | 2017-06-07 | 2017-08-25
Activity | 2CF1610W16A06 | (HRSG #22 S/Structure & Casing) FDN Work | 2017-09-13 | 2017-11-11
Activity | 2PF1610W20A07T | (HRSG #22 S/Structure & Casing) Transportation | 2017-11-30 | 2017-12-28
Activity | 2CF1610W20A08 | (HRSG #22 S/Structure & Casing) S/Structure Installation | 2017-12-30 | 2018-01-30
Activity | 2CF1610W20A09 | (HRSG #22 S/Structure & Casing) Casing Installation | 2018-01-31 | 2018-03-22
Activity | 2EF1610W42A10B | (HRSG #22 Module) MPS Issue |  | 2016-12-09
Activity | 2PF1610W42A11P | (HRSG #22 Module) P.O & Procurement | 2017-01-20 | 2017-12-29
Activity | 2PF1610W42A12T | (HRSG #22 Module) Transportation | 2017-12-30 | 2018-02-06
Activity | 2CF1610W42A13 | (HRSG #22 Module) Installation | 2018-03-23 | 2018-04-02
Activity | 2EF1645W42A01C | (HRSG #22 Drum) Design | 2016-12-08 | 2017-06-30
Activity | 2EF1645W42A02B | (HRSG #22 Drum) MPS Issue |  | 2016-12-09
Activity | 2PF1645W42A03P | (HRSG #22 Drum) P.O & Procurement | 2017-01-20 | 2018-01-30
Activity | 2PF1645W42A04T | (HRSG #22 Drum) Transportation | 2018-01-31 | 2018-03-09
Activity | 2CF1645W42A05 | (HRSG #22 Drum) Installation | 2018-04-03 | 2018-04-09
Activity | 2EF1615W64A01C | (HRSG #22 Duct) Design | 2016-12-08 | 2017-06-12
Activity | 2EF1615W64A03B | (HRSG #22 Duct) MPS Issue |  | 2016-12-09
Activity | 2EF1665W64A13.1 | (HRSG #22 EXP Joint & Bellows) MPS Issue |  | 2016-12-09
Activity | 2PF1615W64A04P | (HRSG #22 Duct) P.O & Procurement | 2017-01-20 | 2017-11-29
Activity | 2PF1665W64A14.1P | (HRSG #22 EXP Joint & Bellows) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2EF1615W00A02 | (HRSG #22 Duct) GA & Load Data to Civil Design | 2017-04-07
Activity | 2EF1615W16A05C | (HRSG #22 Duct) FDN Design | 2017-06-07 | 2017-08-25
Activity | 2CF1615W16A06 | (HRSG #22 Duct) FDN Work | 2017-09-13 | 2017-11-11
Activity | 2PF1615W64A07T | (HRSG #22 Duct) Transportation | 2017-11-30 | 2018-01-06
Activity | 2PF1665W64A15.1T | (HRSG #22 EXP Joint & Bellows) Transportation | 2018-02-28 | 2018-04-13
Activity | 2CF1615W64A08 | (HRSG #22 Duct) Duct Installation | 2018-04-10 | 2018-07-14
Activity | 2CF1615W64A09 | (HRSG #22 Damper) Installation | 2018-05-15 | 2018-07-14
Activity | 2CF1665W64A16.1 | (HRSG #22 EXP Joint & Bellows) Installation | 2018-05-30 | 2018-07-14
Activity | 2EF1615W64A10B | (HRSG #22 Damper) MPS Issue |  | 2016-12-09
Activity | 2PF1615W64A11P | (HRSG #22 Damper) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2PF1615W64A12T | (HRSG #22 Damper) Transportation | 2018-02-28 | 2018-04-13
Activity | 2CF1615W64A13 | (HRSG #22) Installation_Diverter Damper | 2018-06-28 | 2018-07-05
Activity | 2CF1615W64A14 | (HRSG #22) Installation_Guillotine Damper | 2018-07-06 | 2018-07-12
Activity | 2CF1615W86A15 | (HRSG #22) Installation_Diverter Damper Control Unit | 2018-07-06 | 2018-07-10
Activity | 2CF1615W62A16 | (HRSG #22) Diverter Damper Control Unit Flushing | 2018-07-11 | 2018-07-19
Activity | 2SF1615W62A17 | (HRSG #22) Diverter Damper Function Test for HRSG #22 | 2018-07-20 | 2018-07-22
Activity | 2SF1615W62A18 | (HRSG #22) Guillotine Damper Function Test for HRSG #22 | 2018-07-20 | 2018-07-22
Activity | 2EF1625W42A02C | (HRSG #22 Main Stack) Design | 2016-12-08 | 2017-06-21
Activity | 2EF1625W42A03B | (HRSG #22 Main Stack Silencer) MPS Issue |  | 2016-12-09
Activity | 2EF1625W42A01B | (HRSG #22 Main Stack) MPS Issue |  | 2016-12-09
Activity | 2PF1625W42A06P | (HRSG #22 Main Stack Silencer) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2PF1625W42A04P | (HRSG #22 Main Stack) P.O & Procurement | 2017-01-20 | 2017-11-29
Activity | 2EF1625W00A05 | (HRSG #22 Main Stack) GA & Load Data to Civil Design | 2017-04-07
Activity | 2EF1625W16A07C | (HRSG #22 Main Stack) FDN Design | 2017-06-07 | 2017-08-25
Activity | 2CF1625W16A08 | (HRSG #22 Main Stack) FDN Work | 2017-09-13 | 2017-11-11
Activity | 2PF1625W42A09T | (HRSG #22 Main Stack) Transportation | 2017-11-30 | 2018-01-13
Activity | 2PF1625W42A10T | (HRSG #22 Main Stack Silencer) Transportation | 2018-02-28 | 2018-04-13
Activity | 2CF1625W42A11 | (HRSG #22 Main Stack) Installation | 2018-04-10 | 2018-07-14
Activity | 2CF1625W42A12 | (HRSG #22 Main Stack Silencer) Installation | 2018-06-19 | 2018-07-17
Activity | 2EF1650W52A01B | (HRSG #22 Insulation) MPS Issue |  | 2016-12-09
Activity | 2PF1650W52A02P | (HRSG #22 Insulation) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2PF1650W52A03T | (HRSG #22 Insulation) Transportation | 2018-02-28 | 2018-04-13
Activity | 2CF1640W58A05 | (HRSG #22) Piping Work | 2018-04-10 | 2018-07-14
Activity | 2CF1640W62A06 | (HRSG #22) Hydro Test | 2018-07-16 | 2018-07-25
Activity | 2CF1650W52A04 | (HRSG #22 Insulation) Installation | 2018-07-26 | 2018-08-24
Activity | 2CF1640W60A07 | (HRSG #22)Acid Cleaning | 2018-08-16 | 2018-08-24
Activity | 2EF1660W86A03B | (CEMS #22) MPS Issue |  | 2016-12-09
Activity | 2PF1660W86A04P | (CEMS #22) P.O & Procurement | 2017-01-20 | 2018-02-26
Activity | 2EF1660W16A01C | (CEMS #22) FDN Design | 2017-06-07 | 2017-08-25
Activity | 2CF1660W16A02 | (CEMS #22) FDN Work | 2017-09-13 | 2017-11-11
Activity | 2PF1660W86A05T | (CEMS #22) Transportation | 2018-02-28 | 2018-04-13
Activity | 2CF1660W86A06 | (CEMS #22) Installation(incl. Elec, I&C) | 2018-07-16 | 2018-07-31
Activity | 2CF1660W86A07 | (CEMS #22) Loop Test | 2018-08-01 | 2018-08-06
Activity | 2SF1660W62A08 | (CEMS #22) CEMS Function Test for HRSG #22(Main stack) | 2018-08-07 | 2018-08-12
Activity | 2EF1660W86A06B | (HRSG #22 I&C Vendor Equip) MPS Issue |  | 2016-12-09
Activity | 2EF1665W42A11B | (HRSG #22 MECH Vendor Equip) MPS Issue |  | 2016-12-09
Activity | 2EF1655W70A01B | (HRSG #22 ELEC Vendor Equip) MPS Issue |  | 2016-12-09
Activity | 2PF1660W86A07P | (HRSG #22 I&C Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2PF1665W42A12P | (HRSG #22 MECH Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2PF1655W70A02P | (HRSG #22 ELEC Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-02-27
Activity | 2PF1655W70A03T | (HRSG #22 ELEC Vendor Equip) Transportation | 2018-02-28 | 2018-04-13
Activity | 2PF1660W86A08T | (HRSG #22 I&C Vendor Equip) Transportation | 2018-02-28 | 2018-04-13
Activity | 2PF1665W42A13T | (HRSG #22 MECH Vendor Equip) Transportation | 2018-02-28 | 2018-04-13
Activity | 2CF1655W70A04 | (HRSG #22 ELEC Vendor Equip) Installation | 2018-04-14 | 2018-08-08
Activity | 2CF1660W86A09 | (HRSG #22 I&C Vendor Equip) Installation | 2018-04-14 | 2018-08-08
Activity | 2CF1665W42A14 | (HRSG #22 MECH Vendor Equip) Installation | 2018-04-14 | 2018-07-28
Activity | 2CF1660W90A10 | (HRSG #22) Installation & Test - I&C | 2018-05-09 | 2018-08-09
Activity | 2CF1655W74A05 | (HRSG #22) Installation & Test - Elec. | 2018-05-09 | 2018-08-09
Activity | 2SF1600W62A01 | (HRSG #22) Cold Commissioning for HRSG #22 | 2018-09-09 | 2018-09-28
Activity | 2SF1600W62A02 | (HRSG #22) Function Test for HRSG #22 | 2018-09-29 | 2018-10-13
Activity | 2SF1600W62A03 | (HRSG #22) Steam Blowing for HRSG #22 | 2018-10-14 | 2018-11-02
Activity | 2SF1600W62A04 | (HRSG #22) Temporary Piping Restoration for HRSG #22 | 2018-11-03 | 2018-11-13
Activity | 3EF1610W20A01C | (HRSG #23 S/Structure & Casing) Design | 2016-12-08 | 2017-07-06
Activity | 3EF1610W20A02B | (HRSG #23 S/Structure & Casing) MPS Issue |  | 2016-12-09
Activity | 3PF1610W20A04P | (HRSG #23 S/Structure & Casing) P.O & Procurement | 2017-01-20 | 2017-12-14
Activity | 3EF1610W00A03 | (HRSG #23 S/Structure & Casing) GA & Load Data to Civil Design | 2017-04-07
Activity | 3EF1610W16A05C | (HRSG #23 S/Structure & Casing) FDN Design | 2017-06-07 | 2017-08-25
Activity | 3CF1610W16A06 | (HRSG #23 S/Structure & Casing) FDN Work | 2017-09-30 | 2017-11-29
Activity | 3PF1610W20A07T | (HRSG #23 S/Structure & Casing) Transportation | 2017-12-15 | 2018-01-15
Activity | 3CF1610W20A08 | (HRSG #23 S/Structure & Casing) S/Structure Installation | 2018-01-16 | 2018-02-15
Activity | 3CF1610W20A09 | (HRSG #23 S/Structure & Casing) Casing Installation | 2018-02-16 | 2018-04-06
Activity | 3PF1610W42A10B | (HRSG #23 Module) MPS Issue |  | 2016-12-09
Activity | 3PF1610W42A11P | (HRSG #23 Module) P.O & Procurement | 2017-01-20 | 2018-01-15
Activity | 3PF1610W42A12T | (HRSG #23 Module) Transportation | 2018-01-16 | 2018-02-22
Activity | 3CF1610W42A13 | (HRSG #23 Module) Installation | 2018-04-07 | 2018-04-17
Activity | 3EF1645W42A01C | (HRSG #23 Drum) Design | 2016-12-08 | 2017-06-30
Activity | 3PF1645W42A02B | (HRSG #23 Drum) MPS Issue |  | 2016-12-09
Activity | 3PF1645W42A03P | (HRSG #23 Drum) P.O & Procurement | 2017-01-20 | 2018-02-15
Activity | 3PF1645W42A04T | (HRSG #23 Drum) Transportation | 2018-02-16 | 2018-03-26
Activity | 3CF1645W42A05 | (HRSG #23 Drum) Installation | 2018-04-18 | 2018-04-24
Activity | 3EF1615W64A01C | (HRSG #23 Duct) Design | 2016-12-08 | 2017-06-12
Activity | 3PF1615W64A04P | (HRSG #23 Duct) P.O & Procurement | 2017-01-20 | 2017-12-14
Activity | 3PF1615W64A03P | (HRSG #23 EXP Joint & Bellows) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3EF1615W00A02 | (HRSG #23 Duct) GA & Load Data to Civil Design | 2017-04-07
Activity | 3EF1615W16A05C | (HRSG #23 Duct) FDN Design | 2017-06-07 | 2017-08-25
Activity | 3CF1615W16A06 | (HRSG #23 Duct) FDN Work | 2017-08-26 | 2017-10-25
Activity | 3PF1615W64A07T | (HRSG #23 Duct) Transportation | 2017-12-15 | 2018-01-22
Activity | 3CF1615W64A10 | (HRSG #23 Damper) Installation | 2018-03-02 | 2018-05-02
Activity | 3PF1615W64A08T | (HRSG #23 EXP Joint & Bellows) Transportation | 2018-03-15 | 2018-04-28
Activity | 3CF1615W64A09 | (HRSG #23 Duct) Duct Installation | 2018-04-25 | 2018-07-30
Activity | 3CF1615W64A11 | (HRSG #23 EXP Joint & Bellows) Installation | 2018-06-14 | 2018-07-30
Activity | 3EF1615W64A12B | (HRSG #23 Damper) MPS Issue |  | 2016-12-09
Activity | 3PF1615W64A13P | (HRSG #23 Damper) P.O & Procurement | 2017-01-20 | 2018-01-15
Activity | 3PF1615W64A14T | (HRSG #23 Damper) Transportation | 2018-01-16 | 2018-03-01
Activity | 3CF1615W64A15 | (HRSG #23) Installation_Diverter Damper | 2018-07-28 | 2018-08-04
Activity | 3CF1615W64A16 | (HRSG #23) Installation_Guillotine Damper | 2018-08-06 | 2018-08-11
Activity | 3CF1615W86A17 | (HRSG #23) Installation_Diverter Damper Control Unit | 2018-08-06 | 2018-08-09
Activity | 3CF1615W62A18 | (HRSG #23) Diverter Damper Control Unit Flushing | 2018-08-10 | 2018-08-18
Activity | 3SF1615W62A19 | (HRSG #23) Diverter Damper Function Test for HRSG #23 | 2018-08-19 | 2018-08-21
Activity | 3SF1615W62A20 | (HRSG #23) Guillotine Damper Function Test for HRSG #23 | 2018-08-19 | 2018-08-21
Activity | 3EF1625W42A01C | (HRSG #23 Main Stack) Design | 2016-12-08 | 2017-06-21
Activity | 3PF1625W42A02P | (HRSG #23 Main Stack) P.O & Procurement | 2017-01-20 | 2017-12-14
Activity | 3PF1625W42A04P | (HRSG #23 Main Stack Silencer) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3EF1625W00A03 | (HRSG #23 Main Stack) GA & Load Data to Civil Design | 2017-04-07
Activity | 3EF1625W16A05C | (HRSG #23 Main Stack) FDN Design | 2017-06-07 | 2017-08-25
Activity | 3CF1625W16A06 | (HRSG #23 Main Stack) FDN Work | 2017-08-26 | 2017-10-25
Activity | 3PF1625W42A07T | (HRSG #23 Main Stack) Transportation | 2017-12-15 | 2018-01-29
Activity | 3PF1625W42A08T | (HRSG #23 Main Stack Silencer) Transportation | 2018-03-15 | 2018-04-28
Activity | 3CF1625W42A09 | (HRSG #23 Main Stack) Installation | 2018-04-25 | 2018-07-30
Activity | 3CF1625W42A10 | (HRSG #23 Main Stack Silencer) Installation | 2018-07-04 | 2018-08-01
Activity | 3PF1650W52A02P | (HRSG #23 Insulation) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3PF1650W52A03T | (HRSG #23 Insulation) Transportation | 2018-03-15 | 2018-04-28
Activity | 3CF1640W58A05 | (HRSG #23) Piping Work | 2018-04-25 | 2018-07-30
Activity | 3CF1640W62A06 | (HRSG #23) Hydro Test | 2018-07-31 | 2018-08-09
Activity | 3CF1650W52A04 | (HRSG #23 Insulation) Installation | 2018-08-10 | 2018-09-08
Activity | 3CF1640W60A07 | (HRSG #23) Acid Cleaning | 2018-08-31 | 2018-09-08
Activity | 3PF1660W86A04P | (CEMS #23) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3EF1660W16A01C | (CEMS #23) FDN Design | 2017-06-07 | 2017-08-25
Activity | 3CF1660W16A02 | (CEMS #23) FDN Work | 2017-08-26 | 2017-10-25
Activity | 3PF1660W86A05T | (CEMS #23) Transportation | 2018-03-15 | 2018-04-28
Activity | 3CF1660W86A06 | (CEMS #23) Installation(incl. Elec, I&C) | 2018-07-14 | 2018-07-30
Activity | 3CF1660W62A07 | (CEMS #23) Loop Test | 2018-07-31 | 2018-08-04
Activity | 3SF1660W62A08 | (CEMS #23) CEMS Function Test for HRSG #23(Main stack) | 2018-08-19 | 2018-08-24
Activity | 3PF1665W42A02P | (HRSG #23 MECH Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3PF1655W70A06P | (HRSG #23 ELEC Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3PF1660W86A11P | (HRSG #23 I&C Vendor Equip) P.O & Procurement | 2017-01-20 | 2018-03-14
Activity | 3PF1655W70A07T | (HRSG #23 ELEC Vendor Equip) Transportation | 2018-03-15 | 2018-04-28
Activity | 3PF1660W86A12T | (HRSG #23 I&C Vendor Equip) Transportation | 2018-03-15 | 2018-04-28
Activity | 3PF1665W42A03T | (HRSG #23 MECH Vendor Equip) Transportation | 2018-03-15 | 2018-04-28
Activity | 3CF1665W42A04 | (HRSG #23 MECH Vendor Equip) Installation | 2018-04-30 | 2018-08-13
Activity | 3CF1655W70A08 | (HRSG #23 ELEC Vendor Equip) Installation | 2018-04-30 | 2018-08-23
Activity | 3CF1660W86A13 | (HRSG #23 I&C Vendor Equip) Installation | 2018-04-30 | 2018-08-23
Activity | 3CF1655W74A09 | (HRSG #23) Installation & Test - Elec. | 2018-05-24 | 2018-08-24
Activity | 3CF1660W90A14 | (HRSG #23) Installation & Test - I&C | 2018-05-24 | 2018-08-24
Activity | 3SF1600W62A01 | (HRSG #23) Cold Commissioning for HRSG #23 | 2018-09-09 | 2018-09-28
Activity | 3SF1600W62A02 | (HRSG #23) Function Test for HRSG #23 | 2018-09-29 | 2018-10-13
Activity | 3SF1600W62A03 | (HRSG #23) Steam Blowing for HRSG #23 | 2018-10-14 | 2018-11-02
Activity | 3SF1600W62A04 | (HRSG #23) Temporary Piping Restoration for HRSG #23 | 2018-11-03 | 2018-11-13
Activity | 1PF2010W20A04P | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | 2017-03-01 | 2017-08-08
Activity | 1EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | 2016-12-08
Activity | 1EF2010W20A02C | (STG #20 BLDG) Buliding Design | 2016-12-08 | 2017-06-13
Activity | 1CF2010W16A03 | (STG #20 BLDG) FDN Work | 2017-06-21 | 2017-10-18
Activity | 1PF2010W20A05T | (STG #20 BLDG) Transportation - Structure Work(S/S) | 2017-08-09 | 2017-09-08
Activity | 1CF2010W20A06 | (STG #20 BLDG) Structure Work(S/S) | 2017-09-14 | 2018-01-19
Activity | 1CF2010W20A07 | (STG #20 BLDG) Cladding Work | 2017-11-15 | 2018-03-21
Activity | 1CF2010W20A08 | (STG #20 BLDG) Roof Work | 2017-12-18 | 2018-03-21
Activity | 1CF2010W74A11 | (STG #20 BLDG) Installation & Test - Elec | 2018-03-22 | 2018-06-11
Activity | 1CF2010W90A12 | (STG #20 BLDG) Installation & Test - I&C | 2018-03-22 | 2018-06-11
Activity | 1CF2010W36A10 | (STG #20 BLDG) Installation & Test - HVAC | 2018-03-27 | 2018-05-23
Activity | 1CF2010W38A09 | (STG #20 BLDG) Installation & Test - Fire Fighting Sys. | 2018-06-15 | 2018-08-11
Activity | 1EF2020W00A01 | (ST #20) ST Process Data | 2016-12-08 | 2017-01-06
Activity | 1EF2020W00A02 | (ST #20) ST Aux' Steam Consumption Data | 2016-12-08 | 2017-01-05
Activity | 1EF2020W00A03 | (ST #20) Instrument, Service Air Data | 2016-12-08 | 2017-01-05
Activity | 1EF2020W00A04 | (ST #20) Utility Consumption Data | 2016-12-08 | 2017-02-02
Activity | 1EF2020W00A05 | (ST #20) Emergency Load Data | 2016-12-08 | 2017-01-23
Activity | 1EF2020W42A09B | (ST #20) MPS Issue |  | 2016-12-08
Activity | 1PF2020W42A10P | (ST #20) P.O & Procurement | 2017-02-07 | 2018-03-02
Activity | 1EF2020W16A06C | (ST #20) FDN Design | 2017-03-21 | 2017-06-20
Activity | 1CF2020W16A07 | (ST #20) FDN Work | 2017-06-21 | 2017-09-21
Activity | 1CF2020W16A08 | (ST #20) Pedestal & Top Slab Work | 2017-09-22 | 2018-02-08
Activity | 1PF2020W42A11T | (ST #20) Transportation | 2018-03-03 | 2018-04-30
Activity | 1CF2020W42A13 | (ST #20) Placing of Turbine Package | 2018-05-01 | 2018-05-07
Activity | 1CF2020W42A14 | (ST #20) Placing of Turbine Bottom Half | 2018-05-08 | 2018-05-23
Activity | 1CF2020W42A15 | (ST #20) Placing of Turbine Top Half | 2018-05-24 | 2018-05-30
Activity | 1CF2020W42A16 | (ST #20) Alignment of Turbine and Generator | 2018-06-06 | 2018-06-14
Activity | 1CF2020W42A17 | (ST #20) Final Alingment of couplings | 2018-08-29 | 2018-09-08
Activity | 1EF2040W42A01B | (STG #20) MPS Issue |  | 2016-12-08
Activity | 1PF2040W42A02P | (STG #20) P.O & Procurement | 2017-02-07 | 2018-03-02
Activity | 1PF2040W42A03T | (STG #20) Transportation | 2018-03-03 | 2018-04-30
Activity | 1CF2040W42A04 | (STG #20) Placing of Generator | 2018-05-31 | 2018-06-05
Activity | 1EF2070W42A03B | (STG #20 Aux. Equip) MPS Issue |  | 2016-12-08
Activity | 1PF2070W42A04P | (STG #20 Aux. Equip) P.O & Procurement | 2017-02-07 | 2018-03-02
Activity | 1EF2070W16A01C | (STG #20 Aux. Equip) FDN Design | 2017-10-03 | 2018-03-01
Activity | 1CF2070W16A02 | (STG #20 Aux. Equip) FDN Work | 2018-03-02 | 2018-05-28
Activity | 1PF2070W42A05T | (STG #20 Aux. Equip) Transportation | 2018-03-03 | 2018-04-30
Activity | 1CF2070W42A06 | (STG #20 Aux. Equip) Installation | 2018-05-29 | 2018-06-20
Activity | 1CF2035W58A01 | (ST #20) Piping Work | 2018-06-15 | 2018-07-04
Activity | 1CF2060W74A03 | (ST #20) Installation & Test - Elec. | 2018-06-27 | 2018-07-28
Activity | 1CF2065W90A04 | (ST #20) Installation & Test - I&C | 2018-06-27 | 2018-07-28
Activity | 1CF2035W62A02 | (ST #20) Hydro Test | 2018-06-27 | 2018-07-04
Activity | 1EF2030W42A03B | (ST #20 Lube Oil Sys.) MPS Issue |  | 2016-12-08
Activity | 1PF2030W42A04P | (ST #20 Lube Oil Sys.) P.O & Procurement | 2017-02-07 | 2018-03-02
Activity | 1EF2030W16A01C | (ST #20 Lube Oil Sys.) FDN Design | 2017-05-02 | 2017-08-01
Activity | 1CF2030W16A02 | (ST #20 Lube Oil Sys.) FDN Work | 2017-08-02 | 2017-12-01
Activity | 1PF2030W42A05T | (ST #20 Lube Oil Sys.) Transportation | 2018-03-03 | 2018-04-30
Activity | 1CF2030W42A06 | (ST #20 Lube Oil Sys.) Equipment Installation | 2018-05-01 | 2018-06-15
Activity | 1CF2030W58A07 | (ST #20 Lube Oil Sys.) Pipe Installation | 2018-06-16 | 2018-07-09
Activity | 1CF2030W62A08 | (ST #20 Lube Oil Sys.) Lube oil flushing | 2018-08-06 | 2018-08-22
Activity | 1CF2030W58A09 | (ST #20 Lube Oil Sys.) Remove Temp. Pipe | 2018-08-23 | 2018-08-28
Activity | 1EF3546W00A02 | (ST #20 Lube Oil Conditioner) Key data | 2016-12-08 | 2017-03-13
Activity | 1EF3546W42A03B | (ST #20 Lube Oil Conditioner) MPS Issue |  | 2016-12-08
Activity | 1EF3546W00A01 | (ST #20 Lube Oil Conditioner) P&ID & System Design | 2016-12-08 | 2017-07-10
Activity | 1PF3546W42A04P | (ST #20 Lube Oil Conditioner) P.O & Procurement | 2017-02-07 | 2018-02-07
Activity | 1EF3546W16A05C | (ST #20 Lube Oil Conditioner) FDN Design | 2017-02-07 | 2017-07-07
Activity | 1CF3546W16A06 | (ST #20 Lube Oil Conditioner) FDN Work | 2017-07-08 | 2017-09-07
Activity | 1PF3546W42A07T | (ST #20 Lube Oil Conditioner) Transportation | 2018-02-08 | 2018-04-06
Activity | 1CF3546W42A08 | (ST #20 Lube Oil Conditioner) Installation | 2018-04-07 | 2018-05-08
Activity | 1CF3546W58A09 | (ST #20 Lube Oil Conditioner) Piping Work | 2018-04-07 | 2018-06-23
Activity | 1CF3546W74A10 | (ST #20 Lube Oil Conditioner) Installation & Test - Elec. | 2018-05-24 | 2018-06-23
Activity | 1CF3546W90A11 | (ST #20 Lube Oil Conditioner) Installation & Test - I&C | 2018-05-24 | 2018-06-23
Activity | 1SF2000W62A02 | (ST #20) Cold-Commissioning | 2018-09-14 | 2018-10-11
Activity | 1SF2000W62A01 | (ST #20) Aux. Equipment Function Test | 2018-09-22 | 2018-10-11
Activity | 1SF2000W62A03 | (ST #20) Turnning Gear Operation | 2018-10-12 | 2018-10-13
Activity | 1SF2000W62A04 | (ST #20) Steam Blowing | 2018-10-14 | 2018-11-02
Activity | 1SF2000W62A05 | (ST #20) Temporary Piping Restoration | 2018-11-03 | 2018-11-13
Activity | 1SF9035W62A01 | (Comm'g) Steam Blowing | 2018-10-14 | 2018-11-02
Activity | 1CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2018-11-03 | 2018-11-13
Activity | 1SF9035W62A03 | (Comm'g) Bypass Operation | 2018-11-14 | 2018-11-28
Activity | 1SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2018-11-24 | 2018-11-28
Activity | 1SF9035W62A05 | (Comm'g) Steam Admission | 2018-11-29 | 2018-11-30
Activity | 1SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2018-12-01 | 2018-12-15
Activity | 1SF9040W62A07 | (Comm'g) Synchronization Test | 2018-12-16 | 2018-12-16
Activity | 1SF9040W62A08 | (Comm'g) Optimaization Test | 2018-12-17 | 2018-12-31
Activity | 1SF9040W62A09 | (Comm'g) Disturbance Test | 2019-01-01 | 2019-01-03
Activity | 1SF9040W62A10 | (Comm'g) Load Change Test | 2019-01-04 | 2019-01-06
Activity | 1SF9040W62A11 | (Comm'g) Capacity Test | 2019-01-07 | 2019-01-09
Activity | 1SF9040W62A12 | (Comm'g) Minimum Continuous Generation Load | 2019-01-10 | 2019-01-12
Activity | 1SF9040W62A13 | (Comm'g) Ramp rates Test | 2019-01-13 | 2019-01-15
Activity | 1SF9040W62A14 | (Comm'g) Full Load Rejection Test | 2019-01-16 | 2019-01-17
Activity | 1SF9040W62A15 | (Comm'g) Fast Cut Back Test | 2019-01-18 | 2019-01-19
Activity | 1SF9040W62A16 | (Comm'g) Run Back Test | 2019-01-20 | 2019-01-25
Activity | 1SF9040W62A17 | (Comm'g) Black Stop Test | 2019-01-26 | 2019-01-27
Activity | 1SF9040W62A18 | (Comm'g) Start-Up Test | 2019-01-28 | 2019-01-30
Activity | 1SF9040W62A19 | (Comm'g) Outage Period | 2019-01-31 | 2019-02-06
Activity | 1SF9040W62A20 | (Comm'g) Trial Run Test | 2019-02-07 | 2019-02-08
Activity | 1SF9041W62A21 | (Comm'g) Reliability Test | 2019-02-09 | 2019-02-11
Activity | 1SF9042W62A22 | (Comm'g) Performance Test | 2019-02-12 | 2019-02-26
Activity | 0CF6500W70A01 | (SWYD) Permissions Asquistion | 2017-09-20 | 2017-10-19
Activity | 0CF6500W70A02 | (SWYD) Coordination with Interest Groups | 2017-10-20 | 2017-11-03
Activity | 0CF6500W70A03 | (SWYD) Outage for extension | 2018-01-19 | 2018-03-04
Activity | 1CF7000W86A01 | (GTCS) Permissions Asquistion | 2018-04-14 | 2018-05-13
Activity | 1CF7000W86A02 | (GTCS) Coordination with Interest Groups | 2018-05-14 | 2018-05-28
Activity | 1CF7000W86A03 | (GTCS #21) Outage for replacing | 2018-05-29 | 2018-06-27
Activity | 2CF7000W86A04 | (GTCS #22) Outage for replacing | 2018-06-28 | 2018-07-27
Activity | 3CF7000W86A05 | (GTCS #23) Outage for replacing | 2018-07-28 | 2018-08-26
Activity | 0CF1615W42A01 | (Bypass Stack) Permissions Asquistion | 2018-04-14 | 2018-05-13
Activity | 0CF1615W42A02 | (Bypass Stack) Coordination with Interest Groups | 2018-05-14 | 2018-05-28
Activity | 0CF1615W42A03 | (Bypass Stack) Start of Outage for Modification | 2018-05-29
Activity | 0CF1615W42A04 | (Bypass Stack #21) Outage for Modification | 2018-05-29 | 2018-06-27
Activity | 0CF1615W42A05 | (Bypass Stack #22) Outage for Modification | 2018-06-28 | 2018-07-27
Activity | 0CF1615W42A06 | (Bypass Stack #23) Outage for Modification | 2018-07-28 | 2018-08-26
Activity | 0CF1615W42A07 | (Bypass Stack) Finish of Outage for Modification |  | 2018-08-26
Activity | 0CF1615W42A08 | (Outage GT #21) Remove Blacking Plate | 2018-08-27 | 2018-09-09
Activity | 0CF1615W42A09 | (Outage GT #22) Remove Blacking Plate | 2018-09-10 | 2018-09-23
Activity | 0CF1615W42A10 | (Outage GT #23) Remove Blacking Plate | 2018-09-30 | 2018-10-13